## Slide 1: MINISTRY OF HEALTH POLICY MEETING TAJ PAMODZI HOTEL 19TH DECEMBER, 2017

## Slide 2: STEP SURVEY UPDATE
POLICY MEETING
19 DECEMBER 2017

## Slide 3: Background:
Non-Communicable Diseases (NCDs) are the leading cause of death worldwide
According to WHO, of the 60 million deaths that occur annually, two-thirds are attributable to NCDs
The combined burden of these diseases is rapidly increasing in lower income countries, and Zambia is not exempt
The WHO estimates that approximately 23% of all deaths in Zambia are NCD related while the probability of premature mortality from NCDs is 18% (WHO, 2014).

## Slide 4
Zambia has not conducted a national STEP approach surveillance for Non-Communicable Diseases since it was introduced by WHO in the early 2000s.
An attempt to conduct the WHO STEP survey from 2008 to 2011 covered 2 urban and 2 rural districts and could not be completed due to insufficient financial support
Hence, Zambia has prioritized conducting of the National STEP survey in 2017. Findings from this study will provide a national baseline on the risk factors that underlie most non-communicable diseases

## Slide 5: Specific objectives for the survey
To identify the current levels of key risk factors for NCDs in the adult population aged 18 to 69 years in Zambia
To track the key selected indicators related for mental health in the adult population aged 18 to 69 years in Zambia
To track the key selected indicators related to oral health the adult population aged 18 to 69 years in Zambia.

## Slide 6: Current status
The study commenced in July 2017 covering all 10 Provinces of Zambia with support from WHO
Being led by Researchers from the University of Zambia and Centre for Infectious Disease Research in Zambia (CIDRZ) with technical support from WHO
Initially, the survey was planned to run for 40 working days. However, several challenges have arose forcing the survey to be extended for an extra 15 days requiring additional funds to successfully complete the survey.

## Slide 7: Current status (cont.)
Data collection: Now completed
Data entry and synchronization for both questionnaire and Laboratory is completed
Data Management and Cleaning: This is pending as no payment has been paid to the statistician and data manager

## Slide 8
Data analysis: the analysis workshop planned to start 15th-19th January, 2018 in Lusaka, depending on availability of resources
The current short fall is estimated to be ZMK 1, 944,900 (approx. USD 210,259)

## Slide 9
 | 2016/17 NCD SURVEY BUDGET ADDITIONAL BUDGET |  |  |  |  | Total Budget | JUSTIFICATION FOR EACH CATEGORY
Activity |  | Budget item | Qty | Frequency | Unit Cost | ZMK | 
Research Personnel |  | Principal Investigator | 1 | 70 | 2,000 | 140,000 | This will cover effort time for research team. In Kind contribution relate to the staff from the Ministry of Health
 |  | Co-PI | 1 | 70 | 1,500 | 105,000 | 
 |  | Project Coordinator | 1 | 60 | 1,000 | MoH Contribution | 
 |  | Data Manager | 1 | 60 | 1,000 | 60,000 | 
 |  | Biostastician | 1 | 40 | 1,500 | 60,000 | 
 |  | Subtotal |  |  |  | 365,000 | 
Field: Equipment |  | Test strips for lipids and glucose (pack of25) including pipettes | 240 | 1 | 484 | 16,000 | The stocks for some test run out and need to be procured. UTH is handling the testing and the project is to procure the required reagents. EMS is tranporting the urine samples from across the Country
 |  | Urine collection containers (pack of 10) | 1000 | 1 | 5 | 5,000 | 
 |  | Reagent Pack (humalyte plus 3) 1000ml | 60 | 1 | 635.04 | 8,000 | 
 |  | UTH Laboratory costs | 10 | 1 | 6,000 | 60,000 | 
 |  | EMS |  |  |  | 5,400 | 
 |  | Subtotal |  |  |  | 94,400 | 
Communication |  | Data hosting | 1 | 2 | 18000 | 36,000 | The data hosting locally is being done by the the Zambia data centre. This is a standard charge for 2 months and then data to be transferred to MoH
 |  | ONO technical support | 1 | 1 | 27000 | 27,000 | 
 |  | Airtime for Dongos | 11 | 1 | 1000 | 11,000 | 
 |  | Subtotal |  |  |  | 63,000 | 
Data collection in 10 Provinces addition 15 days |  |  |  |  |  |  | 
 |  | Per diem arrears | 40 | 45 | 300 | 540,000 | 
 |  | Per diem: Assistants | 15 | 45 | 700 | 472,500 | The RA and drivers were paid K400 for 40 days. There were arrears of K300 per day 40 days. This is in addition to the the 15 extra days for which the study has been extended
 |  | Provincial CSO mappers | 15 | 5 | 600 | 45,000 | 
 |  | Drivers arrears | 40 | 10 | 200 | 80,000 | 
 |  | Drivers | 15 | 10 | 600 | 90,000 | 
 |  | Fuel | 10 | 1 | 10,000 | 100,000 | 
 |  | Subtotal |  |  |  | 1,327,500 | 
Data Analysis/Report Writing |  | Data Analysis Workshop | 1 | 1 | 50,000 | 50,000 | This is workshop for data analysis and report writing
 |  | Subtotal |  |  |  | 50,000 | 
 |  | Printing of Final Report | 100 | 1 | 500 | 15,000 | The STEPS report wiil be printed and a day will be set asside for dissemination of results
 |  | Dissemination meetings | 100 | 1 | 1000 | 30,000 | 
Dissemination |  | Subtotal |  |  |  | 45,000 | 
 |  |  |  |  | ZMK | 1,944,900 | 
 |  |  |  |  | US$ | 210,259 |