Timeline for Bangladesh Health Financing Implementation Plan, 2013-2019

| Milestones | Sept-Dec 2013 | 2014 | 2015 | 2016-2018 | 2019 |
| --- | --- | --- | --- | --- | --- |
| Dissemination forum and meetings for target groups (influential, internal and general) |  |  |  |  |  |
| Organize the HCFS Advisory Council and HCFS Coordination Team |  |  |  |  |  |
| Contract out HF related researches and studies |  |  |  |  |  |
| HCFS incorporated in the HPNSDP after the mid-term review in Sept 2014 |  |  |  |  |  |
| MOHFW Decree for the registration of all organizations providing health pre-payment schemes by June 2014 |  |  |  |  |  |
| MOHFW Decree for the implementation of the Health protection Fund for the poor by June 2014 |  |  |  |  |  |
| Capacity development in HEU and other stakeholders |  |  |  |  |  |
| Draft legislation on health financing strategy developed and submitted for enactment, with mandatory formal sector coverage |  |  |  |  |  |
| Organization of the HF autonomous agency and coverage of formal sector |  |  |  |  |  |
| Consolidation and expansion of coverage – formal sector, poor and informal sector |  |  |  |  |  |
| Intensified M&E |  |  |  |  |  |
| Review of the HCFS legislation and advocate all necessary amendments |  |  |  |  |  |