## Sheet1
"ANNEX C" - COSTED HEALTH CARE FINANCING STRATEGY up to CY 2016 (in takas)
ACTIVITIES | LEAD | OP | Unit of Measure | July - Sep 2013 |  |  | Oct- Dec 2013 |  |  | Jan-Jun 2014 |  |  | Jul- Dec 2014 |  |  | CY 2015 |  |  | CY 2016
|  |  |  | Quantity | Unit Cost | Total | Quantity | Unit Cost | Total | Quantity | Unit Cost | Total | Quantity | Unit Cost | Total | Quantity | Unit Cost | Total | Quantity | Unit Cost | Total | TOTALS
NECESSARY LEGISLATION
Conduct Dissemination Meetings with other Ministries, parliament members, employer groups, labour unions, NGOs and others | Health Secretary and HEU | HEF (Dissemination- Meeting) | Meetings | 3 | 35000 | 105000 | [15 empty] | 105000
Organize HCFS Advisory Council with HEU as secretariat + organizational meeting | Health Minister | HEF (Dissemination- Meeting) | Meetings |  |  |  | 1 | 10000 | 10000 | [12 empty] | 10000
Quarterly meetings of the HCFS Advisory Council | HEU as secretariat | HEF (Dissemination- Meeting) | Meetings | [6 empty] | 2 | 5000 | 10000 | 2 | 5000 | 10000 | 4 | 5000 | 20000 |  |  |  | 40000
Contract out the conduct of health care financing strategy-related legal and policy research and drafting of legislation, policies and guidelines | HCFS Advisory Council | HEF (Conduct Research) | Consultancy Firm contract |  |  |  | 1 | 2000000 | 2000000 | [12 empty] | 2000000
Law passed on National Health Financing Strategy with mandatory formal sector, registration of independent health pre-payment schemes, and government subsidies for the poor | Parliament | Law (No OP) | N/A
Organization of an Autonomous HCFS government agency (as established by law) with governing board, management team, operations unit, technical services, regulatory unit, marketing unit, provider support unit and all other needed units | HCFS Advisory Council | New OP | see pages 15 and 16 | [18 empty] | 0
COORDINATION | [21 empty] | 0
Conduct Dissemination forums on the HCFS among MoHPW staff (including government personnel in the DGHS, DGFP, public hospitals and other MoHPW units) | HEU | HEF (Dissemination- Meeting) | Meetings | 3 | 15000 | 45000 | [15 empty] | 45000
Organize HCFS Coordination team + organizational meeting | Health Secretary | HEF (Dissemination- Meeting) | Meetings | 1 | 5000 | 5000 | [15 empty] | 5000
Monthy meetings by the HCFS Coordination Team | HEU | HEF (Dissemination- Meeting) | Meetings |  |  |  | 3 | 4000 | 12000 | 6 | 4000 | 24000 | 6 | 4000 | 24000 | 12 | 4000 | 48000 |  |  |  | 108000
Drafting and submission to the MoHFW planning wing of the amended costed Operational plans (OP) related to HCFS implementation | HEU | HEF (development of policy briefs, strategies and options) | Policy paper | 1 | 5000 | 5000 | [15 empty] | 5000
Drafting and submission of the Amended and/or New costed Operational plans (OP) related to HCFS for incorporation in the revised Program Implementation Plan of the HPNSDP | HCFS Coordination Team | HEF (development of policy briefs, strategies and options) | Policy paper | [6 empty] | 1 | 50000 | 50000 | [9 empty] | 50000
IMPLEMENTATION CAPACITY | [21 empty] | 0
Hiring of additional technical staff for the HEF sub-unit of the Health Economics Unit (HEU) | HEU | HEF (Staffing) | Technical staff | [9 empty] | 6 | 300000 | 1800000 | 6 | 600000 | 3600000 | 6 | 600000 | 3600000 | 9000000
Hiring of additional adminstrative staff for the HEF sub-unit of the Health Economics Unit (HEU) | HEU | HEF (Staffing) | Adminstrative staff | [9 empty] | 6 | 150000 | 900000 | 6 | 300000 | 1800000 | 6 | 300000 | 1800000 | 4500000
New office space and equipment and addition running costs related to the additional technical and administrative staff | HEU | HEF (Capital + Running Costs) | Lump sum | [9 empty] | 1 | 250000 | 250000 | 1 | 500000 | 500000 | 1 | 500000 | 500000 | 1250000
Setting up of HEU-Health Protection Fund (poor) central operations cell including hiring of staff a | HEU | HEF (Staffing) | Technical and Administrative staff | [9 empty] | 8 | 250000 | 2000000 | 8 | 500000 | 4000000 | 8 | 500000 | 4000000 | 10000000
Organization of offices related to the setting up of HEU Health Protection Fund (poor) central operations cell | HEU | HEF (Capital + Running Costs) | Lump sum | [9 empty] | 1 | 150000 | 150000 | 1 | 300000 | 300000 | 1 | 300000 | 300000 | 750000
Setting up of HEU-Health Protection Fund (poor) field operations cell including hiring of staff | HEU | HEF (Staffing) | Technical and Administrative staff | [9 empty] | 10 | 225000 | 2250000 | 10 | 450000 | 4500000 | 10 | 450000 | 4500000 | 11250000
Organization of offices related to the setting up of HEU Health Protection Fund (poor) field operations cell | HEU | HEF (Capital + Running Costs) | Lump sum | [9 empty] | 1 | 500000 | 500000 | 1 | 500000 | 500000 | 1 | 500000 | 500000 | 1500000
MoHFW decree directing the pilot implementation of the Health Protection Fund for the poor | MoHFW | Decree (no OP) | N/A
Launch of the Health Protection Fund (poor) scheme in three sites | HEU | HEF (Capital + Running Costs) | Lump sum | [9 empty] | 1 | 100000 | 100000 | [6 empty] | 100000
Health Protection Fund (poor) premium subsidies for eligible poor families | HEU | new OP | Families | [9 empty] | 70000 | 1000 |  | 70000 | 1000 |  | 70000 | 1000 |  | 0
MoHFW decree mandating the registration and regulation with the MoHFW (HEU) of health pre-payment schemes not run by government | MoHFW | Decree (no OP) | N/A | [18 empty] | 0
Manage registration and regulation of the health pre-payment schemes not run by government | HEU | HEF (Capital + Running Costs) | Lump sum | [6 empty] | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 4 | 100000 | 400000 | 4 | 100000 | 400000 | 1000000
Contracting for the drafting of manual of operations for the member management, health care provider contracting an payments, claims management and fund management based in the implementation of the Health Protection Fund (poor) | HEU | HEF (development of policy briefs, strategies and options) | Individual Consultancy contract | [12 empty] | 1 | 500000 | 500000 |  |  |  | 500000
Drafting of the Terms of Reference for the contracting out of Health Care Financing Strategy-related technical activities | HEU | HEF (Consultancy) | Individual Consultancy contract | 1 | 600000 | 600000 | [15 empty] | 600000
Contract with the Institute of the Health Economics the conduct of the health financing research including fiscal space analysis; benefits coverage options; and provider contracting and payment options | HEU | HEF (Research) | Consultancy Firm contract |  |  |  | 1 | 15000000 | 15000000 |  |  |  | 1 | 5000000 | 5000000 | 1 | 5000000 | 5000000 | 1 | 5000000 | 5000000 | 30000000
Studies on the basic benefit packages including premium rates and provider payment methods completed and submitted to the HCFS Advisory Council
Benefit package approved and implemented
Contract out with an independent organization the monitoring and evaluation of the health care financing strategy | HEU | HEF (Research) | Consultancy Firm contract | [6 empty] | 1 | 500000 | 500000 | 1 | 500000 | 500000 | 1 | 1000000 | 1000000 | 1 | 1000000 | 1000000 | 3000000
Independent M and E system in place
Enterprise architecture, health data dictionary and other health data standards and connectivity rules completed and approved | DGHIS-HIS | DGHS-HIS & e-health | Lump sum | [6 empty] | 1 | 100000 | 100000 | [9 empty] | 100000
Autonomous agency organized to conduct the the following activities | New autonomous government agency | New OP | see pages 15 and 16 | [18 empty] | 0
Collection of mandatory premium contributions by the formal sector started
Contracting of hospitals and health facilities rolled out nationally
Payment of covered services in contracted hospitals
Audit of contracted hospitals and health faciltities as to compliance with rules and regulations
Membership database build up and production and distribution of ID cards started
EFFICIENCIES | [21 empty] | 0
Organize HCFS Efficiencies Unit led by the DGHS + organizational meeting | DGHS | DGHS OP | Meetings | 1 | 2000 | 2000 | [15 empty] | 2000
Conduct of regular meetings of the HCFS Efficiencies Unit | DGHS | DGHS OP | Meetings |  |  |  | 1 | 2000 | 2000 | 2 | 2000 | 4000 | 2 | 2000 | 4000 | 4 | 2000 | 8000 |  |  |  | 18000
Contract out with the local organization the development of management training modules and the conduct of management training (including financial management) of government health facilities | HEU | HEF (Research) | Consultancy Firm contract |  |  |  | 1 | 500000 | 500000
Management training modules conducted in Upazilla and district government hospitals | NIPSOM | NIPSOM OP | Hospitals | [6 empty] | 15 | 20000 | 300000 | 15 | 20000 | 300000 | 40 | 20000 | 800000 | 80 | 20000 | 1600000 | 3000000
Retention of incentives as allowed in the DSF scheme expanded to all types of incentives given to government health care providers | MOHPW | Decree (no OP) | N/A | [18 empty] | 0
Increase in the target number of hospitals that would be granted management automony from 3 per year to 20 per year | DGHS | DGHS Hospital Services Management OP | see pages 14 and 15
Expansion on the activities related to Total Quality Management, Quality Assurance, Accreditation and Referral systems | DGHS | DGHS Hospital Services Management OP | see pages 14 and 15
Need-based allocation system approved and implemented | DGHS | DGHS Planning, Monitoring and Research OP | see pages 14 and 15 | [18 empty] | 0
Web-based medicine procurement and distribution system deployed and utilized | DHGS | DGHS Procurement, Logistics and Supply Management OP | see pages 14 and 15 | [18 empty] | 0
Demand side financing expanded to all facilities (or integrated into the benefits paid by the SSK) | DGHS | MNCAH OP | see pages 14 and 15 | [18 empty] | 0
PUBLIC SUPPORT | [21 empty] | 0
Conduct dissemination forums for concerned stakeholders and the general public in all divisions | HEU-GNSP | HEFDissemination | Forums | 5 | 80000 | 400000 | 2 | 80000 | 160000 | [12 empty] | 560000
Organize HCFS Stakeholder Alliance led by the GNSP of the HEU | HEU-GNSP | GNSP Dissemination Meeting | Meetings |  |  |  | 1 | 30000 | 30000 | [12 empty] | 30000
HCFS National Workshops | Stakeholder Alliance | GNSP Dissemination Meeting | Workshops | [6 empty] | 1 | 250000 | 250000 | 1 | 200000 | 200000 | 1 | 200000 | 200000 | 1 | 200000 | 200000 | 850000
Monthly assembly of the HCFS Stakeholder Alliance | HEU-GNSP | GNSP Dissemination Meeting | Meetings | [6 empty] | 5 | 25000 | 125000 | 6 | 25000 | 150000 | 12 | 25000 | 300000 | 12 | 25000 | 300000 | 875000
Contract out with a private/non-government organization the development and implementation of marketing plan | Stakeholder Alliance | GNSP-Research | Consultancy Firm contract |  |  |  | 1 | 800000 | 800000 | 1 | 500000 | 500000 |  |  |  | 1 | 500000 | 500000 | 1 | 500000 | 500000 | 2300000
Marketing and communication plan approved and implemented
Division-level HCFS Stakeholder alliances organized | HEU-GNSP | GNSP Dissemination Meeting | Meetings | [6 empty] | 7 | 50000 | 350000 | [9 empty] | 350000
HCFS Division-level workshops | Stakeholder Alliance | GNSP Dissemination Meeting | Workshops | [9 empty] | 7 | 50000 | 350000 | 7 | 50000 | 350000 | 7 | 50000 | 350000 | 1050000
TOTALS | [5 empty] | 1162000 |  |  | 18514000 |  |  | 2313000 |  |  | 14588000 |  |  | 24326000 |  |  | 24550000 | 85453000