## Scoring & Ranking
Unit # | Area of Work | Level | Milestone | Deliverable | Responsible | Activity | Start | Due | Alignment Scores ∑ 0 … 6 | Impact Scores ∑ 0 … 9 | Compound Score % of max. | Unit Cost estimate EUR | Staff Time person days | Activity's Total Budget | Activity's Value | Activity's Efficiency | Rank by Efficiency | Risk Narrative | Accomplishment Risk 0 … 100% | Time Critical y/n
1 | P4H Expansion | Global | Regular attendance of meetings | Maintain networking with WHO program specific teams and units | Bayar | Partner with WHO programs and thematic teams at different levels. | 2018-01-01 | 2018-12-31 | 3 | 7 | 38.89% | 5000 | 20 | 21000 | 7350 | 35% | 27 | Program specific constraints | 0.9 | n
2 | P4H Expansion | Global | Expand scope of p4h.world | Contribution to / posinioning in UHC2030 agenda. | Helga | Promote of P4H products & advice on P4H services (e.g. white labeling, L4UHC, etc.); dig. comm. strategy. | 2018-01-01 | 2018-12-31 | 6 | 8 | 88.89% | 10000 | 30 | 34000 | 30222.2222 | 88.89% | 4 |  | 1 | n
3 | P4H Expansion | Global | Follow-up of the second WG meeting held in Montreux in Nov 2017. | Increase P4H specific inputs into UHC 2030 movement. | Bayar | Offer P4H platform to UHC 2030 WG on sustainability, transition and health system strengthening | 2018-03-01 | 2018-09-30 | 5 | 5 | 46.3% | 0 | 5 | 4000 | 1851.8519 | 46.3% | 20 | It may need extended discussions | 1 | y
4 | P4H Expansion | Global |  |  | Gwen | NAG | 2018-01-01 | 2018-12-31 | 3 | 8 | 44.44% | 0 | 30 | 24000 | 8533.3333 | 35.56% | 26 |  | 0.8 | y
5 | P4H Management | Global | 70% of the planned activities are properly executed | Activities specified in the 2018 are realised to the maximum extent | Claude | P4H Team Functional Management | 2018-01-01 | 2018-12-31 | 6 | 7 | 77.78% | 100000 | 25 | 120000 | 93333.3333 | 77.78% | 6 | Less credibility of P4H amongst the donors and partner organizations | 1 | y
6 | P4H Governance | Global | Draft agenda adopted. | SG Meeting is held. | Claude | SG related work (contacts, preparation of meetings…) | 2018-01-01 | 2018-09-30 | 6 | 9 | 100% | 0 | 20 | 16000 | 16000 | 100% | 1 |  | 1 | y
7 | P4H Expansion | Global |  |  | Gwen | TCG related work | 2018-01-01 | 2018-12-31 | 5 | 7 | 64.81% | 0 | 14 | 11200 | 6533.3333 | 58.33% | 17 |  | 0.9 | n
8 | P4H Expansion | Country: Tunisia… |  |  | Gwen | Contact with pre-identified potential new P4H members | 2018-01-01 | 2018-12-31 | 4 | 4 | 29.63% | 0 | 6 | 4800 | 1137.7778 | 23.7% | 35 |  | 0.8 | y
9 | P4H Expansion | Global: Institutions | CEB |  | Gwen | Contact with pre-identified potential new P4H members | 2018-01-01 | 2018-12-31 | 5 | 7 | 64.81% | 0 | 6 | 4800 | 2488.8889 | 51.85% | 19 |  | 0.8 | y
10 | P4H Expansion | Country: Morrocco |  |  | Gwen | Develop workplans with members which recently joined | 2018-01-01 | 2018-12-31 | 5 | 7 | 64.81% | 0 | 12 | 9600 | 3111.1111 | 32.41% | 30 |  | 0.5 | n
11 | P4H Expansion | Country: Cambodia | All P4H representatives/associates are cross-fertilised | P4H representatives/associates have a better appreciation of possible configurations for optimal collaborations at country level | Bart | P4HC+ special day in Cambodia (followed by 2-day workshop on P4H specific issues) | 2018-06-01 | 2018-09-30 | 6 | 9 | 100% | 0 | 45 | 36000 | 36000 | 100% | 1 | An unhappy donor | 1 | y
12 | P4H Expansion | Global | Deepened cooperation with UHC 2030 | Increase P4H country base into UHC 2030 | Josselin | Contribute to global discussion based on Cameroonian experience | 2018-06-01 | 2018-12-31 | 3 | 4 | 22.22% | 0 | 3 | 2400 | 266.6667 | 11.11% | 43 |  | 0.5 | n
13 | P4H Expansion | Region: Central Africa | One country focal point is in place in Chad in 2018 | P4H is expanding at country and regional level in CA countries, including a physical presence | Saibou | Tentative expansion of P4H ressource persons in Chad and other Central Africans Countries | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 0 | 65 | 52000 | 34666.6667 | 66.67% | 12 | Missed opportunity | 1 | y
14 | P4H Geographical Networks | Continent: Africa | Meeting launching ACS/P4H strategic collaboration | P4H regional networking in Africa is structured on the basis of the continent | Claude | Participate in an emerging « African continent P4H network » | 2018-01-01 | 2018-12-31 | 4 | 6 | 44.44% | 20000 | 30 | 44000 | 19555.5556 | 44.44% | 23 | P4H extension is not consistent with its members' regional organization and provides no alternative | 1 | y
15 | P4H Geographical Networks | Region: West Africa | Discussion with ADB, USAID, UEMOA. | Sensitization of regional level of organizations (UNICEF, USAID), regional organizations (OOAS, UEMOA) and other active actors in WA (eg: EU) | Alexis | Promote P4H with a focus on P4H platform & P4H products to all relevant WA region stakeholders | 2018-01-01 | 2018-12-31 | 4 | 8 | 59.26% | 0 | 3 | 2400 | 995.5556 | 41.48% | 24 | P4H is missing the WA subregional levels of networks | 0.7 | n
16 | P4H Geographical Networks | Region: EAC | Advocate for harmonised, strengthened move towwards UHC via expanded and strengthened HF/ SHP systems | Follow-up SHP leadership conference in East Africa ( the 2012 conference) | Nina | Re-ignite the joint efforts towards UHC via SHP in the East African Region and obtain high level leadership support | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 200000 | 30 | 224000 | 74666.6667 | 33.33% | 28 | Available Funding and commitment to organise and host such event by one EAC PS | 0.5 | n
17 | P4H Geographical Networks | Region: EAC | One regional focal point is in place in the EA Region in 2018 | P4H is expanding its regional level activity | Nina | Preparing the ground for a RFP at EAC Secretariat level | 2018-01-01 | 2018-12-31 | 6 | 8 | 88.89% | 150000 | 35 | 178000 | 126577.7778 | 71.11% | 10 | agreement to post/ fund RFP by network partners | 0.8 | y
18 | P4H Geographical Networks | Region: West Africa | P4H to become a WHO/AFRO strategy; P4H WA RFP ToR are included in current position | High level discussions with WHO/AFRO | Claude | Preparing the ground for a formalized RFP in WA | 2018-01-01 | 2018-12-31 | 7 | 5 | 64.81% | 2000 | 4 | 5200 | 1685.1852 | 32.41% | 30 | P4H cannot develop in Africa | 0.5 | y
19 | P4H Geographical Networks | Country: Mali, Mauritania, Niger | One country focal point is in place in WA in 2018 | P4H is expanding at country level in WA including a physical presence | Alexis | Tentative expansion of CFP / P4H ressource persons in Western Africa (Mauritania, Niger, Mali…) | 2018-01-01 | 2018-12-31 | 7 | 5 | 64.81% | 1500 | 30 | 25500 | 11569.4444 | 45.37% | 21 | There is no P4H continuum in country, thus no P4H added value | 0.7 | n
20 | P4H Geographical Networks | Country: Cameroon | Explored cooperation between P4H and HDC in Country | Create links between P4H and HDC networks at country level | Josselin | Develop one common activity with HDC in Cameroon | 2018-06-01 | 2018-12-31 | 3 | 4 | 22.22% | 0 | 3 | 2400 | 373.3333 | 15.56% | 37 |  | 0.7 | n
21 | P4H Geographical Networks | Country: Cameroon | Cameroon CFP is formalised | P4H is expanding at country and regional level in CA countries, including a physical presence | Josselin | Promote P4H products in Cameroon | 2018-06-01 | 2018-12-31 | 6 | 9 | 100% | 0 | 11 | 8800 | 880 | 10% | 44 |  | 0.1 | n
22 | P4H Geographical Networks | Region: Central Africa | First contact is established with CEMAC | CEMAC is aware of P4H activities and design | Josselin | Meet with a representative of CEMAC | 2018-06-01 | 2018-12-31 | 5 | 4 | 37.04% | 0 | 3 | 2400 | 622.2222 | 25.93% | 34 |  | 0.7 | n
23 | P4H Geographical Networks | Country: DRC | Relationship with DRC is established | DRC process is again documented in the digital space | Josselin | Meet with a representative of DRC + document P4H platform | 2018-06-01 | 2018-12-31 | 5 | 5 | 46.3% | 0 | 3 | 2400 | 777.7778 | 32.41% | 30 |  | 0.7 | n
24 | Country Collaboration | Country: Chad | At least one activity are implemented in a joined way in 2018 | The interventions of P4H partners are coherent and are made in the joined way | Saibou | Develop a P4H joined workplan with UHC partners in the Chad | 2018-01-01 | 2018-12-31 | 4 | 4 | 29.63% | 0 | 30 | 24000 | 3555.5556 | 14.81% | 38 |  | 0.5 | y
25 | Country Collaboration | Country: Cambodia | Measures for organizational development of the NIPH are implemented, indicators agreed upon with NSPC, report 2017 published | Informed decision making by the National Social Protection Council (NSPC) using valid and reliable data | Bart | Support to the National Institute of Public Health(NIPH) to become a resource centre for M&E on UHC | 2018-01-05 | 3m31.12.18 | 6 | 6 | 66.67% | 0 | 10 | 8000 | 1066.6667 | 13.33% | 41 | non-aligned, fragmented and unequal social health protection system | 0.2 | y
26 | Country Collaboration | Country: China, Mongolia | Partnership opportunities are created and supported in countries like China, Mongolia and others. | Organize and provide P4H support to meet country specific needs and requests. | Bayar | Update country profiles and support activities in countries. | 2018-01-01 | 2018-12-31 | 5 | 8 | 74.07% | 0 | 20 | 16000 | 11851.8519 | 74.07% | 8 | Government interest and priority need to be validated | 1 | y
27 | Country Collaboration | Mozambique | Mozambique | P4H support to HF and SHP reforms and processes | Cristina | P4H approach in HCF / SHP strategies & reforms in development & implementation. Technical advising for HCF / SHP reforms. | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 10000 | 70 | 66000 | 22000 | 33.33% | 28 |  | 0.5 | y
28 | Country Collaboration | Country: Mozambique | Mozambique | P4H framework is promoted | Cristina | Support cooperation partners Sectoral groups in Health Financing, Health Planning, and Social protectionP4H technical meetings with partners | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 10000 | 15 | 22000 | 11733.3333 | 53.33% | 18 |  | 0.8 | n
29 | Country Collaboration | Country: Chad | at least two meetings are organized in 2018 | A permanent dialogue is established between the P4H partners and the national UHC team | Saibou | Organize regular meetings of dialogue between P4H partners and the national UHC team | 2018-01-01 | 2018-12-31 | 5 | 6 | 55.56% | 0 | 30 | 24000 | 9333.3333 | 38.89% | 25 |  | 0.7 | y
30 | Knowledge Management | Global | Support SG in strategic decision making. | SG receives needed strategic information. | Helga | Offer strategic information to the SG (e.g. calender, work plan, etc.). | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 0 | 18 | 14400 | 8640 | 60% | 16 |  | 0.9 | y
31 | Knowledge Management | Region: EAC | Have active news feeds for all EAC coutnries | The plateform reflects what is going on at country and regional level | Nina | Regular news feeds on designated countries/ region (EAC) | 2018-01-01 | 2018-12-01 | 6 | 7 | 77.78% | 0 | 30 | 24000 | 18666.6667 | 77.78% | 6 | Regular access to country news of coutnries where CFP not based | 1 | y
32 | Knowledge Management | Country: FP countries | 8 to 10 good country examples in 2018 | The plateform reflects what is going on at country level and meets its purpose | Claude | Tentative adequate informing of country pages in P4H platform | 2018-01-01 | 2018-12-31 | 6 | 8 | 88.89% | 0 | 5 | 4000 | 3555.5556 | 88.89% | 4 | The plateform project fails | 1 | y
33 | Knowledge Management | Country: FP countries | 2 in-country sessions (Ivory Coast & Indonesia) | Success of the programme according to specifically developped M&E | Claude | Rolling ou of L4UHC flagship programme | 2018-01-01 | 2018-12-31 | 6 | 7 | 77.78% | 0 | 20 | 16000 | 9955.5556 | 62.22% | 14 | continouity of leadership positions | 0.8 | n
34 | Knowledge Management | Mozambique |  | The platform reflects what is going on at country level and meets its purpose | Cristina | Update of activities, seminars, news, National Health Accounts, Health Financing Strategy, GFF and National Health Insurance | 2018-01-01 | 2018-12-31 | 6 | 6 | 66.67% | 10000 | 5 | 14000 | 9333.3333 | 66.67% | 12 |  | 1 | y
35 | Innovations & Other Technical Work for Products to Be | Global | Establish contacts with potential partners e.g. Harvard University which has shown interest in political economy of UHC | Strengthen the UHC concept and its practical applications to increase political commitment. | Bayar | Initiate discussions to promote P4H values from political economy contexts. | 2018-02-01 | 2018-12-31 | 6 | 8 | 88.89% | 30000 | 35 | 58000 | 41244.4444 | 71.11% | 9 | Contract may not approved | 0.8 | y
36 | Innovations & Other Technical Work for Products to Be | Global |  |  | Gwen | Turnkey Network Tool | 2018-01-01 | 2018-12-31 | 6 | 7 | 77.78% | 0 | 30 | 24000 | 16800 | 70% | 11 |  | 0.9 | n
37 | Innovations & Other Technical Work for Products to Be | Country: Malawi | Reviewed draft of Malawi HFS available | Assessment has been used by the HFS drafting team to review and modify the Malawi HFS | Svenja | Develop a political economy assessment of the expected draft Malawi HFS | 2018-11-01 | 2018-12-31 | 6 | 5 | 55.56% | 50000 | 15 | 62000 | 6888.8889 | 11.11% | 42 | Depending on tool availability, unlikely to actually be finished in Dec | 0.2 | y
38 | Innovations & Other Technical Work for Products to Be | Country: Zambia | Dissemination of results of the analytical work on the informal economy | Analytical work on the informal economy is jointly produced by ILO and OECD, with technical inputs from WHO, and results are jointly used to inform policy decision on extension of SHP to workers in the informal economy | Marielle | Carry-on joint study on the informal economy (OECD, ILO, WHO?) | 2018-01-01 | 2018-05-31 | 4 | 4 | 29.63% | 0 | 35 | 28000 | 4148.1481 | 14.81% | 38 | WHO is not official partner, therefore cannot be communicated as a P4H product | 0.5 | y
39 | Innovations & Other Technical Work for Products to Be | Country: Tanzania, Burkina Faso, Cameroon, Malawi | Have at least 2 country evaluations by April 2018 | Evidence for P4H network provision of quality services and products is produced | Nina | Testing / applying of P4H M&E tool at country level | 2018-02-01 | 2018-09-01 | 6 | 9 | 100% | 15000 | 10 | 23000 | 23000 | 100% | 1 | Available funding to conduct qualitative data collection, availability of CFP/ partners | 1 | y
40 | Innovations & Other Technical Work for Products to Be | Country: Burkina Faso | Documentation of GFF process in Burkina Faso | P4H ToR prove to apply in the context of global financing initiatives | Alexis | Supportting the conection of global financing mecanism (GFF, GFTAM & GAVI) with healthfinancing systemic approach | 2018-01-01 | 2018-12-31 | 6 | 5 | 55.56% | 0 | 12 | 9600 | 4266.6667 | 44.44% | 22 | P4H has no added enough value inside the department of Health compared to intersectoral level | 0.8 | n
41 | Visibility | Global | Knowledge sharing. | Establish contacts with eligible experts, who are able to translate P4H specific docs as needed. | Helga | Facilitate translation processes in UN & other languages. | 2018-05-01 | 2018-12-31 | 6 | 3 | 33.33% | 10000 | 5 | 14000 | 3733.3333 | 26.67% | 33 |  | 0.8 | n
42 | Visibility | Global | Draft documents | Articles or documents published | Claude | Documenting best practices by P4H at country, regional and global level | 2018-01-01 | 2018-06-30 | 3 | 3 | 16.67% | 0 | 5 | 4000 | 666.6667 | 16.67% | 36 | Lost opportunities for optimising P4H activities and results | 1 | n
43 | Visibility | Global |  |  | Gwen | Editing monthly newletter | 2018-01-01 | 2018-12-31 | 3 | 3 | 16.67% | 0 | 12 | 9600 | 320 | 3.333% | 46 |  | 0.2 | y
44 | Visibility | Region: Russian speaking | At least one event to promote P4H is organized | Discuss and promote P4H in Russian speaking countries | Bayar | Translate P4H TORs into Russian | 2018-06-01 | 2018-12-31 | 2 | 5 | 18.52% | 30000 | 25 | 50000 | 7407.4074 | 14.81% | 38 | Contract may not approved. | 0.8 | n
45 | Visibility | Country: Malawi | One article on Malawi NHI assessment accepted by a scientific journal | P4H supported activities gain prominence in policy-making and scientific community | Svenja | Publicize P4H supported work in Malawi | 2018-01-01 | 2018-12-31 | 1 | 5 | 9.259% | 0 | 5 | 4000 | 259.2593 | 6.481% | 45 | Acceptance of paper | 0.7 | n
46 | Capacity Building | Region: Central Africa | Cameroon participates in L4UHC programme | L4UHC is implement for Cameroon | Josselin | Support/facilitate the gobal process | 2018-06-01 | 2018-12-31 | 6 | 7 | 77.78% | 0 | 7 | 5600 | 3484.4444 | 62.22% | 14 |  | 0.8 | n

## Resources Determination
Person | % of full-time | days p.a. available for projects | Cost (e.g. travel expens, etc.)
CD1 | 1 | 105 |  |  | workdays p.a. | 210
CD2 | 1 | 105 |  |  | time required for routine | 50%
CD3 | 1 | 105 |  |  | Cost of staff day | 800
CD4 | 0.5 | 52.5 |  |  | Total Staff days available | 882
CD5 | 0 | 0
RFP1 | 0.5 | 52.5 |  |  | Total staff days planned | #VALUE!
CFP1 | 1 | 105 |  |  | balance | 0
CFP2 | 1 | 105
CFP3 | 0.75 | 78.75 |  |  | Total cash available | 430000
CFP4 | 0.75 | 78.75 |  |  | WHO | 130000
CFP5 | 0.5 | 52.5 |  |  | GIZ BMZ | 100000
CFP6 | 0.2 | 21 |  |  | GIZ SDC | 200000
CFP7 | 0.2 | 21 |  |  | total cash required | #VALUE!
CFP8 | 0 | 0 |  |  | balance | -223500
RFP2 | 0 | 0
CD6 | 0 | 0
Total time allocation |  | 882 |  | ONLY FILL IN THESE KIND OF FIELDS!!!

## CT Country Map
# | Country | R/CFP |  | P4H CD
1 | Bangladesh |  |  | Bayar | WHO
2 | Benin | Alexis | AFRO | Claude | WHO
3 | Burkina Faso | Alexis | AFRO | Gwen | WHO
4 | Burundi | (Nina) | GIZ | Claude | WHO
5 | Cambodia | Bart | GIZ/SDC | Claude | WHO
6 | Cameroon | Josselin | GIZ | Claude | WHO
7 | Chad | Saibou | GIZ | Claude | WHO
8 | Colombia |  |  | Claude | WHO
9 | Congo |  |  | Gwen | WHO
10 | Cote d'Ivoire |  |  | Gwen | WHO
11 | Ethiopia
12 | Haiti | Ludovic | PAHO | Claude | WHO
13 | India |  |  | Gwen | WHO
14 | Indonesia | Zohra | USAID
15 | Kenya | (Nina) | GIZ
16 | Kyrgyzstan |  |  | Bayar | WHO
17 | Lao PDR | Bart | GIZ/SDC | Claude | WHO
18 | Madagascar |  |  | Claude | WHO
19 | Malawi | Svenja | GIZ
20 | Mali | Alexis | AFRO | Gwen | WHO
21 | Mauritania | Alexis | AFRO | Gwen | WHO
22 | Morocco |  |  | Gwen | WHO
23 | Mozambique | Cristina | GIZ | Claude | WHO
24 | Mongolia |  |  | Bayar | WHO
25 | Myanmar | Bart | GIZ | Bayar | WHO
26 | Nepal
27 | Niger | Alexis | AFRO | Gwen | WHO
28 | Philippines |  |  | Bayar | WHO
29 | RD Congo |  |  | Claude | WHO
30 | Rwanda | (Nina) | GIZ | Claude | WHO
31 | Senegal |  |  | Gwen | WHO
32 | Tanzania | Nina | GIZ
33 | Tajikistan |  |  | Bayar | WHO
34 | Togo | Alexis | AFRO | Gwen | WHO
35 | Uganda | (Nina) | GIZ
36 | Vietnam |  |  | Gwen | WHO
37 | Yemen |  |  | Claude | WHO
38 | Zambia | Marielle | ILO