## Scoring and Ranking
Unit # | Area of Work | Geographical level | Responsible | Objective (beyond oneself and beyond 2020) | Deliverable for June 2020 | Activities | Start | Due | Alignment Scores ∑ 0 … 6 | Impact Scores ∑ 0 … 9 | Compound Score % of max. | Unit Cost Estimate EUR | Staff Time Person Days | Activity's Total Budget | Activity's Value | Activity's Efficiency | Rank by Efficiency | Risk Narrative | Accomplishment Risk 0 … 100% | Time Critical y/n
1 | P4H Visibility | P4H partner countries | A1. CFP & RFP | The p4h.world platform gives P4H an uncomparable value-add in the global and local HF environment | Countries' pages are updated and reflect what happens in an adapted way; key actors in-country are enrolled as members on p4h.world | Regular updated; recruitment of members and possibly of (co)administrators (for some collaborations) | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 100.53 | 80424 | 80424 | 100% | 2 |  | 1 | y
2 | P4H Visibility | P4H partner countries | A1. CFP & RFP | P4H countries' documentation | To all CFP specific lines corresponds a specific output that participates in capitalizing P4H added value in country. Participation in the L4UHC programme also means documentation of practice. Documentation of regular ToR also appreciated. | Formalization of output from each specific activities | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 167.55 | 134040 | 134040 | 100% | 2 |  | 1 | y
3 | P4H Country Collaboration | P4H partner countries | A1. CFP & RFP | The FP prove to be an adapted set up for the implementation of the P4H network at country level | The focal points implemented their P4H related ToR, especially in terms of coordination, based on their technical expertise | All Country & Regional Focal Points generic and specific ToR | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 50000 | 402.12 | 371696 | 278772 | 75% | 30 |  | 0.75 | n
4 | P4H Management | P4H partner countries | A2. CFP & RFP & CD | Great network | Annual Report to the results of our activities of our strategic planning & work program | 2 physical meetings & 10 monthly TCs are held | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 75000 | 130 | 179000 | 143200 | 80% | 14 |  | 0.8 | n
5 | P4H Country Collaboration | Senegal | Abdoulaye | Capitalization methodology to describe Senegals experience in health financing with the HF technical working group | Capitalization of Senegals experience in health financing is achieved | Support the capitalization of Senegal's experience in health financing | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 5000 | 55 | 49000 | 34844.4444 | 71.11% | 34 |  | 0.8 | n
6 | P4H Country Collaboration | Senegal | Abdoulaye | To support the evaluation of the "CMU" programme (universal financial risk protection) in collaboration with all DPs and stakeholders | Evaluation document | Participation in the overall process. | 2019-07-01 | 2019-07-01 | 6 | 8 | 88.89% | 0 | 10 | 8000 | 0 | 0% | 81
7 | P4H L4UHC Product | Senegal | Abdoulaye | L4UHC 2nd Francophone Africa session is a success | Senegal team got support in the L4UHC modules and in the RRI. The overall session benefited from a UHC expertise | Participation in the overall session as UHC expert; follow-up of the RRI in Senegal | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 7000 | 15 | 19000 | 13511.1111 | 71.11% | 37 |  | 0.8 | n
8 | P4H Geographical Networks | Benin, Mali, Mauritania, Niger, Togo | Alexis | P4H is expanding at country level in WA with focal points in more countries | There is a focal point in Niger. Progresses are made towards the presence of a focal point in at least one other country in WA | Active coordination of development partners to organize a P4H in-country set up is finalized in Niger and starts in Ivory Coast and/or Mali and/or Benin | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 1500 | 12 | 11100 | 6906.6667 | 62.22% | 46 | There is no P4H continuum in country, thus no P4H added value | 0.7 | n
9 | P4H L4UHC Product | Africa | Alexis | L4UHC 2nd Francophone Africa session is a success | Niger & Burkina teams got support in the L4UHC modules and in the RRI. The overall session benefited from a UHC expertise | Participation in the overall session as UHC expert; follow-up of the RRI in Burkina Faso & Niger | 2019-07-01 | 2020-06-30 | 6 | 6 | 66.67% | 7000 | 15 | 19000 | 10133.3333 | 53.33% | 57 |  | 0.8 | n
10 | P4H Visibility | Africa | Alexis | CFP more at ease with their ToR and P4H tools | New CFPs in Western Africa master their ToR | Light coaching of CFP in francophone Africa with a focus on Western Africa (regular TCs) | 2019-07-01 | 2020-06-30 | 5 | 6 | 55.56% | 1000 | 10 | 9000 | 4000 | 44.44% | 63 |  | 0.8 | n
11 | P4H L4UHC Product | Global | Alexis | L4UHC program is implemented well and progressing towards sustainability | Contributions have been made in the L4UHC program documents | Participation to the global coordination team meetings & to documents & discussions | 2019-07-01 | 2020-06-30 | 6 | 6 | 66.67% | 1000 | 10 | 9000 | 4800 | 53.33% | 57 |  | 0.8 | n
12 | P4H Country Collaboration | Kazakhstan | Arystan | Finalize terms for Kazakhstan's contribution to network | Signed contract on RK contribution to the network with the WHO | Include proposal of budget reconsideration agenda for Foreign Affairs consideration and/or negotiate with WHO HQ to include healthcare financing question in the amount that RK contributes to suppor GDO on PHC in Almaty | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 45 | 36000 | 28800 | 80% | 14 | Slow and highly burecratic process that can take longer than this time limit. | 0.8
13 | P4H Product Development | Kazakhstan | Arystan | Propose a PPP model to cover rural health needs in RK | Developed PPP model | Acquire Local Executive Branch head support for a specific region (Karkaraly region, Central Kazakhstan). Analyze PPP terms in KZ. Develop a model with technical support form ADB and WB. Present to the Ministry of Healthcare for a feedback. | 2019-07-01 | 2020-06-30 | 4 | 6 | 44.44% | 0 | 14 | 11200 | 3982.2222 | 35.56% | 71 | TBD after thorough analysis on the region infrastructure and workforce capacity | 0.8
14 | P4H Expansion | Kazakhstan | Arystan | Increase visibility of the network in RK and region | Published article with in a regional media (for Kazakhstan and Kyrgyz Republic). | To organize a regional meeting for healthcare financing experts in Almaty, with the P4H network representatives. Provide wide media coverage. Conduct an round table with a high rank health economist to discuss healthcare financing situation in both countries and offer network's technical advice on this matter. | 2019-07-01 | 2020-06-30 | 4 | 6 | 44.44% | 4000 | 7 | 9600 | 3413.3333 | 35.56% | 72 | Countries have too much immidiate problems to solve and might not be interested at this point in a long-term solutions research | 0.8
15 | P4H Visibility | Thailand | Bart | PMAC 2020 in Thailand | P4H event on accelerating progress towards UHC during PMAC 2020 | Prepare a proposal to submit and obtain approval and organize the event | 2019-07-01 | 2019-06-30 | 5 | 6 | 55.56% | 0 | 3 | 2400 | 1333.3333 | 55.56% | 39 | It may need extended discussions | 1 | y
16 | P4H Knowledge Management | Cambodia | Bart | Informed decision making by the National Social Protection Council (NSPC) using valid and reliable data | Annual Reports on financial risk protection trends | Training of staff members of National Institute of Public Health (NIPH), National Institute of Statistics and Secretariat to the National Social Protection Council (SNSPC) in econometric analysis with World Bank & WHO | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 20000 | 18 | 34400 | 214044.4444 | 622.2% | 1 | Non-aligned, fragmented and unequal social health protection system | 7 | y
17 | P4H Visibility | SE Asia | Bart | Special issue Health Policy and Planning | Co-editing and co-funding of a special issue of Health Policy & Planning on health financing in SE Asia | Writing up peer reviewed papers, editing contributions and formulating editorial with Uiversity of New South Wales, WHO, World Bank, P4H & London School of Hygiene and Tropical Medicine | 2019-07-01 | 2019-11-01 | 6 | 7 | 77.78% | 7800 | 8 | 14200 | 8283.3333 | 58.33% | 35 | Late submission by co-authors | 0.75 | y
18 | P4H Knowledge Management | Cambodia | Bart | Informed decision making by the National Social Protection Council (NSPC) using valid and reliable data | Study tour | Study tour to Thailand with staff members of the NIPH, SNSPC to get familiar with Thailand's institutions in charge for M&U for UHC, means of information dissemination and use of informatin by policymakers | 2010-10-01 | 2019-10-01 | 6 | 5 | 55.56% | 14000 | 8 | 20400 | 11333.3333 | 0% | 62 |  | 1
19 | P4H Knowledge Management | Cambodia | Bart | Aligned donor funding to promote efficiencies by incorporating related activities into the next phase (2021-23) of the Global Fund for tuberculosis, AIDS and Malaria (GFTAM) funding for Cambodia | Report on faesibility to channel GFTAM money through government mechanism (with WB, USAID, DFAT, BMZ) | Assesment of fiduciary compatability of the GF and government financialmmanagement systems, identifying possible interventions for channeling GF money with due consideration of stakeholders' preferences | 2019-10-01 | 2019-12-20 | 6 | 6 | 66.67% | 0 | 40 | 32000 | 21333.3333 | 0% | 62 |  | 1
20 | P4H Expansion | Global | Bayar | Offered values, positioning and recognition | Information and document sharing to promote partnership collaboration within WHO technical units and teams | Attend meetings, post and promote team products | 2019-07-01 | 2020-06-30 | 3 | 7 | 38.89% | 10000 | 8 | 16400 | 5740 | 35% | 73 | Program specific constraints | 0.9 | n
21 | P4H Expansion | Global | Bayar | Social health protection training in ILO / Turin | ILO and P4H co-organized training event on social health protection | Prepare a proposal to submit and obtain approval and organize the event | 2019-07-01 | 2020-06-30 | 5 | 7 | 64.81% | 1000 | 14 | 12200 | 7907.4074 | 64.81% | 42 | It may need extended discussions | 1 | y
22 | P4H Expansion | Global | Bayar | PMAC 2020 in Thailand | P4H event on accelerating progress towards UHC during PMAC 2020 | Prepare a proposal to submit and obtain approval and organize the event | 2019-07-01 | 2020-02-28 | 5 | 9 | 83.33% | 1000 | 10 | 9000 | 7500 | 83.33% | 12 | It may need extended discussions | 1 | y
23 | P4H Product Development | Global | Bayar | Better understanding of a political economy in the context of P4H | A political economy tool and training materials | Draft, discuss and finalize the tool | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 30000 | 30 | 54000 | 38400 | 71.11% | 34 | Contract my not be approved | 0.8 | y
24 | P4H Product Development | Region and countries | Bayar | Partnership work on developing and implementing P4H products | L4UHC in Asia and NUD Cards for selected Asian countries | Participate in implementation and discussion of P4H products | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 30000 | 20 | 46000 | 36800 | 80% | 14 | Contract my not be approved | 0.8 | y
25 | P4H Country Collaboration | China | Bayar | Partnerships are expanded | An expert meeting on private sector participation in health financing for UHC | Invite experts, facilitate dialogues for organization | 2019-07-01 | 2019-10-30 | 4 | 6 | 44.44% | 5000 | 7 | 10600 | 4711.1111 | 44.44% | 66 | Government interest and priority need to be validated | 1 | y
26 | P4H Country Collaboration | Kazakhstan | Bayar | Partnerships are expanded | Fulltime P4H focal person | Work on P4H Focal Person ToRs and collaborative projects in Kazakhstan and Central Asia | 2019-07-01 | 2019-10-30 | 6 | 8 | 88.89% | 5000 | 10 | 13000 | 11555.5556 | 88.89% | 9 | Government interest and priority need to be validated | 1 | y
27 | P4H Country Collaboration | Russia | Bayar | Partnerships are expanded | Increased access to information in Russian | Translate P4H documents and develop a strategy to launch the P4H Web platform in Russian | 2019-07-01 | 2020-06-30 | 4 | 6 | 44.44% | 8000 | 15 | 20000 | 8888.8889 | 44.44% | 63 | Government interest and priority need to be validated | 1 | y
28 | P4H Country Collaboration | Republic of Korea | Bayar | Partnerships are expanded | Organization of joint events in Korea and region | Discuss, explore and organize a joint P4H event | 2019-07-01 | 2020-06-30 | 4 | 6 | 44.44% | 5000 | 7 | 10600 | 4711.1111 | 44.44% | 66 | Government interest and priority need to be validated | 1 | y
29 | P4H Country Collaboration | Niger | Bouchaib | L4UHC 2nd Francophone Africa session is a success | Niger team got support in the L4UHC modules and in the RRI. | Participation in M2 & M3 as P4H CFP; follow-up of the RRI in Niger | 2019-07-01 | 2020-06-30 | 6 | 6 | 66.67% | 5000 | 20 | 21000 | 11200 | 53.33% | 57 |  | 0.8
30 | P4H Geographical Networks | EAC | Christian | P4H is expanding its regional level activities to other EAC countries | Scope, entry points and potential demand from EAC countries are documented for next steps | Kenya with WHO, Burundi with WB, Uganda with ILO | 2020-02-01 | 2020-06-30 | 6 | 5 | 55.56% | 2000 | 10 | 10000 | 4444.4444 | 44.44% | 63 | Agreement to a joint activity | 0.8 | y
31 | P4H Management | Global | Claude | Activities specified in 2019-2020 are realised to the maximum extent | 70% of the planned activities are properly executed | P4H Team Functional Management | 2019-07-01 | 2020-06-30 | 6 | 7 | 77.78% | 20000 | 18 | 34400 | 26755.5556 | 77.78% | 26 | Agreement to a joint activity | 1 | y
32 | P4H Management | Global | Claude | Formation of a global expert team on health financing facilitation across members | 2 face to face meetings are held | Identification of the opportunity, organisation, draft agenda, etc. of the face to face meetings | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 5 | 4000 | 2000 | 50% | 60 | The plateform project fails | 0.5 | n
33 | P4H Governance | Global | Claude | The P4H SG is providing strategic and operational guidance | The SG meeting in 2019 is held & draft agenda for the meeting 2020 is adopted | SG related work (contracts, preparation of meetings…) | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 1500 | 12 | 11100 | 11100 | 100% | 2 | There is no P4H continuum in country, thus no P4H added value | 1 | y
34 | P4H Expansion | Global | Claude | Using the P4H Network as the main mechanism of the SDG 3 GAP Sustainable Financing Accelerator | Formal agreement among partners is adopted | Support Gwen when needed | 2019-07-01 | 2019-11-01 | 6 | 9 | 100% | 30000 | 14 | 41200 | 41200 | 100% | 2 |  | 1 | y
35 | P4H Governance | Global | Claude | P4H visibility in global health | Comprehensive Communication Strategy | Participation during key milestones and oversight | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 0 | 3 | 2400 | 2133.3333 | 88.89% | 11 | Lost opportunities for optimising P4H activities and results | 1 | n
36 | P4H Governance | Global | Claude | P4H visibility in global health | Side Event during PMAC Conference in Bangkok in February 2020 | Preparation and holding the Side Event at PMAC 2020 | 2019-07-01 | 2020-06-30 | 6 | 7 | 77.78% | 100000 | 20 | 116000 | 90222.2222 | 77.78% | 26 |  | 1 | y
37 | P4H Governance | Global | Claude | P4H visibility in global health | P4H Health Financing for UHC Side Event in relation with the UNI HLM in New York September 2019 | Preparation and holding the P4H Health Financing for UHC Side Event in relation with the UN HLM | 2019-07-01 | 2020-10-30 | 6 | 7 | 77.78% | 0 | 10 | 8000 | 6222.2222 | 77.78% | 26 | P4H extension is not consistent with its members' regional organization and provides no alternative | 1 | y
38 | P4H L4UHC Product | Global | Claude | Continuous development of the L4UHC product and collaboration with other capacity development programs | P4H proposal for combined capacity development program | Identification of collaboration oportunities | 2019-07-01 | 2020-10-30 | 6 | 7 | 77.78% | 0 | 6 | 4800 | 2800 | 58.33% | 51 |  | 0.75 | n
39 | P4H L4UHC Product | Africa | Claude | Inclusion of the adaptive dimension in health financing processes | Three participating countries had developed impactful collective action initiative | Participation in conducting the three moduls | 2019-07-01 | 2020-06-30 | 6 | 5 | 55.56% | 20000 | 25 | 40000 | 11111.1111 | 27.78% | 75 | P4H cannot develop in Africa | 0.5 | y
40 | P4H L4UHC Product | Asia | Claude | Inclusion of the adaptive dimension in health financing processes | Four participating countries have developed impactful collective action initiative | Participation in conducting the three moduls | 2019-07-01 | 2020-03-31 | 5 | 5 | 46.3% | 10000 | 11 | 18800 | 8703.7037 | 46.3% | 62 |  | 1 | y
41 | P4H L4UHC Product | P4H partner countries | Claude | Inclusion of the adaptive dimension in health financing processes | One in-country session | Rolling out of L4UHC programe at country level | 2019-07-01 | 2020-06-30 | 6 | 7 | 77.78% | 10000 | 10 | 18000 | 11200 | 62.22% | 44 | Lost opportunities for optimising P4H activities and results | 0.8 | n
42 | P4H Management | P4H partner countries | Claude | Functional P4H Network at country level | Partner collaboration has improved in three countries | Joint country missions | 2019-07-01 | 2019-11-01 | 6 | 9 | 100% | 5000 | 8 | 11400 | 9120 | 80% | 14 |  | 0.8 | n
43 | P4H Product Development | Mozambique | Cristina | Capacity building in costing public health services (GIZ-SDC-WHO) | Roadmap on how to constitute a routine costing system for the public health sector | One week training on Costing of Health Services, targeting NHS Hospital Administrators nation-wide + MoH Planning . | 2019-07-01 | 2020-06-30 | 6 | 6 | 66.67% | 10000 | 15 | 22000 | 14666.6667 | 66.67% | 38 |  | 1 | y
44 | P4H Expansion | Global | Gwen | Using the P4H Network as the main mechanism of the SDG 3 GAP Sustainable Financing Accelerator | Formal agreement among partners is adopted | Lead all related activites: contracts, meetings etc. | 2019-07-01 | 2019-11-01 | 6 | 9 | 100% | 30000 | 50 | 70000 | 52500 | 75% | 31 |  | 0.75 | y
45 | P4H Country Collaboration | China | Gwen | Partnerships are expanded | An expert meeting on private sector participation in health financing for UHC | Invite experts, facilitate dialogues for organization | 2019-07-01 | 2019-10-30 | 5 | 8 | 74.07% | 0 | 10 | 8000 | 5925.9259 | 74.07% | 33 | Government interest and priority need to be validated | 1 | y
46 | P4H Expansion | Global | Gwen | Health related networks collaboration | Functional Networks Administrators Group | Managing the Networks Administrators Group | 2019-07-01 | 2020-06-30 | 3 | 6 | 33.33% | 0 | 5 | 4000 | 1000 | 25% | 76 |  | 0.75 | n
47 | P4H Expansion | Global | Gwen | TEG providing support to the SG | TEG Meeting 2020 is held | TEG related work | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 0 | 5 | 4000 | 3555.5556 | 88.89% | 9 |  | 1 | y
48 | P4H Product Development | Global | Gwen | Inclusion of the private sector in the global conversation on health financing | Report of the expert consultation in Shanghai on Private Sector Participation in Health Financing product | Preparation, organisation | 2019-07-01 | 2020-06-30 | 3 | 4 | 22.22% | 10000 | 15 | 22000 | 4400 | 20% | 77 |  | 0.9 | y
49 | P4H Expansion | Global | Gwen | Contribution to / positioning in UHC2030 agenda | Expand scope of p4h.world | Promote & advice on p4h.world's white labelling to UHC2030 networks | 2019-07-01 | 2020-06-30 | 5 | 7 | 64.81% | 1000 | 10 | 9000 | 4375 | 48.61% | 61 | Objection by government | 0.75 | y
50 | P4H Governance | Global | Helga | P4H visibility in global health | Comprehensive Communication Strategy | Project lead & product management | 2019-07-01 | 2020-04-30 | 6 | 8 | 88.89% | 8000 | 12 | 17600 | 14080 | 80% | 14 | Non-aligned, fragmented and unequal social health protection system | 0.9 | y
51 | P4H Expansion | Global | Helga | Contribution to / positioning in UHC2030 agenda | Expand scope of p4h.world | Promote & advice on P4H products to UHC2030 networks (e.g. white labeling, L4UHC, etc.); dig. comm. Strategy | 2019-07-01 | 2020-06-30 | 5 | 7 | 64.81% | 5000 | 5 | 9000 | 5250 | 58.33% | 51 |  | 0.9 | n
52 | P4H Management | Global | Helga | Design work processes and project management standards across P4H activities | Updating p4h.world and shaping activities of the CT | Implement use of P4H CT work programm and p4h.world maintanance management | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 10 | 8000 | 8000 | 100% | 2 |  | 1 | y
53 | P4H Visibility | Global | Helga | Increase P4H visual identity & visibility | Consistent quality of p4h.world | Quality control of the visual identity & p4h.world | 2019-07-01 | 2020-06-30 | 6 | 8 | 88.89% | 0 | 10 | 8000 | 6400 | 80% | 24 |  | 0.9 | n
54 | P4H Management | Global | Helga | Digitazition & Innovation | p4h.world product is fully developed | Designing the implementation of p4h.world | 2019-07-01 | 2020-06-30 | 5 | 9 | 83.33% | 100000 | 21 | 116800 | 97333.3333 | 83.33% | 12 | It may need extended discussions | 1 | n
55 | P4H Governance | Global | Helga | Support SG in strategic decision making | SG receives needed strategic information | Offer strategic information to the SG (e.g. newsletter, calender, work plan etc.) | 2019-07-01 | 2020-06-30 | 7 | 5 | 64.81% | 0 | 6 | 4800 | 2800 | 58.33% | 51 | P4H cannot develop in Africa | 0.9 | y
56 | P4H Knowledge Management | P4H partner countries | Helga | The platform reflects what is going on at country level and meets its purpose | Seven good country examples in 2020 | Tentative adequate informing of country pages on the P4H platform | 2019-07-01 | 2020-06-30 | 5 | 7 | 64.81% | 0 | 22 | 17600 | 11407.4074 | 64.81% | 42 |  | 1 | y
57 | P4H Visibility | Global | Helga | P4H's visibility at high level meetings on UHC in 2019/2020 | P4H National UHC Dynamics Card product for twenty four partner countries | Visual representation of the UHC history of P4H member & partner countries | 2019-07-01 | 2020-05-31 | 3 | 8 | 44.44% | 60000 | 9 | 67200 | 26880 | 40% | 69 |  | 0.9 | n
58 | P4H Product Development | Myanmar | Htet | To support advocacy and dissemination for UHC and Health Financing concepts to stakeholders | A glossary book on Health Financing and UHC in Myanmar | Developing a Glossary Book for Health Financing in Myanmar Language | 2019-12-15 | 2020-06-30 | 6 | 6 | 66.67% | 3700 | 10 | 11700 | 7800 | 66.67% | 38 | It may take some time to find the right person and get the author contracted. | 1 | y
59 | P4H Knowledge Management | Myanmar | Htet | To support the development of a UHC law in Myanmar by having the draft bill translated into English and reviewed by (a) legal expert(s) | The draft UHC bill in English reviewed | Translation of the draft UHC bill and having it reviewed by (a) legal expert(s) | 2019-12-15 | 2020-06-30 | 6 | 8 | 88.89% | 10000 | 8 | 16400 | 10933.3333 | 66.67% | 38 | It depends on the political climate of the country. | 0.75 | y
60 | P4H Expansion | Global | Josselin | Increase P4H country base into UHC 2030 | Deepen the cooperation with UHC2030 | Contribute to global discussion based on Cameroonian experience | 2019-07-01 | 2020-06-30 | 3 | 4 | 22.22% | 0 | 3 | 2400 | 266.6667 | 11.11% | 79 | Depends on the dynamic of the country and real commitment of the government to UHC | 0.5 | n
61 | P4H Country Collaboration | Cameroon | Josselin | Create links between P4H and HDC networks at country level | Explored cooperation between P4H and HDC in country | Develop one common activity with HDC in Cameroon | 2019-07-01 | 2020-06-30 | 3 | 4 | 22.22% | 0 | 3 | 2400 | 373.3333 | 15.56% | 78 |  | 0.7 | n
62 | P4H Country Collaboration | Cameroon | Josselin | P4H is expanding at country and regional level in CA countries, including a physical presence | Cameroon CFP is formalised | Promote P4H products in Cameroon | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 11 | 8800 | 880 | 10% | 80 |  | 0.1 | n
63 | P4H L4UHC Product | Central Africa | Josselin | L4UHC is implement for Cameroon | Cameroon participates in L4UHC program | Support / facilitate the global process | 2019-07-01 | 2020-03-31 | 6 | 8 | 88.89% | 0 | 7 | 5600 | 3982.2222 | 71.11% | 34 |  | 0.8 | n
64 | P4H Geographical Networks | Asia | Marielle | Joint awareness campaign on Social Health Protection in south-east asia (focus: VN, Laos, Myanmar) | Concept note developed, buy-in from at least one P4H member (other than ILO), medias developed, campaign started | Promote joint efforts on advocacy campaign for SHP among DPs; develop concept note; develop product; support implementation | 2019-07-01 | 2019-12-31 | 6 | 6 | 66.67% | 0 | 30 | 24000 | 9600 | 40% | 69 | No interests from other P4H members to implement a joint campaign | 0.6 | y
65 | P4H Country Collaboration | Viet Nam | Marielle | Matrix developped, filled by partners and kept up to date | Development of DPs joint matrix on capacity building on health insurance and health financing with ILO/P4H, WB, ABT, WHO, JICA, | Sell the idea to DPs, get commitment to fill and update, circulate, raise warning if duplication | 2019-07-01 | 2019-12-31 | 6 | 7 | 77.78% | 0 | 3 | 2400 | 1866.6667 | 77.78% | 26 | Sharing of information is only going in one direction - incomplete information provided | 1 | n
66 | P4H Country Collaboration | Viet Nam | Marielle | Provide aligned views and recommandations to MoH on selected policy reforms within the framewok of the HI law revision | Joint technical note on provision of additional HI benefit package (ILO with WB & WHO) | Countries experiences reviews, workshop, joint technical note developped and disseminated (with WHO & WB) | 2019-07-01 | 2020-03-01 | 6 | 8 | 88.89% | 0 | 20 | 16000 | 12800 | 80% | 24 | Heads on institutions do not endorse joint technical note | 0.9 | y
67 | P4H L4UHC Product | Viet Nam | Marielle | Effective participation and sustained commitment of Viet Nam delegation to the program | Viet Nam participates in L4UHC program | Identify participants, facilitate invitations process, assist preparation in country, participate to at least one module | 2019-07-01 | 2020-03-01 | 6 | 6 | 66.67% | 0 | 10 | 8000 | 4800 | 60% | 47 | Absence of interests from Viet Nam; administrative burden to obtain authorization and visas approvals | 0.9 | y
68 | P4H Geographical Networks | Country | Nina | Functional P4H Network at country level | Partner collaboration has been revived in India | Joint country dialogue | 2019-10-01 | 2020-12-31 | 6 | 9 | 100% | 1000 | 8 | 7400 | 5920 | 80% | 14 | No interests from other P4H members to meet under the P4H umbrella | 0.8 | n
69 | Preparation of SG | Global | Olivier | Preparation of SG | a prepared and internally cleared document for SG discussion and a well structured SG meeting | facilitate SG preparation through prior TEG meeting |  |  | 6 | 9 | 100% |  | 10 | 8000 | 6400 | 80% | 14 |  | 0.8
70 | Preparation of TEG |  | Olivier | Revitalise TEG as per original mandate specified in the TORs of P4H | Updated workplan with inputs from TEG members, well prepared draft agenda SG | Prepare agenda & minute including for a meeting in 2nd week of May and contact organisatins directly, prepare for the logistics of the event | Now | 2020-05-01 | 6 | 9 | 100% |  | 20 | 16000 | 12800 | 80% | 14 |  | 0.8
71 | P4H Knowledge Management | Global | Olivier | Contribution to documenting and showcasing P4H work at country level | Documentation of CT work on platform | Follow up of activities at country level through P4H Focal point and of its documentation | Now | 2020-09-01 | 5 | 8 | 74.07% |  | 14 | 11200 | 6637.037 | 59.26% | 49 |  | 0.8
72 | P4H capacity building | Global | Olivier | increase knowledge of P4H focal points on PFM | Training needs assessment | Develop a short curriculum for PFM et al with WB and 4 G | After TEG Meeting | 2020-09-01 | 5 | 8 | 74.07% |  | 14 | 11200 | 6637.037 | 59.26% | 49 |  | 0.8
73 | P4H Product Development | Global | Olivier | Set up a comprehensive CGAP and CAP DEV plan in a P4H country | Decision on which country to pilot | conduct joint cap gap analysis with subsequent cap dev | Relevance to be assessed during TEG | 2021-12-01 | 4 | 7 | 51.85% | 500000 | 5 | 504000 | 209066.6667 | 41.48% | 68 |  | 0.8
74 | P4H Strategy Reflection | Global | Olivier | coordinate inputs for SG and TEG | Evaluation document | coordination of dates for feedback on this with SG and TEG | Now | April/May 2020 | 6 | 9 | 100% |  | 10 | 8000 | 6400 | 80% | 14 |  | 0.8
75 | P4H Strategy Reflection | Global | Olivier | Strategic orientation of expansion according to criteria - reflection paper | Reflection paper on Strategic deployment of P4h Focal points | Write up of some guiding principles | Now | 2020-06-01 | 6 | 7 | 77.78% |  | 2 | 1600 | 995.5556 | 62.22% | 44 |  | 0.8
76 | P4H Expansion | Global | Olivier | Alignment of P4H with GAP countries | New countries have requested support for P4H Focal Points | Leading discussions with 4G and partner countries | Now | 2020-06-01 | 6 | 9 | 100% |  | 5 | 4000 | 3200 | 80% | 14 |  | 0.8
77 | P4H Expansion | Central Africa | Saibou | P4H is expanding at country and regional level in CA countries, including a physical presence | One country focal point is in place in CA in 2020 | Tentative expansion of P4H resource persons in Chad and other Central African Countries | 2019-07-01 | 2020-06-30 | 6 | 6 | 66.67% | 0 | 21 | 16800 | 11200 | 66.67% | 38 | Missed opportunity | 1 | y
78 | P4H Country Collaboration | Chad | Saibou | Elaborate a set-up plan of the NHIS | Implementation plan for the NHIS is adopted by the Government | Participation in the overall process to develop the plan with SDC, WHO & AFD. | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 15 | 12000 | 9000 | 75% | 31 |  | 0.75 | n
79 | P4H Knowledge Management | Chad | Saibou | Follow-up L4UHC national team | The L4UHC team members apply the knowledge gained and contribute to the NHIS start-up process | Assist the team with the preparation of his work plan and organize two follow-up meetings | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 10 | 8000 | 8000 | 100% | 2 |  | 1 | y
80 | P4H Product Development | Chad | Saibou | Develop tools and materials for actuarial calculations | Tools for costing the NHIS benefit packages are available and implemented | Build an excel tool, provide training to concerned NP and support for implementation with other P4 partners | 2019-07-01 | 2020-06-30 | 5 | 6 | 55.56% | 0 | 19 | 15200 | 8444.4444 | 55.56% | 55 |  | 1 | y
81 | P4H Country Collaboration | Malawi | Siri | Improved purchasing for quality, efficiency and ensuring accessibility of essential health services | HMIS assessment for payment reform at Central Hosptials in Malawi | Improving HMIS toward more efficient purchasing at tertiary hospitals in Malawi with other P4H members | 14/10/2019 | 2019-12-12 | 4 | 5 | 37.04% | 0 | 15 | 12000 | 3555.5556 | 29.63% | 74 |  | 0.8 | n
82 | P4H Country Collaboration | Madagscar | Virgile | Building institutionnal capacities for health financial protection | Establishing a Trust Fund to affiliate vulnerable people (92%) | Drafting Bill with Government, Ministries and Technical and Financial Partners (TFPs). | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 20 | 16000 | 16000 | 100% | 2 |  | 1 | n
83 | P4H Country Collaboration | Madagscar | Virgile | Ensuring smooth functioning and relevance of action of the National Financial Protection Health Agency (CNSS) | New decree is adopted and executive measures are taken. | Advocacy with national stakeholders and TFPs to ensure effectivity and efficiency of the CNSS. | 2019-07-01 | 2020-06-30 | 6 | 9 | 100% | 0 | 10 | 8000 | 4800 | 60% | 47 |  | 0.6 | n
Note on M65: Marielle Phe Goursat: TA only at the moment
Note on U65: Marielle Phe Goursat: within the time frame of the ILO-Lux projct supporting the costs of actvities
Note on M66: Marielle Phe Goursat: Technical assistance costs only
Note on M67: Marielle Phe Goursat: The costs of the drafting of the joint technical note are only TA. However the costs of the countries experience review and workshop are about USD 15,000 (these were implemented by ILO onlym hence not P4H product) but are the foundation on which the joint technical note was dveloped
Note on M68: Marielle Phe Goursat: The L4UHC team knows the costs of travels to the three countries. I don't have this information. The faciltiation part of it has only TA costs

## Resources Determination
COORDINATION DESK | [10 empty] | workdays p.a. |  | 210
Colonne1 | Person | % of full-time | days for routine work | days p.a. available for projects | Days spent on specific activities | Regular physical meetings | Balance | Colonne2 | Colonne3 | Colonne4 | time for routine for FP |  | 20%
| Claude | 1 | 105 | 168 | 142 | 10 | 16 |  | coeff of FP common tasks |  | time for routine for CD |  | 50%
Half a year | Gwen | 50% | 52.5 | 84 | 95 | 0 | -11 |  | platform | 15% | Cost of staff day |  | 800
| Bayar | 1 | 105 | 168 | 121 | 10 | 37 |  | documentation | 25%
| Jean-Olivier | 91.67% | 96.25 | 154 | 80 | 0 | 74 |  | regulr ToR | 60% |  | Nb
| CD5 | 0 | 0 | 0 |  |  | 0 |  | Total | 100% | CFP & RFP | 15
| Helga | 70% | 73.5 | 117.6 | 95 | 10 | 12.6 |  |  |  | CD | 4
| Marie-Pierre | 40% | 42 | 67.2 | [6 empty] | Helga | 1
[11 empty] | Marie-Pierre | 1
Colonne1 | CF Person | % of full-time | days for routine work | days p.a. available for projects | Days spent on specific activities | Regular physical meetings | Days available for common task (FP) | Days available for the platform | Days available for the documentation | Days available for regular ToR | Total nb staff | 21
1 | Abdoulaye | 75% | 31.5 | 126 | 80 | 10 | 36 | 5.4 | 9 | 21.6
2 | Alexis | 0.5 | 21 | 84 | 47 | 10 | 27 | 4.05 | 6.75 | 16.2 | 2019-2020 | #
3 | Arystan | 75% | 31.5 | 126 | 66 | 10 | 50 | 7.5 | 12.5 | 30 | nb of staff at 100% | 2 | 200%
4 | Bart | 75% | 31.5 | 126 | 77 | 10 | 39 | 5.85 | 9.75 | 23.4 | nb of FP at 50% | 8 | 400%
5 | Bouchaib | 41.67% | 17.5 | 70 | 20 | 5 | 45 | 6.75 | 11.25 | 27 | nb of FP at 20% | 2 | 40%
6 | Christian | 0.5 | 21 | 84 | 10 | 10 | 64 | 9.6 | 16 | 38.4 | nb of FP @75% | 4 | 75%
7 | Cristina | 0.5 | 21 | 84 | 15 | 10 | 59 | 8.85 | 14.75 | 35.4 | Gwen |  | 50%
8 | Htet | 0.5 | 21 | 84 | 18 | 10 | 56 | 8.4 | 14 | 33.6 | Helga |  | 70%
9 | Josselin | 0.5 | 21 | 84 | 24 | 5 | 55 | 8.25 | 13.75 | 33 | Jean-Olivier |  | 91.67%
10 | Ludovic | 0.2 | 8.4 | 33.6 | 0 | 0 | 33.6 | 5.04 | 8.4 | 20.16 | Bouchaib |  | 41.67%
11 | Marielle | 0.5 | 21 | 84 | 63 | 5 | 16 | 2.4 | 4 | 9.6 | Marie-Pierre |  | 40%
12 | Nina | 0.5 | 21 | 84 | 8 | 0 | 76 | 11.4 | 19 | 45.6 | Total equi nb staff |  | 10.0833
13 | Saibou | 75% | 31.5 | 126 | 65 | 10 | 51 | 7.65 | 12.75 | 30.6
14 | Siri | 0.2 | 8.4 | 33.6 | 15 | 0 | 18.6 | 2.79 | 4.65 | 11.16
15 | Virgile | 0.5 | 21 | 84 | 30 | 10 | 44 | 6.6 | 11 | 26.4
| Total time allocation |  | 2072 | 2072 | 1071 | 135 | 798.8 | 100.53 | 167.55 | 402.12

## guidelines
| FP STANDARD TIME DISPATCHING | Total days available | Routine work 20% | Physical meetings | Days available for the platform | Days available for the documentation | Days available for regular ToR | Days available for specific tasks
| FP @20% | 42 | 8 | 5 | 10 | 7 | 12 | 0
| FP @50% | 105 | 21 | 10 | 10 | 14 | 50
For next workplan | FP @75% | 157.5 | 31.5 | 10 | 15 | 21 | 80
| CD STANDARD TIME DISPATCHING | Total days available | Routine work 40% | Physical meetings | Days available for the platform | Days available for activities including documentation
| CD (100%) | 210 | 84 | 10 | 12 | 104