Ministry of Labor and Social Affairs

Contribution by other Yemeni organization

اسهامات (مشاركات ) من مؤسسات  يمنيه اخرى

By When ?

متى

Priority

اولويه

Role of your organization

دور مؤسستك

Your contributions

(Activities)

نوع مشاركاتكم (انشطة)

Last quarter of

2015

Providing financial support to the project

Develop structure to integrate it to the disabled fund within the health insurance fund.

Suggesting opening branches for this fund in all governorates

Rehabilitation and physical therapy supported by the Fund

Supporting development of skills and  education

Searching for fun to open a hospital and pharmacy

Allocation and mobilization of resources

Provide health services to the maximum number of poor and disabled people.

Attention to rehabilitation and health of disabled people

Develop regulations that are approved by the responsible entities and following them.

Search for resources to accomplish these tasks

Inventory and classification expenditure of services provided and work include as much as possible poor and disabled people

Build a Central hospital and a pharmacy for the disabled

Engaged a study to learn whether it’s possible to include poor people and orphans

Classification of health services currently provided to disabled people.

1- develop organizational regulation for the Care and development of disabled people.

2- National strategy Resources for people with disabilities

In case the sponsorship is found

Priority

Ministry of Labor and social Affairs

Care of people with disabilities

Goals

Agreement with MoPHP to provide with Health services, financed by the fund accordingly to the services provided

Classification of currently provided services. Development of these services in cooperation with Health and Health insurance fund

Engaged in study in cooperation with MoPHP and Health insurance Fund to learn the possibility to include poor and orphans as beneficiaries

DB that includes all people involved, in particular Disabled people and orphans with in the ministry.

1- Development of organizational regulations for the care and development of disabled people fund

2- Development of national strategy for disabled people

Goal 2

Working on building the hospital that includes all necessary equipment for the disabled people with pharmacy.

Work on including workers in privet sector for health insurance as it is mandatory

Ministry of Public Health & Population

Role of your organization

دور مؤسستك

Priority

Your contributions

(Activities)

نوع مساهماتك  (انشطة)

Contribution by other Yemeni organization

مساهمات باقي المؤسسات اليمنية

By When ?

متى

Technical UCH committee  اللجنة الفنية

High level UCH committee اللجنة الوزارية العليا

Development HFSاستراتيجية التمويل الصحي

Shift ODA from capacity appositional تحويل النفقات الرأسمالية للإجرائية التشغيليه

capacity assessment & capacity Develop strategyدراسة تقييم القدرات

key person coordinate meeting

leading coordinate meeting

-leading

-coordinate

-leading

-coordinate

advocacy

Coordinate -TOR develop meeting –policy, develop, plans

T.coordinate       TOR development expert        reporting dissemination

- Expert           info                    documents

Q1,2,3

Expert            -providing data

Justification       -prioritization

Q3,4

Q2

Q1,2

Q2,3

representation of health insurance in the Supreme Committee and participation in preparation of the terms of references

Participation and support of the ministerial committee

Representing health insurance in in technical committee and participation in health insurance related activities

Participation of health insurance in strategic development of health sector

Participation in strategy development

Participation in supervision

Resource mobilization

Participation of health insurance in the evaluation and capacity building

Transfer from capitalist to commercial approach

Participation in ministerial and technical committees

Capacity building and trainings

| Priority | specific activities | responsibility | Time frame |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| high level UCH committee technical UCH committee development HFS 2 capacity assessment & capacity develop strategy shift ODA from capacity apparitional | evaluation 1key persons HPTSU 2-TOR developing 3-kickoff meeting 1-key person 2-TOR 3-kick-off 4-meeting committee in depth situation analysis identify ????? tools conduct capacity assessment clear priority for ODA (local resources) | 1-MOPHP 2-MOPHP ,MOF,MOPIC .labor academic side 3-MOH,Gi2 WHO,Eu all stakeholder MoH + GIZ MoH + GIZ MOH(HPTSU) MOH+GIZ,WHO EU MOH-MOF Mopic EU policy | Q1 | Q2 | Q3 | Q4 |
|  |  |  | implementation collecting resource mobilization √ | √ √ √ | √ √ √ √ | preparation Ministry of Public Health & Population Priority اولويه |

Ministry of Finance

Ministry of  Planning

Contribution by other Yemeni organization

اسهامات باقي المؤسسات اليمنية

By When ?

متى

Priority

Role of your organization

دور مؤسستك

Your contributions

(Activities)

نوع مساهمتك (انشطة)

Creation of the ministerial committee

New tax reforms

Proposing new editions in communal health insurance

Support in the cabinet and participation in the committee

Issues and associate

Participation in identifying the constraints and priorities

3 months

3 months from now

Immediately, 1 month max

Participation in preparing the regulation

Cabinet approval

Support the idea to the institution leaders

Idea supporting

Cabinet and parlament

Cabinet and parlament

Capacity building and trainings

Transfer the investment programme to the 2nd door of health

The Ministry of Labor will support the decision-making of the crisis for the establishment of a ministerial committee to impose taxes and to amend the Insurance Act

The Ministry of Health is to be the leader of the Technical Committee

Re-programming the current tax and resources together in proportion to the overall health coverage

Cooperative committee that will discuss the regulation considering current situation

Participation in tax revision

Priority

اولويه

Ministry of Finance

Ministry of  Planning

توصيه وزاه الصحة بتقديم تعديل قانون التامين الصحي الاجتماعي  بأسرع وقت ممكن حتى يتمكن القيام بمهامه التي انشاء من اجله

Make recommendation to MoPHP to make corrections / adjustments to the health insurance as soon as possible, to enable it to conduct its tasks.

التوصية الى وزير الصحة العام للقيام بتقديم مشروع فرض ضرائب جديده اضافيه بالتنسيق مع وزاره المالية  تخصص للتغطيه الصحية الشاملة

Make recommendation to MoPHP minister to impose a new additional taxes programe along with ministry of Finance, targeting the health coverage.

Reconsideration of health budget on bases to allocate expenses for infrastructure from Donors that will enable Ministry of finance to make the transformation from capitalism to commercial approach. Whereas the ministry of planning develops a plan to contact the donors and allocate funding from those donors

Make a recommendation to the Minister of Health to present a proposal to the Prime Minister to form a ministerial and technical committee and determine their functions and tasks

على وزاره الصحة تقديم مشروع التامين الصحي الالزامي (القطاع الخاص) بالتنسيق مع وزاره الشئون الاجتماعية والعمل

MoPHP responsible to propose a mandatory health insurance programme (privet sector) along with ministry of Labor and social affairs

2- Support the technical committee

اعداد وزاره الصحة الاستراتيجية الوطنية لتغطيه الصحية الشاملة وعرضها على مجلس الوزراء لإقرارها وعلى ان يتم هذا العمل خلال 13 شهر كحد اقصى

Preparation of national strategic plan for the health coverage and presenting it to the cabinet for approval. This must be done in maximum of 13 months

Priority

اولويه

Social Health Insurance Authority

Contribution by other Yemeni organization

اسهامات باقي المؤسسات اليمنية

By When ?

متى

Priority

Role of your organization

دور مؤسستك

Your contributions

(Activities)

نوع مساهمتك (انشطة)

During 2015 if finances are available

Presenting the plan to the donors

Defining time duration

Media and social affairs

Executive state authorities – legislative- judiciary – donors – privet sector – civil society organizations

Easing the access to labor low for technicians in order to complete the database.

Ministry of labor will assist to complete the strategic plan for health insurance

Fasten development and approval of the strategic plan for health insurance

Agreement of capacity development and trainings

Cooperation in capacity building and training

Notarization of the strategic plan and financial and media support

Development of strategic plan for health insurance and accessing full coverage.

Providing health package to government employees under the labor low

Complete construction of infrastructure? Institutional building and capacity building

Completing the preparation phase for database

Resource mobilization

s

Social Health Insurance Authority

Priority

اولويه

Activity

In case the sponsorship is found

Plan for health insurance 2015

3- capacity building

6- completion of plan to pay the retirees

5- collection of data for the database

2- completion of infrastructure and institutional organization

4- completion of database configuration

- Completing strategic plan including the therapeutic and propaganda aspects

7- actual preparation of the low that satisfies the next steps

Academia

Contribution by other Yemeni organization

اسهامات باقي المؤسسات اليمنية

Priority

Role of your organization

دور مؤسستك

Your contributions

(Activities)

نوع مساهمتك (انشطة)

During 2015

Social fund for development and Ministry of finance and MoPHP

Building capacity for staff for academic studies through list of trainers in insurance

Search for sponsorship for long term researches

Collecting and providing resources and mobilizing these resources from the  donors

Health management

Actual studies and health insurance

Health finances

A proposal to add everything in the framework of training and development

Involvement the academy as a neutral side

Set up training units in the ministry and in the governorates

Linking every training with the academy

Engaging and supervising  training

Educational training plan

Hall availability

Materials and training curriculum

Training staff

By When ?

متى

Priority

اولويه

Academia

ان الله يحب اذا عمل احدكم عملا فليتقنه (حديث شريف)

Shorts courses

Training courses

Methods of statistical analysis in actuarial studies and health insurance

Health financing

Health management

Biostatistics and research methods

Vocabulary and content

Health management concepts

Hospital management

TQM

Health Financial Management

PHC

Foundations and concepts of Health Economics

Measuring efficiency in health systems

Measure equity in the health system

Comprehensive health coverage and financing of health and National Accounts

Health sector reform

Target groups

Working groups of health administrators and technicians that are in relationship

Members of local councils and civil society organizations that are in relationship

Partners in Health Development

Funders

Methods of scientific research and design of Health Studies

Forecasts and aid strategic planning

Descriptive methods of statistical analysis (Table \ graph \ statistician)

Inferential statistics and hypothesis testing

Statistical methods in actuarial studies

The concepts of private insurance and social importance of health

Foundations and concepts of Actuarial Studies