## Workplan
What | Who | A | M | J | J | A | S | O | N | D
PREPARATORY WORK
Health Financing draft outline | Who: ThinkWell
Health Financing development workplan | Who: ThinkWell
Meeting with key stakeholders (WB, WHO, MITRAB, MIMAS, ILO, HPG focal point, UNICEF …) | Who: ThinkWell | Workshop
Presentation of health financing outline to partners, validation of objectives, principles and workplan | Who: DPC / ThinkWell; A: GTF 1 | Deliverable
RATIONALE
Review and synthesis of existing papers | Who: ThinkWell
Develop Investment case for health | Who: check status with world bank / DFID
Rationale: Draft chapter | Who: ThinkWell
SUSTAINABLE INCREASES IN RESOURCES FOR HEALTH
Create Minimum Benefit Package which can be financed with existing resources | Who: Sub Group 1: DNPS, DPC, WHO, INSS
Review assumptions of PESS costing | bar: A
Preparation of Benefit Package Scenarii (using OneHealth tool) | Who: check status with WHO
Working session with sub group on benefit package | J: SG 1
Agreed benefit package based on available resources | bar: J
Validation by GTF | J: GTF 4
Increase revenues for health | Who: GTF
Engagement with MEF | Who: DPC / ThinkWell
Presentation of innovative financing options and feasability methodology | Who: ThinkWell; M: GTF 2
Development of TORs for feasability studies | Who: DPC / ThinkWell
Feasability of earmarked taxes (interview with key stakeholders, financial projection) | Who: TBD
Feasibility of Public Private Partnership | Who: TBD
Assessment of population capacity to contribute | Who: TBD
Increase budget execution | Who: Sub Group 2: DAF, MEF, DPC, GTAF
Development of TORs for bottleneck study | Who: DPC / ThinkWell / Sub Group 2
Assessment on key bottlenecks to effective budget execution | Who: TBD
Working session with sub group on budget execution | Who: Sub Group 2: DAF, MEF, DPC, GTAF; A: SG 2
Presentation at technical council / ministry of coordination | bar: A
Validation by GTF | Who: DPC / ThinkWell / Sub Group 2; A: GTF 5
Increasing sustainable resources: Draft chapter | Who: ThinkWell
INCREASE EFFICIENCY OF RESOURCE ALLOCATION
Institutionalize and harmonized ressource tracking | Who: Sub Group 3: M&E group, DPC
Presentation of international practices to GTF | Who: TBD; M: GTF 2
TOR for assessment study | Who: TBD
Assessment of current situation and recommendations | Who: TBD
Sub Group working session | Who: TBD; S: SG 3
Presentation to GTF | Who: TBD; S: GTF 6
Rationalization of financing across all financing agents
Mapping of current input financing streams | Who: ThinkWell
Recommendations for improved financing by agents | Who: TBD
Validation with GTF | Who: TBD; O: GTF 7
Efficiency of ressource allocation: Draft chapter | Who: P4H coordinator
IMPLEMENT STRATEGIC PURCHASING
definition of purchasing mechanisms
Presentation of different international models | Who: ThinkWell; M: GTF 3
International study tour (Thailand) | Who: DPC / ThinkWell (conditional on funding)
Interaction with key stakeholders (Ministers, MIMAS, MITRAB, INS, donors) | Who: ThinkWell
SWOT analysis of different scenarios | Who: TBD
WG group recommendation | Who: DPC / ThinkWell
Political endorsement | bar: S
regulation of PBF mechanisms
Consultation with key stakeholders | Who: TBD
Draft regulation | Who: TBD
Strategic Purchasing: Draft chapter | Who: P4H coordinator
STRATEGY FINALISATION
First draft of the strategy | Who: P4H coordinator
Review by GTF | Who: DPC / P4H coordinator; N: GTF 8
Presentation to political entities | Who: DPC
Final strategy approved | Who: GTF large group; D: GTF 9