RESULT- BASED FINANCING PROJECT IN TANZANIA

PROCESS ASSESSMENT of THE PILOT PROJECT IN KISHAPU HEALTH DISTRICT - SHINYANGA REGION

Consultancy Report

Consultants:

Dr Eric BIGIRIMANA, MD, MSc

Dereck CHITAMA, PhD.

December 2016

Contents

Executive Summary	6

1	Introduction	9

2	Background	11

2.1	Geography and the economy	11

2.2	Health system	11

2.3	Health Status of the Population	12

2.4	Health Financing	12

2.5	RBF System in Tanzania	13

2.6	In summary	13

3	METHODOLOGY	14

3.1	Main objectives and scope of work	14

3.2	Data collection	16

3.3	Methods	17

4	FINDINGS	19

4.1	Design and institutional set up	19

4.1.1	More recruitment autonomy to address the shortage of staff in rural areas	20

4.1.2	Savings: the key to maintain the balance between expenditures and income	22

4.1.3	More procurement autonomy to address stock-outs	23

4.2	General knowledge on RBF	24

4.3	Are key RBF functions fulfilled?	26

4.3.1	Regulator (MOHCDGEC)	26

4.3.2	Facilitator (PO-RALG and its deconcentrated bodies)	42

4.3.3	Purchaser (NHIF)	48

4.3.4	Fund holder (MoF)	59

4.3.5	Provider / Health Facilities and MSD	63

4.3.6	Verifier  (IAG)	77

4.3.7	PBF steering Committee	83

4.3.8	The Counter – Verifier (Controller Auditor General)	84

5	DISCUSSION AND SOLUTION HINTS	85

5.1	The design phase	85

5.2	The training phase	85

5.3	The Implementation	85

5.3.1	Regulation role	86

5.3.2	Facilitation Role	86

5.3.3	Purchasing role	86

5.3.4	Verification role	87

5.3.5	Health care provision role	88

5.3.6	Counter verification role	88

5.3.7	Fund Holding role	88

6	References	89

ACRONYMS

BOT:      	Bank of Tanzania

BRN:      	Big Results Now

CBO:      	Community Based Organization

CCHP:   	Comprehensive Council Health Plan

CHMT:  	Council Health Management Team

CMO:    	Chief Medical Officer

RHMT:  	Regional Health Management Team

DED:      	District Executive Director

DMO:    	District Medical Officer

DPP:      	Directorate of Policy and Planning

DQA:     	Directorate of Quality Assurance

GIZ:        	German Development Cooperation

HFTWG: 	Health Financing Technical Working Group

IAG:        	Internal Auditor General

MOF:    	 Ministry Of Finance

MOHCDGEC: 	Ministry of Health Community Development, Gender, Elderly and Children

MOHSW: 	Ministry of Health and Social Welfare

NHIF:    	National Health Insurance Fund

PBF:     		 Performance Based Financing

P4H:     	Providing for Health

P4P:     		Pay For Performance

PFM:    	 Public Financing Management

PMORALG: 	Prime Minister Office for Regional and Local Government

PO-PSRS: 	President’s Office- Public Service Recruitment Secretariat

PORALG: 	President Office for Regional and Local Government

PS:  		Permanent Secretary

RAS:   		Regional Administrative Secretary

RBF:   		Result- Based Financing

SNHI:  		Single National Health Insurance

WHO: 		World Health Organization

Acknowledgement

We are grateful to the World Health Organization (WHO) and P4H/GIZ for the support and supervision that the focal persons, respectively Elina Dayle and Nina Siegert, contributed in the course of this work.

Also our gratitude to Pr. Bruno Meessen from Antwerp Institute of Tropical Medicine for technical and methodological collaboration that he provided us for this work completion.

Finally to all actors in the Tanzanian health system for the true collaboration we always witnessed during our meetings. The results of this work would not have been available without their opening sense and strong desire to further learn on the Result Based Financing.

# Executive Summary

This report is the main output of a mission led by Eric Bigirimana, MD, MSc. For this assessment, he was assisted by Dereck Chitama, PhD (field surveys) and Bruno Meessen, PhD (guidance). The mission was funded by the World Health Organization and the GIZ Gobal Project P4H.

The mission took place from June to October 2016. It was done in two stages, namely a first mission in June and a second mission in October 2016.

The main objective assigned to the mission was to assess the RBF implementation process in line with the Project Design Document and the operational manual. The assessment will help  make recommendations for a smooth continuation of health interventions.

The main findings are the following ones:

- Adoption: The RBF has been well received by officials of the Ministry of Health and Social Welfare and PORALG in Tanzania. This has manifested itself through an inclusive approach of consultation that involved senior officials of key directorates, those of health programs, the various important services in the implementation of health programs. The establishment of a RBF team was an important step for the roll out of the RBF pilot experience.

Recommendation: Further strengthen the inclusive approach by improving the larger scale information sharing starting with senior officials of the Ministry of Health and Welfare, PORALG and MOF. To involve them will improve the process of implementation and contribute to its adoption beyond the pilot.

- Vision: The RBF is considered as a mechanism which is well integrated into existing sector strategies for financing and improving quality of health services implemented by the Government (e.g. the HSSPIV, BRN initiative, draft health financing strategy). It is not seen as a magic bullet expected to solve all the problems found around health services delivery but a welcome innovation to introduce some level of performance based purchasing in Tanzania. However, as a result, certain issues, like managerial autonomy of facilities, ability to hire staff, contract negotiation, use of remoteness bonus need to still be addressed in this pilot. This could be changed and RBF could spearhead many of these related PFM and HF reforms.

Recommendation: Ensure effective complementarity between RBF and other initiatives of the Government and Integrate RBF’s good practices to address the weaknesses of the Tanzanian health system.

- General design: Key documents such as the project design document defining the institutional arrangements are in place. It is remarkable that a special effort has been made to embed the RBF system within the existing structures and use the existing procedures. As for the operational manual, it details the procedures to follow and the roles and responsibilities of each structure involved in the implementation.

- Design features: Some RBF good practices have not received the required attention to meet the needs expressed by health facilities at the peripheral level. This is for example:

- Use of the equity bonus which is usually applied to improve resources availability in remote areas, which helps to attract and to retain staff and to improve the standards for infrastructures and equipments;

- Promotion of  the balance between expenditures and revenues to ensure financial sustainability in case of payment delays;

- Competition for contracts that make health facilities take contracts for granted.

- Technical leadership: The national RBF team is well organized and is capable to follow the RBF implementation activities. However, different actions can be taken to strengthen its capacities further. First, the team could be more exposed to RBF approaches outside Tanzania. Second, it has to expand its roles in terms of active monitoring and evaluation and advocacy. Moreover, the geographical constraints (vast geographical distances of the country/ large country – small RBF team i.e. national team will not be able to cope serving all the regions as roll out continues (capacity constraints)  calls for establishment of regional RBF task force to be built within the RHMT as relay of RBF national team to ensure close monitoring.

Recommendation: Strengthen the capacity of the RBF National team as well as regional capacities to enable smooth further roll out of RBF.

- Implementation at peripheral level: So far, the training that stakeholders benefited from put more emphasis on the operational aspects, at the expense of explaining the implications of the RBF fundamental principles. There is need for them to keep those principles in mind to avoid some lack of separation of functions found at the regional level.

Recommendation:  Improve training for RBF stakeholders at various health system level (health providers, RHMT, CHMT, National RBF Team) by giving sufficient weight to the implications of the RBF principles and best practices. This requires a refresher training with new modules to emphasize the RBF principles and good practices.

- Local associations have not been sub-contracted to carry out the community verification and patient satisfaction surveys.

Recommendation: Revise certain roles and responsibilities assignments by ensuring an effective separation of key functions in accordance with RBF guidelines. This is especially the case for the separation of the regulation and the verification functions at the regional level. The local based organizations could be involved as verifiers at the community level as it is described by the project design document.

- Implementation at higher levels: Roles and responsibilities were well followed by structures like the RBF national team, the health care providers and verifiers. However, some structures have not yet exercised their functions. These include the:

- The role of NHIF has been limited to signing annual contracts with different RBF stakeholders (RHMT, CHMT, Health facilities). Today, it cannot properly monitor compliance with contract terms and content of the Business Plans to improve performance. It has not yet assumed full role as RBF related purchaser a lot of the functions are still carried out by MOH directly.

- Internal Auditor General who has not fully played its role, which gave way to RHMT to act as principal verifier thereby creating a possible conflict of interest between the regulatory function and the verification function.

- CAG is not yet contracted to conduct an external verification.

Recommendation: Let each implementation structure play its role in the RBF framework ensuring the availability of resources and capacity required and the necessary autonomy to avoid conflicts of interest.

# Introduction

In low-and middle-income countries (LMICs), Results-based financing (RBF) is a relatively new strategy in health financing. The strategy innovates by linking financing to outputs, measured through pre-determined indicators. Through this mechanism, it can accelerate the achievement of health targets. Experiences in several countries like Rwanda (Meessen, B., Musango, L. et al. 2006, Soeters R, Habineza C et al. 2006)), Burundi (Peter Bob Perenboom, Olivier Basenya et al. 2014) or Cambodia (Van de Poel E, Flores G,et al.2016) , have also shown that it has the potential to boost health system functioning and facilitate the progress towards universal health coverage ( Meessen B., Soucat A., Sekabaraga C. 2011).

Yet, introducing and scaling up RBF is not straightforward. RBF corresponds to a paradigm shift that puts strong focus on purchasing results in accordance with health system priorities of the country rather than providing inputs to health facilities as it was the case with the input-based financing approach. While RBF is a flexible strategy, a body of practice has emerged and certain principles and good practices are today recommended (Fritsche G, Soeters R, Meessen B, 2014) . Beyond the purchase of results, these principles ensure a lifting of bottlenecks to allow a full performance of the health system at all implementation stages. The application of these principles and good practices is also as important as the funding approach per se to reach a desired improvement of health indicators.

RBF system is also about learning and improving. It requires systematic monitoring and documentation of system design and implementation, as well as thorough evaluation of effects. There is more and more evidence on the effectiveness of the RBF in different contexts of developing countries such as the sub-Saharan Africa. There is also a vast international experience embodied in experts themselves and global knowledge to tap for any country willing to move with the RBF agenda.

This is certainly the case of Tanzania. Between 2011 and 2013, the country experimented with pay-for-performance (P4P) project in Pwani region. This but also another pilot project in Zanzibar have provided key lessons such as the importance of integrating P4P activities within the existing structure, provision of facility autonomy, and teamwork. A key lesson learnt in course of implementation of the pilot is that a strengthened health system enables smooth implementation and achievements of any output-based financing mechanism.

However, certain limitations were noticed and they have motivated a redesign of the RBF approach. In 2014 and 2015, stakeholders worked closely to revise RBF, integrating lessons from experiences elsewhere in the region. There were also some synergies to seize with particularly the discussions around the health financing strategy development, and certainly the Big Results Now initiative (BRN initiative).

The first pilot project was launched in Shinyanga region, Kishapu district in April 2015, after the elaboration of key documents such as the RBF design document and the operational manual. The further roll out to other regions has started early 2016 in accordance with the RBF project design established by the MOHSW until 2020. This is the state of affairs that as consultants, we were invited to document and assess.

Our assessment task of the implementation process focuses on the experience of Kishapu district in Shinyanga region and aims to :

- Assess the implementation of RBF against the RBF Design Document and Operations Manual,

- Assess the implementation of RBF from the perspective of integration and sustainability,

- Formulate practical recommendations to ensure that RBF roll-out supports the goal and objectives of current reforms in service delivery, health financing, and Public Financing Management (PFM) and as expressed in key strategic and analytic documents, including the draft Health Financing Strategy.

The assessment and recommendations will focus on the roles and responsibilities for each RBF stakeholder to see how far the activities are carried out and bring technical and analytical views on their effectiveness to continuously strengthen the health system.

The report is divided in 4 main parts, starting by the background which shows the situation of the reform processes occurring in Tanzania. These reforms paved the path to the different steps of designing and implementing RBF. The following parts will be on the methodology used to collect data at various levels of the health system. The findings present the compliance of the different RBF stakeholders to their roles and responsibilities. An analysis is conducted based on those findings to assess the processes used during the pilot phase in Kishapu health district. After each key function, recommendations are formulated to guide the policy makers on changes needed or adjustments to be brought in.

# Background

## Geography and the economy

According to the Project Design Document, the population of Tanzania mainland is estimated to be about 49 million people living on 945,087 sq. km. About 75% of the population lives in rural areas while the majority of the human resource for the health work in urban areas.  The country is divided into 167 Local Government Authorities (LGAs) known also as councils and which are the implementing units’ foremost services in the country. This width of the Tanzanian territory and the decentralization dynamic require some coping mechanisms to adapt the RBF approach to the local realities.

## Health system

The Government operates a decentralized health system, organized around three functional levels: council (primary level), regional (secondary level), and referral hospitals (tertiary level). The council level corresponds to what is called ‘health districts’ in many other sub-Saharan African countries.

However, there are differences with the situation in many other similar countries. Within the framework of the ongoing local government reforms, regional and councils have full responsibilities for delivering health services within their areas of jurisdiction, and report administratively to the President’s Office for Regional Administration and Local Government (PO-RALG) – and not the Ministry of Health. As we explain later in this report, this separation of functions raises particular challenges due to structural set up, but also creates opportunities in terms decentralization.

Under this system, the councils have full mandate for planning, implementation, monitoring and evaluation of health services. Each council has a District Medical Officer (DMO) who heads the Council Health Management Team (CHMT) and is answerable to the District Executive Director (DED), the head of the council. CHMTs are responsible for provision of services in dispensaries, health centers and district or District- Designated Hospitals

The Regional Health Management Teams (RHMTs) are responsible for interpreting health policies at the regional level. The RHMT is a kind of regional Health regulator headed by the Regional Medical Officer (RMO) who is answerable to the Regional Administrative Secretary (RAS) and not directly to the Ministry of Health and social welfare (MOHSW).

The Ministry of Health, Community Development, Gender, Elderly and Children(MOHCDGEC) is responsible for policy formulation, supervision and regulation for all health services throughout the country, as well as playing a direct role in the management of tertiary health services. There are about 6,518 health facilities, of which 70% are owned by the public sector (MoHSW2013).

In a nutshell, the system is in the form of a pyramid on top of which there are specialized hospitals owned by the MoHSW and at the bottom are primary health care facilities. Almost 85% of the population gets their health services from primary health care facilities (MoHSW 2013), however they face a lot of challenges in delivering services including poor infrastructure, shortage of skilled staff and essential medicines.

According to the project design document and the operational manual, the main challenge of the health sector in Tanzania is the shortage and mal-distribution of human resources for health (HRH) which affects the availability and readiness of health services across regions, districts and health facilities. According to the HRH Public Expenditure Review (PER) of 2010, the HR gap was about 60% (MoHSW HRH Report, 2011). The health sector is challenged with production, attrition and retention of health professionals. A recent study documenting staffing levels and productivity in southern Tanzania (Manzi et al, 2012) found inadequate staffing of health facilities, high levels of absenteeism and low productivity. These are issues which RBF have sometimes managed to correct in other countries (reference).

## Health Status of the Population

The current data on health status of Tanzania shows progress in achieving 2015 health targets. The Mid Term Review analytical report (MoHSW/WHO 2013) shows that there has been improvement for some HSSPIII indicators toward achieving the 2015 targets, such as infant and under five mortality rates, immunization coverage, HIV management etc. However some indicators show no progress despite the various interventions put in place.

An assessment of the socio-health situation led to the creation of package of indicators requiring particular attention in line with the BRN initiative. BRN is a domestic results-driven reform whose methodology is geared towards transforming government delivery and changing the way it works. This is done through establishing clear performance targets, rigorous tracking and monitoring of implementation progress as well as problem solving within the BRN Delivery System. BRN is therefore a domestic results-based approach and an “umbrella” for a number of public sector reforms. The Big Results Now Initiative was launched by the President in 2014. It aims at improving the performance of public services relying on the « delivery Units » model.

## Health Financing

This Draft Health Financing Strategy (HFS) describes the strategic direction of the health sector relating to health financing for the period 2015-2025. The fourth pillar stipulates that this strategy will improve the Health Care Purchasing by establishment of a Standard Minimum Benefit Package as legal entitlement to the whole population.  This package would evolve over time as available funding increases, and the health system is strengthened.  It will also allocate Health Sector Resources Strategically with the intention of continuously adapting and shaping the purchasing structure within the health system, placing particular focus on improving incentives for improved services delivery (e.g. through results-based financing).  This strategy aims at developing effective provider payment methods throughout the country with integrated performance structures.

This Health Financing Strategy paved the path for the RBF pilot and it is ready to incorporate the reforms coming with it.

## RBF System in Tanzania

The current RBF system in Tanzania was launched in April 2015 as a pilot project in Kishapu district, Shinyanga region. This will be scaled up progressively, informed by implementation research, to eventually cover all regions in the country. The primary purpose of the process assessment of the Shinyanga Region RBF Pilot is to inform the next phase of RBF roll-out. The results and recommendations of the assessment will be used to determine project- and sector-specific interventions to contribute to the success and sustainability of the RBF roll-out. This may include: modifying the RBF design, enhancing broader health-sector level framework conditions for RBF, and increasing government ownership and leadership of RBF in the country. It is also intended to inform preparation for SNHI implementation and broader PFM realignment.

## In summary

This assessment of the RBF process occurs after one year of implementation in Kishapu District in Tanzania. The country made progress on some indicators and encountered failures on others, which motivated the change in the initial P4P design towards the current RBF. With its geographically large size and location, effective M&E and guided implementation in the region pose logistical and financial challenges to routine RBF activities.

The political will is shown through the extent to which the country launched reforms with the BRN initiative. The RBF is included as an innovation in the health sector but it must cope with the challenge of stimulation of change in the existing system to make it perform better.

This assessment will explore technical and financial questions to address the assigned targets. And to achieve this, the following methodology shows the applied procedures and techniques.

# METHODOLOGY

## Main objectives and scope of work

The main objectives of the RBF process assessment are to:

- Assess the implementation of RBF against the RBF Design Document and Operations Manual,

- Assess the implementation of RBF from the perspective of integration and sustainability,

- Formulate practical recommendations to ensure that RBF roll-out supports the goal and objectives of current reforms in service delivery, health financing, and Public Financing Management (PFM) and as expressed in key strategic and analytic documents, including the draft Health Financing Strategy.

The assessment and recommendations will focus on the roles and responsibilities for each RBF stakeholder to see how far the activities are carried out and bring technical and analytical views on their effectiveness to continuously strengthen the health system.

This assessment is carried out after one year of RBF implementation in Kishapu health district. As a process assessment, it investigates how the strategic choices were made and how far the operational activities were carried out. This will assess the adequacy between health system challenges and the RBF strategies adopted. It will highlight the strengths and the weaknesses of this pilot project and formulate the recommendations to the different RBF stakeholders. This will enable the decision makers and policy makers to take corrective measures, make adjustments or revisions needed to strengthen and make the health system more productive.

A performing RBF scheme requires a sound design

Two key documents namely the project design document and in the operational manual highlight the guidelines for RBF design in Tanzania. The first shows the key players of the RBF Tanzanian model and explains the vision that is conveyed by this new architectural set up. The roles and responsibilities are assigned to each stakeholder based on RBF principles and good practices. Building on the international RBF experience of the lead consultant, we carried out an assessment of the extent to which the RBF scheme in Tanzania satisfies the principles and good practices identified by the RBF expert community.

A well performing RBF scheme also requires a good implementation.

As for the operational manual, procedures to be followed and the sequence of necessary activities to be undertaken to ensure improved performance of the health system are explained. The activities undertaken by each RBF stakeholder come from guidelines dictated by the institutional structure and the operational manual in strict compliance with the practices advocated by this approach.

Thus, the assessment takes into consideration the key steps from process taken to move from the elaboration of key documents to the preparation and the real implementation. We also checked whether what was described in the plans was actually implemented at the frontline level and actions taken in compliance with the RBF rules of the game. A very important aspect concerned the assessment of the procedures for the operational implementation at the Kishapu district in Shinyanga region. This component helped us explore the respective roles and responsibilities that each actor has to perform. In addition, some skills assessment placed at the disposal of this project was completed.

Sustainability matters

In terms of project financial sustainability, a financial analysis was conducted at key health facilities. It helped us understand the financial implications of this pilot project. Projection to a broader scale-up will help the Government of Tanzania and international organizations to see the level of requirement and the cost-effectiveness that this approach brings.

The institutional sustainability needs to be built within the heath system by involving the existing structures but the separation of functions should be respected. The technical sustainability will rely on the support and assistance that the teams will receive to build capacities of the local experts.  The stage of elaboration of key documents and that of operationalization are connected by successive trainings to prepare teams at regional, council and health facility levels. Thus an analysis of the training stage was conducted.

Our approach

The team of consultants is made up of three consultants, building a multidisciplinary team of complementary expertise.

The lead consultant is a medical doctor and public health specialist with extensive experience in the region. His expertise is complemented by the support from a senior RBF health economist with a long history of international expertise of RBF. The two international consultants are supported by a national consultant with a background in health economics.

The lead consultant is putting ahead his tacit knowledge based on his long experience of RBF implementation in different African countries while the senior health economist focuses on the integration and sustainability part of the RBF experience beside the overall backstopping.

The national consultant is bringing his knowledge of the health system in Tanzania and helps the rest of the team to get access to the right sources of information.

## Data collection

Literature review

The literature review was started by identifying key reading materials that are RBF related and those that give the broad guidelines for the future of health in Tanzania. Documents included:

- RBF design document

- Operational  manual

- USAID assessment document

- HSSP 3

- HSSP4

- Draft health financing strategy 2015-25

- Aide- memoire BM & MOH

- Training Guide for Providers

- Training Guide for verifiers.

The documents were consulted by taking important notes related to the subject of the evaluation. This shed light on the country context and the actors that have been put forward in the RBF implementation. Identification of actors at each level of the health pyramid and the roles and responsibilities they have exercised allowed us to develop specific tools to collect the data itself.

Development of data collection tools

Three types of documents have been developed and used for data collection with different RBF implementation actors:

- A semi-structured interview guide was prepared to conduct individual interviews with the actors directly or indirectly involved in the implementation of the FBR. This guide builds on the implementation cycle of the RBF.

- A questionnaire for self-assessment with such components as the different strands of activities to be undertaken by function. And the questionnaires were adapted to the respective actors including RBF national team, the RHMT, CHMT, the health facilities. The questions and statements run through the routine activities related to the RBF implementation to allow capacity self-assessment for each component.

- A questionnaire for the identification of stakeholders and resource persons. It allows the evaluation of the adequacy of their professional profile and the position held.

- The RBF integration framework in the health system that builds on the framework of strengthening the health system (WHO, 2008). It focuses on the building blocks of the health system namely the provision of care and services, human resources, infrastructure and equipment, the financing of health, health information, governance and leadership, medicines and other pharmaceutical products.

The tools can be found in the appendix.

## Methods

Direct observation

In all visited structure, direct observation was applied to assess the team’s organization, communication, information sharing and individual behavior. The readiness and quality of teamwork were briefly evaluated. This direct observation has also allowed us to see the level of involvement of each resource person in the various teams including RBF Unit, the RHMT the CHMT and to a lesser extent in health facilities.

Group discussions (with the implementation teams)

Group discussions were organized to assess the collective understanding of the RBF and its implications to the various implementation stages. General questions about the RBF on the functions at each level. During these discussions, the floor was given to each member of the team in order to assess their individual level of understanding of the RBF concept and information sharing level received during training. Participants could complement each other in answering our questions. These group discussions were followed by individual interviews.

In-depth Interviews

- Individual in-depth interviews were targeting people who did not take part in group discussions and aimed to understand the level of understanding of the RBF and its implications for successful implementation. Those individual interviews were conducted with RBF national team members, the Director of Quality Assurance (DQA), the Director of Health Management Information System (HMIS), the  Chief Medical Officer (CMO), the Chief Accountant (CA), the RBF Accountant, the Director of Policy and  Planning (DPP), the Director of Preventive Care (DPC in charge of vertical programs), the Controller Auditor General for the health sector, the acting Regional Administrative Secretary (RAS), the selected health professionals at different health system levels in Shinyanga region.

- International Organizations:

- USAID (3 persons: PS3 and 2 others), P4H Country Focal Person, Chairperson of the DPGH (Development partner group health), Public Health Expert who worked on the Pwani Project

The interview was structured based on the PBF implementation cycle while exploring aspects related to the design and assigning roles and responsibilities for the actors who were involved in these two steps. For actors whose activities are devoted to a step such as verification, training or payment procedures, more pointed questions were asked about this step which now occupied the major part of the interview.

Some saturation was sought during various interviews and triangulation was made to better understand the contours of the RBF implementation in Tanzania.

Self-assessment

Some of our informants were invited to participate in a self-assessment. Each time, one consultant explained the content of the tool and the information sought for. The methodology followed for individually self-administering the questionnaire first and collective self-assessment in team then was explained. Members of the research team were present to facilitate the understanding of the items put in the questionnaire. This self-assessment was conducted to evaluate the readiness and capabilities available at different levels of the RBF system.

Identification was also conducted through a questionnaire that identifies the profile of implementing actors.

Evaluation of the level of integration of RBF

The level of integration of the RBF into the health system was assessed by asking predetermined questions about the various the health system building blocks (WHO, 2008). In terms of strengthening the health system by RBF, key aspects were identified to see the level of integration of appropriate measures or practices to the efficiency of RBF.

# FINDINGS

The results are presented beginning with the provisions of the institutional structure and the principles put forward in the implementation of the Tanzanian RBF. These aspects help explain the choices made by the country and the issues that guided to make these choices according to the contextual realities.

They will be followed by analysis of the level of respect of roles and responsibilities assigned to each implementation actor. Our work will explore the alignment or not of the actions undertaken on the directions of policy documents namely the Operational Manual and the Project Design Document.

The observations we have made in our various filed visits are also made to highlight the strengths and weaknesses that characterize this model of the Tanzanian RBF. The order given to different key functions will keep some consistency as to the sequence followed in the practical implementation of the approach.

The opportunities and threats observed have led us to the formulation of recommendations issued progressively to inform policy makers on relevant action to be undertaken.

## Design and institutional set up

As it is found in several countries that adopted the RBF, the institutional set up of Tanzania gave birth to a RBF steering committee to highly monitor the evaluation of that approach. Structures were determined to assure the key functions notably the regulation, facilitation, result purchasing, verification and health care provision.

Our assessment is that the Tanzanian RBF model complies with most principles and good practices in terms of RBF design.

The notion of separation of functions was initiated on macrosystemic level in assigning regulation functions to MOHSW, the facilitation role to PORALG, purchaser role to NHIF, verifier’s role to IAG, Fund Holder role to MOF, provider’s role to health facilities and the external verifier’s role to CAG. The internal  verifier (AIG) was asked to sign a subcontract with local NGOs for community verification on patient tracing and assessment of  patient ‘s satisfaction.

On meso systemic level (intermediate), roles and responsibilities were given to intermediate organs such as RHMT and CHMT to assure the best connection between the policy and operational implementation.

On micro systemic level (peripheral), the Tanzanian RBF model took into account criteria such as the payments based on output made to a bank account of the health center, hospital or clinic. The officials of the health centers with the Health Facility Governing Committees have been granted the right to withdraw and use funds according to their needs. In their operation, they are required to develop a business plan and sign a contract. These practices show that the Tanzanian model of RBF adopted the principles and good practices of the Performance Based Financing (PBF)(Fritsche G. et al. 2014) .

However, some other principles were left aside. We would like to highlight three points of deviation: (1) the ability to hire or fire staff according to the needs expressed at the health facility, (2) being able to maintain the balance between expenditures and income, (3) the ability to purchase drugs or equipment at a wider list of certified suppliers to create competition for reduced prices and to avoid stock out of drugs in facilities. .

In the following sections, we will develop these three points.

### More recruitment autonomy to address the shortage of staff in rural areas

As a reminder, one of the main challenges for the Tanzania’s health system is the mal-distribution of health staff: there are insufficient trained personnel in rural facilities, while they are expected to serve around 75% of the population (Reference RBF design document).

Our field work evidenced that recruitment of staff remains the prerogative of the President’s Office- Public Service Recruitment Secretariat (PO-PSRS) "Utumishi" which has to assign staff by region and council. Indeed, from the discussions we had at the regional level emerged that the RAS compiles the human resources needs and sent the request to the MoL in Dar-Es-salaam. The latter will then allocate resources depending on the available qualified personnel. Thus, the requested numbers are rarely given especially for councils which are in rural areas, most professionals preferring to stay in the big cities. One of the high officials recognized that:

It is different for Dar- Es-Salam, where we have 51 % of the staff. The 49% remaining are distributed across regions. So you need to redistribute from Dar-Es-Salaam to some regions especially the lakes regions like Shinyanga, Geita, Shemiyo or the western regions like Tabora, Kigoma, we need very good support from the Ministry.(Ref)

These procedures have not changed despite an axis to improve the availability of human resources mentioned in the BRN initiative document.

On the possibility of allowing health facilities to recruit staff, decision maker level key informant at the regional level told us the following:

I am not sure the facilities have capacities to scrutinize the skills for personnel required at the health facilities. So you need someone high up who will oversee this. This can be the DED, assisted by the DMO or the District HR officer

From experience in other ‘RBF countries’, we know that misallocation of human resources is a major challenge. The RBF community recommends enough autonomy for health facilities to recruit staff according to their needs, if they have the means to pay them. They should also be allowed to dismiss them in case of staff misconduct or in case of staff plethora situation. The way to move towards such an ideal situation is to allow health facilities to recruit ‘contracted staff’ (full-time or part-time). The signed contracts can be long or short term with specifications that are negotiated between the facility and the employee.

This good practice experience of RBF can be accompanied by establishing an equity bonus for remote health facilities (see box). This would help to gradually relax the human resources constraint. The introduction of such an equity bonus has not been considered in the development stage of the project.

Equity bonus, remoteness bonuses or isolation bonuses (Gyuri et al. 2014)

This strategy   is used for reaching the poor. It consists in adjusting the payment schedule so that providers in poor areas are paid higher amounts for each service delivered than providers in wealthier areas. This is called ‘remoteness bonus’ in countries like Zimbabwe, ‘isolation bonus’ in some parts of DRC or ‘equity bonus’ in Burundi

Theses bonuses are a form of geographic targeting and a way to push more resources to underserved facilities in remote, and typically poor, areas where the health outcomes tend to be worse.

The fundamental idea behind this approach is to enable facilities to have relatively more resources for paying the higher cost of providing quality services to their population. Attracting and retaining good health care workers and paying for the higher cost  of transportation are the two main reasons behind this approach.

- Recommendations: To allow health centers and hospitals to hire staff when needed, Health facilities must ensure they possess the necessary financial resources to pay the recruited staff. This staff must negotiate with officials of the center or the hospital and sign a contract for either full- or part-time engagement depending on the needs of the facility.

- Integrate the equity bonus for the allocation of resources to health facilities. Eligibility would be opened to facilities which are disadvantaged – for instance, because of geographical remoteness, dilapidation of their infrastructure, reduced number of staff, etc. This bonus will make them more attractive to health workers but also make them as competitive as those in favorable environments such as urban or semi-urban areas.

### Savings: the key to maintain the balance between expenditures and income

Any organization should worry about the sustainability of its performance. This goes through a permanent concern to balance expenses with incomes. Thus expenses and investment should be realistic and lead to a more comfortable financial situation. The standard recommendation to ‘RBF’ health facilities is to gradually build bank reserves. They can help them to sustain their activities, even in case of shocks (typical in RBF systems are delays in payments). These bank reserves can help facilities to make some expensive investments which require many months’ savings.

Our experience has taught us that such bank reserves can greatly enhance financial stability in order to maintain normal operation.

This principle is not applied in the Tanzania model. This aspect seems not to have been developed during the training.

Recommendations:

- To introduce the notion of balance between expenses and revenues in health centers and hospitals itrequires capacity building to master management tools including the ‘index tool’ that will help facilities better allocate their resources.

Indices tool

The indices tool is a financial management tool that helps the manager (a) manage all cash income and expenses of the facility in a holistic and integrated manner, (b) provide summary snapshot on the income and expense statements of the health facility and therefore, is also a budget planning tool; and (c) allocate performance bonuses to individual health workers in a transparent manner. (Gyuri F. Et al. 2014, PBF toolkit, p.155).

### More procurement autonomy to address stock-outs

The ability to purchase drugs or equipment at a wider list of certified suppliers is one of the RBF practices to avoid stock out of drugs. This creates competition for reduced prices at the drug suppliers’ level. Today, health facilities are authorized to replenish from accredited drug stores only when drugs are missing from the public MSD. The problem is that stock-outs at the MSD are not known in advance. Furthermore, facilities experience loss of time and financial resources (they must pay for transportation, hotels, meals and incidentals of the agents sent to the store). In some remote facilities, the cost for those expenses is actually higher than the money to be withdrawn! Indeed, health center agents must travel long distances to the MSD in Mwanza where they will be informed whether the products are available or not. It is only when certain products are not present that agents can revert to licensed structures such as Shinyanga Pharmacy  and  Kishapu Pharmacy.

This process is cumbersome and costly for the health center team. Keeping this conditionality increases the interference of the Council in health facilities management with abuses sometimes observed in some structures.

A simplification of these procedures combined with a strengthening of expenditure audit activities may be more efficient without affecting the level of transparency and accountability.

In Cameroon, South West region, part of the solution came from the accreditation of other wholesale pharmacies through specific criteria validated at the national level. This allowed for more openness and more competition. Private health centers have begun to buy medicines in the regional public repository (Special Fund for the Health Promotion) instead of traveling long distances to purchase from private sellers in Douala. Public health centers could source in faith pharmaceutical stores that are close to them. A total of 4 large pharmacies were competing to attract customers of health centers and offered drugs at competitive prices. In addition, they were planning to open branches in remote areas where customers were present, which would facilitate access to medicines for rural health centers.

With this experience in other countries, we believe that this would be far better compared to logistic strengthening system for MSD to supply drugs to health facilities. Recommendations:

- Enhance competition between MSD and accredited drug suppliers to enable health facilities to access drug products quickly. Health facilities should be allowed to replenish stock from less expensive accredited pharmacies without the approval of the MSD. This would reduce stock-outs, would impact on the price of goods sold and significantly reduce the procurement process costs. This reform would push the MSD to open branches in the region of Shinyanga even in the Kishapu district in a commercial logic of competition.

- Remove the requirement to approve requisitions and cash withdrawals at the Council. This would strengthen the autonomy of health centers in their decision-making processes and would improve reactivity in solving problems. In return, respect for regulatory rules and directives could be strengthened through supervision activities and financial auditing at facility level.

## General knowledge on RBF

The training sessions focused on the operational aspects including the development of the Business Plan, the types of contracts that are signed, the verification method, payment procedures, sharing incentive bonuses for staff, etc. This emerged in the discussions we have had with some of the staff.

During our visits to facilities, we have checked the general understanding of RBF at the level of facility staff. Our assessment is that knowledge on the RBF system is limited to the reward for the results produced. The staff is not aware of RBF principles and good practices which can be introduced with the approach.

From our discussion with the staff in several facilities, it emerged that RBF practices such as the separation of functions in RBF, management autonomy, the authorization to recruit staff, the importance of a good balance between expenses and revenues have not been taught during training.

More generally, it seems that several RBF concepts, ‘principles’ (or good practices) (e.g. the application of equity/ remoteness bonus, the balance between expenditures and revenues, etc) or processes (e.g. the contract negotiation, link between a Business Plan and the signing of performance contract, use of indices tool, etc.) have not been promoted in Tanzania. We have reviewed the training guide. The explanation on the implications related to these principles is not provided.

Our observation is that this was probably due to the current practices found in the Tanzanian health system where the pre-established rules and procedures seem to have influenced the set up and the RBF implementation regulations.

Here, the question is to know whether the RBF wants to fit with existing systems and procedures in Tanzania or whether the RBF has to bring solution suggestions to instigate needed reforms for the best productivity. We estimate that the second position would be the best but it requires the openness and the flexibility of the Tanzanian policy and decision makers.

RBF Training

The training was organized starting by the training of trainers who were the members of the RBF national team and some professionals from academic institutions. The Facilitation was conducted by the Technical assistant who is an RBF expert.

The group of trainers started then to conduct training in the region starting by the health facilities and the Council Health Management Team (CHMT). 2 persons per health facility and 5 persons from the CHMT were trained to ensure a good understanding of the RBF concept.

These were expected to train other staff in their facility. However, in some facility they did not. In some facilities those who got training have been relocated or retired. The remaining ones do not have a good idea of RBF requirements.

The resource persons from administrative services were invited for a session of orientation on RBF which is a two days workshop where some key RBF features were taught.

The training for verifiers was carried out later in February 2016.

The training facilitation teams are made of trainers from the central level and some selected at the local level. All of them have been trained during the initial session of training conducted by the national team.

## Are key RBF functions fulfilled?

In this section, we analyze the extent to which key functions of a RBF system are fulfilled.  Our assessment combines two sources of information: the information we gathered during interviews and group discussions and the self-assessment questionnaire.  Our assessment is organized per function.

### Regulator (MOHCDGEC)

In the project design document  it is said that the MOHCDGEC must provide clinical and technical vision and oversight to ensure the quality of services offered to the population and that all directorates should work together to ensure better implementation of RBF system.

Within the MOHCDGEC, it is the Policy and Planning Department which is formally assigned the role of coordinating the implementation of RBF system. It is governed by the MOHCDGEC RBF Steering Committee which in turn can be advised by the MOHCDGEC. An RBF National Team is appointed within the Department of Policy and Planning to carry out the day-to-day RBF implementation functions and coordination with the other RBF participating institutions.

Our work will show the involvement of different levels of decision making in the regulation of RBF starting first by the central level of MOHCDGEC we visited. This central level is represented at regional and district levels respectively by the RHMT and CHMT that have some solemn responsibilities for health programs in general and for the RBF in particular.

The description of our analysis tackles the key central level directorates exercising their regulatory work based on the action of the RBF national team, regulations regional teams that are RHMTs and CHMT in their respective entities. This will further highlight the potential for conflict of interest observed in relation to key RBF functions.

Regulation can be defined as the mandate to ensure the population receives quality health services to improve their livelihood. This requires the different stakeholders to be aligned to the norms and standards to provide good quality services.

The Ministry is in charge of formulation and issuance of standards, plans and guidelines, their inscription in official documents and procedures and oversight efforts to ensure due compliance by other actors of the health sector.

According to the project design document, in Tanzania, it is the MOHCDGEC which has this role. It has the responsibility for overseeing all services provided to the population of Tanzania. It must ensure that provided services are of quality by their compliance with health standards of the country to ensure population’s well-being. It ensures oversight through devolved or decentralized bodies at regional level and at the level of councils.

#### Inclusive process at initial stage

From our discussion with key informants, we made the following observations:

- The development of the institutional structure of the RBF and the preparation of the initial stages of implementation were conducted in an inclusive and participatory way. The different directorates were consulted and involved to bring their technical contributions. These include the Directorate of Quality Assurance, Directorate of Preventive Services, Directorate of Health Information System.

One of the informants described the process as follows:  There was a series of workshops at different stages, with various people. For the selection of indicators, the programs were consulted. Some indicators were aligned with the Monitoring and Evaluation framework of the different programs such as RCH, Malaria, HIV. Indicators which have been collected for day to day follow up at the health facilities.

These statements show that the different directorates have been actively involved in policy formulation in collaboration with partners. This included the World Bank in formulating the new RBF project. The meetings between the MOHSW and missions of the World Bank demonstrate this commitment at the highest level. Similarly to elaborate the operational manual was effective participation in defining the roles of each RBF stakeholder.

#### Different strategies for same health system challenge

Our analysis of the BRN document found some reforms already defined and some of them overlap with areas where RBF usually suggests strategies.  Indeed, some challenges like the shortage of human resources in some rural areas, the stock out of drugs and commodities in health facilities, the poor conditions for infrastructures were handled in the BRN strategic plan.

For the Human resources for health, strategies have been taken to develop universal distribution mechanism streamlining recruitment and supply processes and to develop an implementation plan for national roll-out and incentives to sustain health workers distribution.

According to the BRN document this will be carried out in order to:

- Prioritize allocation of employment permits to 9 targeted regions with critical skilled HRH shortage and ensure prioritization of the underserved regions for the period between 2015 – 2018 to ensure balanced HRH distribution is achieved

- Initiate redistribution of health care workers within the regions and reinforcement of HRH redistribution within and between LGA in a region to ensure balanced distribution of staff.

For medicines and other health commodities, strategies rely on improving supply chain management, improving financing of health commodities and ensuring governance accountability throughout all levels of supply chain.

Concerning the infrastructures and equipment, the BRN initiative suggested the allocation of start-up fund for health facilities renovation and for buying some basic equipment to complete the package of services.

For those above-mentioned areas, the RBF project usually suggest some strategies to mitigate those shortcomings. The strategies promoted by the BRN have probably prevented the RBF promoters to suggest RBF-related strategies to avoid a kind of confrontation of strategies on same issues. This may have prevented the RBF promoters from digging too deeply into this question to propose related new strategies.

Human resources management is possibly the most important problem for the Tanzanian health system. When we asked why the design of the RBF has not offered solutions to address this problem, an informant who was at the center of shaping the RBF told us the following:

RBF is here to complement the Government initiative. It is not going to solve everything. That’s what we agreed in principle. We agreed the local Government will ensure to have staff in Health facilities. And we agreed to have at least one trained staff per facility. This is in the local Government  mandate to reallocate staff from where they have more to where they don’t have………………………………….So we don’t expect RBF to start improvising any Human Resource direct initiatives. We talked to the local authorities, they know their responsibilities. They need to make sure there is a conducive environment.

Our own interpretation of this statement is that the power of RBF to (partly) address some structural problems of the health system has not been fully recognized by senior health officials. The RBF is mainly seen as a way to motivate staff to improve the quality of services; it is less considered in the scope of an approach which is coming to reform some practices.

#### Need of wider ownership

From our interviews, we understand that the communication over RBF within the MOHSW and across directorates could be improved. Since the launch of the pilot project in Kishapu district, directorates that are not directly involved in the operationalization did not closely follow the development of events. The information produced at the field is shared primarily between the RBF team and its relevant directorate namely the DPP. Information is regularly presented at the Health Financing Technical Working Group and with the RBF Steering Committee, but several senior officials are not involved sufficiently to understand the progress made under the project.

On the question of what the RBF has achieved, a senior informant at the central level replied us that:

So I understand the concept but for practicalities, not much………………………………..You can talk to the technical entities. But myself and even the Permanent Secretary, we are the top posts but we have not been really engaged in this project itself. I don’t see a lot of RBF passing through me.

Another senior official expressed concern about its financial sustainability, arguing that it is a strategy that is fully supported by external funding:

This RBF approach is good but my concern is that it is totally donor- funded. I don’t know if without the international organizations, this will be sustainable. This is my concern.

The lack of communication across different parts of the Ministry generates information gaps on the progress of the RBF pilot project. Our interpretation is that this could indicate the need for more collaboration among different directorates. The risk of too little collaboration is that RBF may rapidly be perceived as a vertical program under the DPP only, while it should be cross-cutting on many directorates.

Our interpretation during our discussions with the responsible persons highlighted the following points:

- The directorates and officials who are directly involved in the implementation follow the development of activities at the peripheral level through the national RBF team that coordinates the daily implementation of activities. These are the DHIS and the Chief Accountant. For the first, this is done through the sharing of health information from this project and preparation of communications for its dissemination to the technical and financial partners. For the second, sending of results from health facilities is done quarterly for financial audits to be conducted prior to forwarding the payment request to the Ministry of Finance.

- The RBF team serves as a technical body for the daily monitoring of the implementation on behalf of the regulator/ MOHCDGEC. Other directorates than the DPP that were met have shown a limited involvement and information held on this project is very limited. Some like the Directorate of Quality Assurance, Directorate of Preventive Services were involved in the early stages of the elaboration of key documents. Since the launch of the pilot project, their involvement was very superficial hence the limited knowledge of the achievements.

#### The role of the RBF National Team

The RBF National Team is expected to play a decisive role for the success of RBF in the country. According to the project design document, the team is responsible for coordination, implementation, monitoring and evaluation of the RBF program.

This team consists of eight people including:

- RBF coordinator

- RBF administrator

- Verification officer

- Capacity building officer

- IEC officer

- Legal officer

- Supply chain officer

- Monitoring and evaluation officer

We found a team that is well organized; it prepares in advance its meetings, work sessions, training sessions and supervision visits. The team spirit looks good with an appropriate distribution of tasks and responsibilities within the team. Each RBF Team member has a job description and the tasks are well described.

Our analysis of the qualification profiles and roles assigned confirms that the team is multidisciplinary with complementary backgrounds.

The main weakness lies at the level of their previous experience with RBF implementation. Most of them did not have exposure to RBF until they joined the unit. At the date of our assessment, the staff in the unit had 6 to 10 months of experience with RBF.

During our discussions, members of the RBF team expressed the feeling they are not adequately prepared to lead the RBF project. They expressed the wish to follow more advanced training to better lead the implementation and further roll out of RBF in Tanzania.

One of the resource persons working closely with the RBF team realized that:

We have conducted some training but the team still needs more capacity building. I have advised them to take part in an international course on RBF. This could help them to understand the challenges coming with this kind of approach.

Our assessment is that in exercising their functions, the RBF national team staff rigorously apply what they have learned during the training. They do their best to follow the ongoing implementation process, such as the training of providers in the regions and districts that planned to launch the RBF pilot project.

Experience of RBF in others countries has shown that the RBF Unit should also work horizontally and upstream with different relevant directorates of MOHCDGEC. We have observed that it is done so in Tanzania – yet, this aspect could be strengthened.  The RBF National Team regularly organizes presentations to discuss the state of progress of the RBF project. This is done in the through the technical working groups. Presentations are also made at meetings of the RBF Steering Committee. Until now, two RBF Steering Committee meetings were held and exchanges on progress were made. However, actions of RBF National Team are often contained within the DPP, with limited collaboration of officials from other directorates such as DHIS and the Chief Accountant Office. We recommend the dynamics of collaboration with other directorates to be improved to increase their buy-in of RBF.

The RBF national team should act as a catalyst for sharing information more widely to facilitate exchanges and decision making from the lessons learned from implementation. This should pass through a proactive action of this team to take the lead in a dynamic exchange across sub-sector directorates for learning, monitoring and evaluation.

Downstream, the RBF National Team is supposed to closely follow the implementation in the pilot regions and districts and to provide technical guidance at all steps.

According to the RBF design document, the team is responsible for coordination, implementation, monitoring and evaluation of the RBF Program. A certain number of roles and responsibilities are assigned to that team. We analyzed each of them to assess how effectively they are conducted.

The detailed roles and responsibilities for the RBF national team, according to the project Design document, are:

- To take all the necessary technical, administrative, tactical and day-to-day running of the programme and operational decisions regarding the programme’s implementation, as well as overall coordination.

- To lead the design process for the RBF roll-out, coordinating inputs from all relevant stakeholders and ensuring consistency with existing health sector policies;

- Provide continuous technical assistance in the overall design and implementation, training, monitoring and evaluation, financial management, linkage with partners, contracting, and Independent validation;

- Ensure that all implementing stakeholders understand the RBF concept and are prepared for its implementation;

- Lead the Training of Trainers who will then conduct cascade training at different levels;

- To ensure districts have adequate data collection tools (HMIS) in time for implementation of the RBF program.

- On behalf of MOHCDGEC, to contract the purchaser and fund-holder;

- Develop, with relevant national and regional stakeholders, the necessary processes, deadlines, tools(contracts, reporting tools, verification tools), training materials and other job aides as necessary for the successful implementation of RBF;

- Provide on-going monitoring and evaluation of the program, with concrete action steps to follow in order to relieve bottlenecks, give targeted support to weak health facilities, build the capacity of CHMTs to appropriately support facility managers;

- Develop a detailed work plan and hold all stakeholders accountable for timely

implementation and delivery of results;

- Receive from the NHIF the list of facilities and payment amounts following verification and submit to the MoF for disbursement;

- Prepare an Annual PBF Report, summarizing progress in the year and conduct advocacy and education relevant to RBF.

- Ensure that training is carried out to roll out revised rules and procedures each year;

planning and budgeting process;

- Support the design and implementation of the impact evaluation component of the RBF, including undertaking operational research to understand what is working and what needs to be refined;

- Ensure that the Health Management Information System is programmed to provide the necessary functionality for implementation of the RBF;

- Share regular progress reports on the RBF roll-out through the Health Financing TWG;

The following paragraphs show the assessment of each role and responsibility assigned to it.

 Leading the design process

During our meetings, it was found that very few of the members of the RBF team have really participated in the RBF design process. Most of them actually arrived at the time of roll out. The fact of not having taken part in this process of design and coordination of inputs leaves some shortcomings in the dynamics of cooperation with other actors. To date, there is no real proactive dynamic to stimulate contribution from different actors. It would be desirable to strengthen the coaching of the RBF national team on how the interactions with others RBF stakeholders could be carried out so that the team changes the communication and information sharing strategies. The objective should be to ensure the best participation from the widest array of stakeholders.

Lead the Training of Trainers

At the initial stage, the RBF team took part in the preparation of the training of trainers but it didn’t lead it. The training was carried out by the RBF expert working as a technical assistant to the RBF National team and some people from academic institutions were recruited to play the role of trainers.

Now the RBF national team members are considered as trainers and they actively organize themselves for the training sequence to be conducted in different regions according to pre established plan. They strictly follow the training guidelines they used during the first training sessions at the national level.

However, the content of the training focused only on the operational aspects of RBF. We recommend to revise partly the content to ensure that key concepts and principles are well understood. Good clarification of concepts and their implication greatly assist implementation actors in order to stimulate entrepreneurial actions and competitive way of working. This has to go through the organization of new additional or refreshing training to adjust the given messages during the previous trainings.

This is reported by some members who noticed that need:

We need more capacity building. We may think we are well with what we have learned but some additional capacity building and training could help us to master the functions expected from our RBF National Team

Recommendation:

Strengthen the capacity of the RBF national team through advanced training on the RBF to make it an advocacy body to a big number of directorates, technical and financial partners but also to enable a genuine monitoring and evaluation of activities conducted at the regional and the councils’ level.

 Running of the programme, operational decisions and coordination.

From our discussions with key informants, it emerged that RBF National team coordinated the roll out of the project. It monitors the implementation of the RBF in pilot projects after preparing and taking part in sequences of staff training at different levels. The coordination of activities in the regions relies on the regional RBF Coordinator who is a RHMT resource person. The latter has only learned the RBF with the training conducted by the team from the central level and he was not exposed to RBF approaches before.

The RBF team complained of not receiving enough documented feedback and that the coordinator is left with a lot of different functions assigned by the RHMT.

This does not streamline collaboration and regular information sharing for the RBF to ask about the status of implementation on a daily basis.

The experience with RBF in other countries has showen that it is key to have a resource person at regional level. One of his tasks is to share the updated information with the national team on a regular basis.

In the case of Tanzania, a regional coordinator remains indispensable to serve as a focal person for the RBF national team. However, it would be best to find a unit outside the RHMT to avoid a conflict of interest. In addition, capacity building of this person at regional level is very indispensable to better document the lessons learned from the RBF and to exchange regularly with the RBF National team.

Continuous technical assistance in the overall design and implementation,

So far, we observe that the RBF national team takes part in the preparation of training for providers in the regions. It works closely with a pool of experts who have been recruited to conduct the training after receiving training administered by a RBF expert recruited as a consultant.

For monitoring and evaluation, the team tracks the evolution of results produced regularly. One oversight field visit has allowed him to realize the achievements on the ground. However, the RBF team is still in learning phase and does not yet ensure proper technical assistance.

A better exposure to the RBF national team activities and a good experience sharing through the RBF study tours in countries where similar units are experienced could help to integrate the different responsibilities in its operations.

Ensure stakeholders understand the RBF concept

From our discussions with the staff in Shinyanga region and Kishapu health district, it emerged that the staff of these structures is partly trained. Indeed, some people selected in the RHMT, CHMT, in health facilities were trained on the RBF by the National team but they  have not properly transmitted the information received to those who did not participate. Many staff members have a limited understanding of the RBF concept especially the requirements and implications of this approach. At the RHMT level, 5 persons out of 20 were trained while at the CHMT level it is 5 out 26.

The answer which comes when asked the meaning of the RBF, is that it's being paid on the basis of results produced. When probing on the requirements and implications of the reformers principles of RBF, answers become inaccurate especially for those who were not directly involved in the training provided by the national team.

The information sharing level between those who have been trained and those who have not is low. This becomes a weakness when the non trained staffs have to supervise and coach health facilities. A refresher training of staff at different levels is essential to prepare a good mastery of the RBF concept. This can be succeeded by adding modules explaining the rights and duties related to this new approach in health.

 Adequate data collection tools (HMIS) in time

Health districts use the existing HMIS as was desired by the MOHSW. The tool is already available and technicians that manage it have the required skills and knowledge for the job. A compilation of data is done at the council level and entered in the DHS2 format to be sent to the regional level where the RHMT will conduct a second compilation before sending it to the national level. All the quantity indicators have been integrated in the existing HMIS.  The routine data has been reported on a regular basis to the central level. Analyses are conducted by the RBF National team to see the trends in close collaboration with the HMIS directorate.

The HMIS existed even before the integration of RBF. Since the design phase, the HMIS was involved and no investments were driven by the RBF project to improve it. Since the launching of RBF, data is shared timely and there were no particular complaints about the data accuracy.

 Contract the purchaser and fund-holder;

The RBF team does not sign contract with the NHIF or with the MOF. So far no contract has been signed between the team and other hierarchical structures. A contract has been signed between the MOHSW and the NHIF and another one between NHIF and MOF.

For the RBF national team, only the hierarchical relationship defined by the MOHSW governs this unit and members are paid as Government officials. There is not yet a result- based contract signed with the RBF national team to make it more accountable to the DPP. This could be envisioned in the near future to strengthen the accountability commitment as it is seen in other countries implementing RBF.

Develop, the necessary processes, guidelines, tools training materials and other job aides as necessary for the successful implementation of RBF;

As mentioned for a higher function, the vast majority of members of the RBF national team  found all documents and tools, the training material and other job aides already prepared and they were trained on their application. However, some changes were suggested by this team when inconsistencies were observed. The RBF Steering Committee has to decide on it.

For example, the performance premium sharing provision for the health facilities staff is not very clear on the consideration of government employees or not. Guidelines on how performance payments should be divided among health workers should be made clearer. For example, some health facilities are sharing the individual bonuses only with the employees who are on the Government payroll while others are not.

The RBF team has also realized the RHMT is taking many responsibilities which cover the regulatory role but it is also playing the role of lead verifier. This has been discussed at the regional level for a better separation of functions but the RHMT claims this was one of its assignment defined by the RBF design document and the operational manual.

It is important to note that the process is still in its infant stage and numerous amendments to the tools and guidance documents come after a slightly longer time of implementation.

 On-going monitoring and evaluation

Monitoring and evaluation of the implementation is somehow conducted and the RBF national team works closely with the HMIS department to analyze the trends. The lack of field visits for supervision by the RBF national team nevertheless hinders the efficient work and rapid response that should follow the identification of bottlenecks to implementation.

 Work plan and accountability

The RBF team develops its workplan and activities to be carried out with specific timelines. During our visit, we found a training plan for providers in different regions who embrace the RBF. Responsible persons are designated for each type of activities to ensure some accountability. The RBF team is accountable to the Directorate for policy and planning.

The RBF national team faced some difficulties to carry out some field visits for supervision. Only one field supervision visit in Kishapu has been conducted since the beginning of the pilot project in April 2015.

Field actors such as RHMT and the CHMT and health facilities are accountable through regular reporting mechanism to benefit from RBF payment. Supervision is carried out at different levels to ensure proper application of the new rules of the game. The RHMT conduct supervision for CHMTs and the latter supervise the health facilities. Moreover, some RBF stakeholders are not yet involved to actually be accountable for the tasks assigned to them. These are the NHIF, the CAG, IAG whose actions are not yet implemented effectively. The reasons cited for the low involvement of these bodies are developed below.

The RBF National team produces an annual report where all the activities are mentioned as well as the achievements and challenges encountered. The recommendations are made to highlight the need of adjustments or corrective measures. These are presented to the RBF National Steering Committee for analysis and decision taking.

Reception of the list of facilities and payment amounts

Health facilities lists involved in the RBF are transmitted from regions via RHMT and PORALG to make the payment requests. The NHIF has so far signed contracts for the first year but no other functions have been exercised. This is a deviation from the operational manual especially that even this body was not really involved as a purchaser. Instead, it is the RHMT in collaboration with the PORALG which is responsible for the development of health facilities lists bearing results and payables. These lists are sent at the MOHSW for verification by the Permanent Secretary’s office before they are sent to the Chief Accountant's office for financial checking procedures.

From discussion had with the NHIF central team, it emerged that NHIF officials who have been trained at the beginning of the RBF project have left and the successors were neither trained nor aware of the normal functioning of the RBF system. The purchasing role was handled by the MOHCDGEC using a direct payment process in collaboration with the Bank of Tanzania.

Facilitate appropriate inclusion of RBF activities and resources in the annual district

planning and budgeting process;

The RBF national team has just started its interactions with pilot districts. A single supervisory training took place in a group of sampled health facilities. The Kishapu district was visited and technical supervision work has begun.

During our visit Kishapu, we found that the CHMT is organized to make a follow up on the RBF activities by conducting training supervision at health clinics and centers. However, the CHMT seems to lose basic activities for planning, monitoring and evaluation, report production. No plan or report produced by the CHMT was found on site. Moreover, the RBF project processes seem to grab a lot of attention since its launch at the expense of other programs that were there before. Indeed, CHMT team told us that: "supervisors make one visit per quarter per health center. It is often devoted to the supervision of health centers teams so they know well make report for the RBF. "The RBF national team needs to monitor activities at the regional and council levels to identify potential negative effects.  It is still necessary that the RBF national team be either directly or indirectly involved to ensure that effective strategies are chosen to improve performance products in field. This will go through a coaching job the regional RBF coordinator (or regional RBF task force) can make at regional and council levels level to enhance the capacities of CHMT. This will further integrate the RBF in all of their activities from health facilities.

 Design and implementation of the impact evaluation

The impact evaluation structure was not discussed in detail and the RBF national team did not discuss monitoring of its implementation. All the discussions we conducted at different levels have not tackle the impact assessment conducted at the Kishapu district.

Ensure that the Health Management Information System is programmed to provide the necessary functionality for implementation of the RBF;

Share regular progress reports on the RBF roll-out through the Health Financing TWG;

The RBF team works closely with the HMIS for data management and monitoring and evaluation. During our discussions with the HMIS leadership, it was meant that it was involved from the beginning in the situational analysis and the production of baseline data. To date, all data from the periphery are managed centrally. From there, the sharing is between the HMIS leadership and the RBF national team for dissemination to the technical and financial partners. This powers the sharing of information with Health Financing Technical Working Group.

Note however that the release made by the RBF team is limited to senior officials of RBF steering Committee and the HFTWG.

Experience in other countries such as Benin, Cameroon, Rwanda, Burundi made that the RBF National team which makes more dissemination of results even with partners who are not yet involved in RBF eventually to convince these latter to adopt the approach or at least be inspired to introduce this approach in their interventions.

Develop a capacity building plan,

Conflict resolution

The process is in its infancy and the RBF team is still in initial training. This is due to launch pilot projects in other regions such as Mwanza. At this stage, the training is based on the modules developed by the team of consultants in the initial phase of the RBF Kishapu project. The observed shortcomings will emerge from this process evaluation to initiate changes for better capacity building or conflict resolution between different institutions.

 Revision of  the scheme

The revision of the scheme is not yet part of the RBF National team activities at this stage of the project. For the responsibilities like the revision of the indicators, the targets or the prices, it is too early to assess so as the first steps on the selected indicators and the selected unit prices have not yet shown their hand results to see if the need for amendment is present. This is also the case for the  revision of the RBF Design Document . RBF's experience in Tanzania still needs more time to draw lessons that can influence the revision of design or how to conduct the regulation on the RBF.

This team has the regional RBF technical coordinator to liaise with the RHMT.

All information collected goes through this regional coordinator who is also an active RHMT member. He produces a summary report to be forwarded to RBF National team following the guidelines laid down by the latter. The team relies on the reports of the RBF Coordinator in Shinyanga region to conduct the analysis.

Our discussions with officials of the RBF national team found that the financial argument was advanced to explain the impossibility of conducting direct oversight in the Kishapu district. Since the launch of the pilot project in 2014, one field descent was conducted in the months of April-May 2016 by the RBF National team in the district.

In addition, the regional RBF coordinator was recently introduced to the RBF during cascade training. Some issues are still new to him. Discussions that we had with him showed that he discovered the new approach with the experience of Tanzania. Capacity building detailing the different components of the Regional coordinator’s actions could help much in the documentation of lessons learned to be shared with the National team. This has an impact on collaboration with RBF Team to inform about the effects on the health system at the regional level. This remains a weak point for the learning process and operational research. It also reduces the capacity RBF national team to conduct an appropriate follow up and an effective evaluation of quantitative and qualitative results of the RBF.

Recommendations:

- Create an entity at regional level to serve as a relay for the RBF National Unit to allow regular documentation and operational research. This can be a regional RBF Task force built within the RHMT. The latter will help identify gaps in an early way to transmit them rapidly at the national level for analysis and adjustments. This mechanism is implemented in many countries and it cannot be assured by a structure under an implementation contract as is the case for RHMT.

- Strengthen the involvement of various Directorates at the central level for the update on the progress of the implementation and their potential contribution in the future. This could increase the chances of institutional and technical sustainability when the country will build a full ownership of the approach with its integration into the existing technical directorates.

- Strengthen information sharing between the intermediate levels (regional) and peripheral (council) and the central level (RBF Unit) to draw lessons from the RBF implementation in the Tanzanian context. Financial, technical and human resources should be provided to these levels.

### Facilitator (PO-RALG and its deconcentrated bodies)

According to the project design document, a dedicated unit was supposed to be established at PO-RALG whose major role and responsibility was to facilitate and ensure that the Councils are supported to carry out their role with respect to health facilities.

Specific roles and responsibilities are as follows:

1. Providing sound advice to CHMTs and health facilities on how to plan to maximize the future revenue from RBF;

2. Support the development of health facility business plans;

3. Capacity building of CHMTs and health facilities;

4. Continuous follow up of RBF activities and results in order to improve future results;

5. Providing quality and timely information regarding health services provision in regions and LGAs to higher authorities;

6. Monitoring of health provision through the Regional Secretariats, represented by the RHMT on issues related to health;

7. Providing link, support and advice between regions, LGAs and all other health development partners to ensure health services provision are improved.

8. Liaise with the MOHSW to facilitate the selection of MSD SBUs to participate in the RBF scheme

It emerged from the group discussion with the central PORALG that many of these roles and responsibilities are carried out at the regional and council levels. The central team PORALG conducts supportive supervision to entities acting at the regional level. The reports coming from regions and councils are sent to the PORALG central level before sharing with the MOHCDGEC.

A department of health in PORALG has been put in place and strengthened with a dedicated team of 5 persons.

The latter took part in the design phase and they conduct a routine monitoring and evaluation of activities carried out in regions and councils.

A close collaboration with the MOHCDGEC through the RBF national team has been initiated and any changes needed in the implementation has to be analyzed by the PORALG department of health to see if nothing will disturb the smooth implementation of programs at the peripheral level.

Considering the various roles and responsibilities of the facilitator we conducted a grouping that can shed light on duplication observed in the field.

Indeed, for the responsibilities concerning:

1. Providing sound advice and Capacity building to CHMTs and health facilities

These responsibilities dedicated to PORALG facilitation unit are currently exercised by the RHMT. This takes the form of supportive supervision that RHMT conducts to support CHMT and capacity building done for the latter,

Indeed, the RHMT organizes field visits to see how CHMTs conduct their activities and organize health facilities supervision. With the Regional Administrative Secretary (RAS) support, the RHMT organizes meetings of the RBF regional committee whereby CHMT Representatives are invited to take the flow and give updates on the progress of the RBF implementation. However, this kind of framework for monitoring and evaluation are not yet formalized into a formal coordination means as is the case in other countries.

In countries such as Cameroon, Burundi, the implementation teams hold regular information sharing meetings which stand for monitoring and evaluation framework of the implementation. These meetings provide good opportunities to explore the challenges facing the implementation of RBF related to local realities. The body acting as a coach or technical supervisor takes these opportunities to make recommendations and give guidance for changes or corrections to current procedures, making it a dynamic and responsive approach to issues related to context. This should be done in close collaboration with the RBF National Team to better document the modifications.

One problem observed is that RHMT members were trained at the same time as those of CHMT reason why the RHMT has no technical influence over the CHMT. So it brings little added value of the advice and suggestions of corrections.

By analyzing other responsibilities assigned to PORALG as facilitator, we found that certain activities are conducted by the CHMT with very little coaching or external technical facilitation. These include the following responsibilities:

2. Support the development of health facility business plans;

4. Continuous follow up of RBF activities and results in order to improve future results;

5. Providing quality and timely information regarding health services provision in regions and LGAs to higher authorities;

Furthermore, these responsibilities relate to the technical activities and information sharing obligations, which should be easily done by bodies such as the RHMT as regional coordinating entity. This calls to mark a clear separation between the responsibilities which fall within the technical bodies such as RHMT and those that remain for the administrative structures as facilitation bodies. Both organs should establish frameworks of exchange to strengthen the monitoring and the sharing of information on the implementation of RBF in the region.

As for the responsibilities on the fact of:

7. Providing link, support and advice between regions, LGAs and all other health development partners to ensure health services provision are improved.

8. Liaise with the MOHSW to facilitate the selection of MSD SBUs to participate in the RBF scheme.

They are provided by the RAS which is helped by the RHMT, according to the Project design document.

Note that concerning responsibility for dealing with Monitoring of health provision through the Regional Secretariats, represented by the RHMT on issues related to health,

With that representation by the RHMT, there is some overlap of responsibilities which makes duties separation difficult.

Indeed, according to the project design document, the RAS is assisted by the Regional Medical Officer and Medical in-charge of the regional hospital. This provision puts in the same packet the regulation function exercised by the Regional Medical Officer (RMO) and facilitation function reserved to the RAS. The greatest complication comes when the RAS is cited as the responsible in chief for the verification function whereas he is the immediate superior of the IAG and RMO. This creates an ideal space for the conflict of interest due to much centralization of power in the hands of the RAS.

The RBF National team lodged in PORALG central level?

Considering that the PORALG central level straightly collaborates with the RHMTs and the structures at the councils level, one can wonder if to put the RBF national team in the PORALG central level wouldn’t be more efficient.

In fact, the RBF national team must straightly collaborate with the RBF implementation structures notably the RHMTs and the CHMTs to assure a close monitoring of the approach evolution in different country regions. The approach strengths and weaknesses discovered during the implementation must be documented and the adjustments decisions must be quickly taken so as to improve the strategy.

Locating the RBF National team in the PORALG central level could strengthen the close collaboration with the intermediate (RHMTs, CHMTs) and peripheral level (Health facilities).

Risk of accumulation of functions

This is still the RHMT that plays this role of monitoring health provision at regional level. This creates confusion about the roles to be played by RHMT and the separation of the functions of regulator and facilitator and auditor.

Indeed, the RHMT ends up with responsibilities for different functions in the RBF structure in Tanzania:

- As explained by earlier in the responsibilities of the regulator, the MOHSW to ensure compliance with the guidelines of health policy, strategic planning, coordination, supervision and monitoring - evaluation of interventions, it counts on the RHMT, giving to this structure a regulator role at the regional level.

- PORALG as facilitator says that the permanent secretariat for health who is his assistant in this sector is represented by the RHMT (see Project Design Document, ), which gives the RHMT the facilitation role.

- The project design document provides in addition a key role in the verification of data generated by health facilities.

These three functions that ought to be separate under the RBF are found accumulated with involvement at the forefront of RHMT, which increases the risk of conflict of interest and false reporting to beautify the health situation which is de facto RHMT responsibility.

According to the RBF design document, the roles of the Regional Secretariat, in addition to their roles as verifier outlined above, are as follows:

1. Co-ordinate and advise on implementation of health policy, health and social welfare matters in the region;

2. Facilitation of internal and external audits and verification to be undertaken within the region;

3. Supporting the RHMT for coordination of RBF at the district level;

4. Preparation of quarterly progress report to the MoHSW and PMORALG;

5. Monitor proper management of health services provided by public and private sector

hospitals and other health facilities in the Region;

6. Build the capacity of LGAs in health service delivery;

7. Provide technical advice on preparation of all health services plans, and assess Council health plans and interventions to strengthening health systems in the Region;

8. Provide backstopping support during health epidemics in the region;

9. Provide clinical services under Regional Hospitals to inpatients and outpatients referred to by LGA hospitals; for example on curative specialist services;

10. Provide expert/technical backstopping service to LGA hospitals and health centers during major communicable disease epidemics;

11. Provide referral laboratory services;

12. Coordinate availability of adequate pharmaceuticals products for the hospital and other health facilities;

13. Link between districts and central MoHSW in matters regarding standards and quality of health care both public and private;

14. Mobilize and allocate resources for health service provision to Region and LGAs;

15. Interprets policies into actions that can be implementable to specific LGA's in a region;

16. Documentation of challenges and success for problem solving and future planning;

17. Settlement of all disputes arising during the implementation of the RBF system.

These RAS responsibilities show a mixture of technical responsibilities and administrative missions. Apart from the coordination, other roles and responsibilities are not yet exercised as it should.

In other countries which apply the RBF, this facilitation function is not as highlighted as it is the case in Tanzania. However, administrative officials are regularly informed of the progress of activities through a partnership framework for the development and health at regional and central level. So they can bring their multifaceted support to technical bodies and the latter are accountable for harmonizing views interventions underway.

This provision could be replicated at the Council level to facilitate cooperation between the District Executive Director (DED) as administrative body and CHMT as technical control body.

The exchanges we had with stakeholders made us understand that The PORALG which is a central Ministry in the functioning of the Tanzanian administrative system. It is represented at regional level by the Regional Administrative Secretary (RAS) and the District Executive Director (DED) at the Council. The country has made some decentralization with many prerogatives given to the Councils.

As part of the RBF, the RAS has played the role of facilitation with obtaining for health facilities the opening of bank accounts while there still some reluctance coming from the Ministry of Finance. Health facilities currently hold bank accounts with selected signatories among staff and members of the Health Facility Government Committee. This confirms the will of decentralization by PORALG.

Up to now, the RBF project applies to one star and above dispensaries and health centers. The star zeros were not allowed to start the RBF. However the Government has allocated through the PORALG 10 million Tanzanian Shillings (Tsh)(5000USD) to enable them to improve some aspects related to infrastructure, equipment. This will pave the way to their reassessment to see if these facilities are ready to be included in the RBF project.

Recommendations:

- Formalize and institutionalize the information sharing frame which will include the national, the regional levels to discuss about successes and challenges on a regular basis in order to find quick adjustments  and solutions.

- Reinforce the training for the RHMT so that it can play a better supervisory and coaching role in the region.

- Mark a clear separation between the responsibilities which fall within the technical bodies such as RHMT and those that remain for the administrative structures as facilitation bodies

- Mark the clear separation of functions between the regulation/ Facilitation on one side and the verification role on the other side by appointing the NHIF as the verifier.

- Redefine the responsibilities with a better distribution of technical and administrative roles that avoids overlapping or duplication that may hinder or delay decisions.

- Create of a formal framework for information sharing at the regional level would be helpful to strengthen the monitoring of the progress of the RBF implementation

### Purchaser (NHIF)

According to the project design document, the National Health Insurance Fund was to be the Purchaser under the RBF system. The NHIF, with the MoF, MoHSW, and the PO-RALG were to enter into a Master Memorandum of Understanding for RBF implementation.

The NHIF roles and responsibilities include:

- To purchase health services from health facilities according to indicators set by the Regulator;

- To purchase supply chain services from MSD strategic business units according to set indicators set by the regulator;

- Entering into a contract with each participating health facility and MSD strategic business units;

- Participate in the verification process and approve payments after receiving verification reports;

- Prepare a full list of health facilities, health facility addresses, health facility bank accounts and verified payment amounts (including penalties) and initiate the payment process with the MOHSW for the health facilities and directly to MSD SBUs;

- Recommend to MoHSW necessary actions for any irregularities found during the

verification process, as highlighted to the NHIF by the IAG of the relevant region;

- Follow up with Ministry of Finance to ensure approved incentive is timely disbursed to the facilities.

The analysis of NHIF roles and responsibilities has enabled us to assess the degree of implementation of the powers entrusted to it. For each role or responsibility we dodge below the observations made during our evaluation meetings.

- Purchasing health services

The NHIF is not yet involved in the RBF implementation and the purchase of results as was desired by the initial structure.

According to accounts collected in the field, the NHIF was involved early in discussions about the functioning of the RBF system. It participated in the signature of the first contracts with health facilities and other implementation bodies like the RHMT and the CHMT. An annual contract was signed after developing the Business Plans, and the office of the NHIF central level was a signatory.

However, apart from signing a one year contract, NHIF did never play its role as a purchaser. The monitoring of contract was not carried out and it was not even aware of the content of the Business plans to ensure the adequacy with the contracts signed.

The roles and responsibilities were not clarified to know the distribution of power between the national and the regional NHIF offices.

Many of the roles which should be played by the NHIF on a quarterly basis were carried out by the MOHCDGEC directly.

Indeed, when health facilities produce results, they are verified by a Regional Health management Team (RHMT), NGOs, some NHIF staff from the regional office and representatives of local partners on a quarterly basis. A report is finalized by the RHMT and approved by the PORALG represented by the Regional Administrative Secretary (RAS). It is then sent to MOHCDGEC / RBF team for verification before submitting the reports to the Office of the Chief Accountant. The latter conducts audits on the reliability of documents and account information of health facilities. He prepares a request including payment request and details of the health facilities accounts in commercial banks. These requests are then sent to the Bank of Tanzania for payment. It then proceeds to transfer funds into these health facilities accounts directly.

Figure 1: Flow Charts – From Receipt of RBF Invoices to Payment of Incentives

This chart from the operational manual shows the level of involvement of the NHIF and the MOF in these invoicing and payment procedures. The reality found during our assessment appears not to use them as key RBF stakeholders. The following chart shows the actors involved.

Figure 2: the reality of flow Charts – from Receipt of RBF Invoices to Payment of Incentives

Health facilities

Summary form

Regional Identified Verification Team

DHIS2

CHMT

Notification by  RAS of the completion of the verification after the quarter

BOT disburses payment to HFs, CHMT, RHMT bank accounts

MOHSW

Full list of facilities and verified payment amounts

BOT

With that diagram illustrating the reality of payment flux, we can realize that the NHIF and the Finance Ministry don’t play the respective roles just like it is described by RBF project design document.

Within the MOHSW, the flux is described as follows:

Figure 3: Auditing flow and payment

RBF coordinator      Director of policy and Planning (DPP)        Chief Accountant         Examination

section

Permanent Secretary (PS)           Project accounting (Vouching)           Examination section

Bank of Tanzania

NMB( Facility account)

According to the chief accountant the whole process can take 3 days if all the signatories are available.  The question is if this duration can be maintained in the scale up phase.

Figure 4: Funds flow for RBF System

This chart from the RBF operational manual shows the involvement of the purchaser and the payer. This is not the case for the reality illustrated by the following chart.

Figure 5: the reality of Funds flow for RBF System

PROVIDERS

VERIFIER

RHMT is the lead verifier  and collaborates with NGOs, 2 NHIF resource persons

Document the results and generates data

Receive funds and sends confirmation of receipt to PORALG and MOHSW

PORALG/RAS confirms the list of facilities and amounts to be paid

BOT

Transfers funds to health facilities‘ bank accounts

REGULATOR

(Chief Accountant’s office )  Confirms funds to be disbursed to providers

Ultimately, we noticed that the purchaser (NHIF) does not play its role: it is not part of this process. The same thing is observed for the payer (MOF).

The NHIF regional team we met meant that it was never involved in the purchase of results. The only action in which it appears to have a role is verification. It sends two resource persons who have been trained on the verification to take part in this activity once a quarter. However even for this activity, their statements seem to show that they are especially involved in checking if the health facilities meet the requirements for the Community Health Fund (CHF) payment and not for the actual verification of RBF results.

A correction should be proposed at this level to really involve the NHIF and make it play a full role of purchaser. For practical reasons, the regional office would play this role to capitalize on its proximity to health facilities in the region.

When we asked why it is not sufficiently involved, actors met on the ground put forward the idea that the NHIF does not have enough qualified staff to fulfill this role in the health sector.

From the discussion that we’ve had with the central level NHIF team, it is noticed that the team that took part in the phase of project design was substituted and the information transmission on RBF was not well done to allow the new team take over. Nobody from the new team was informed on the RBF. The carried out attempts by that NHIF team to have further information on the RBF were unsuccessful. We were informed that between September 2015 and September 2016 no related activity to RBF was carried out the NHIF national office. It’s recently in October 2016 that they were invited to sign the new contracts that we found in the Director office.

The linkage between the contract and the business Plan

The contract is signed by the NHIF while the content of the Business Plan is analyzed by the CHMT. The latter, as a coach of dispensaries and health centers has under its responsibility the success or failure of health facilities under its control. This provision jeopardizes the contract negotiation logic that should occur between the provider and the results’ purchaser. The implementation as it is currently shows that instead of negotiations, the CHMT helps health facilities develop business plans each quarter. These business plans are kept at the CHMT and a copy is forwarded to the RHMT. The NHIF is not involved in the follow up of contracts and above all in the negotiation of business plan content.

Thus, CHMT is not in better position to negotiate performance improvements with some requirement while itself will be evaluated on the results achieved by the health facilities. CHMT will tend to place very low the benchmark to pretend to have achieved the objectives.

This activity should be fully ensured by the NHIF to ensure good quality of negotiations in line with the actual performance improvement. This negotiation should lead to an agreement on expected results to deserve payment. This assumes that the NHIF should have technically equipped people to conduct this kind of negotiation with the health facilities. Then it must regularly ensure payments meet the agreements set in the contract and that reflect the agreement on outcomes. Otherwise, there should not be any payment. This is not currently the case following the current assignment of roles and responsibilities between the NHIF and the CHMT.

The achievements of the health facilities should be followed up closely by the NHIF itself to ensure that the signed contracts are respected. This requires that the structure be strengthened at regional level to hold the resources and expertise necessary to perform this proximity function. In the present circumstances, it’s the national office that signed the contract but cannot follow the activities in regions without involving its regional sub-office. A certain decentralization of NHF is necessary to insure proximity follow up.

To purchase supply chain services from MSD

The initiation of the RBF on the medicines supply chain is in its initiation phase. The NHIF is not yet involved at this level as purchaser.

- Contract with health facility and MSD strategic business units;

The NHIF office of the central level has been engaged in the signing of an annual contract with the health facilities. However, it is not involved in regular monitoring of the results produced and their purchase. It does not participate in negotiation of the priorities to be set in the business plan to improve productivity of health facilities. This step is normally done prior to signing the contract.

This shows certain disconnect between the logic of developing the business plan and contract signing which is formality without any sense of commitment of the signatory parties. This leads us to question the importance of signing a contract if the signatories are not required to observe strict compliance with its provisions. The Tanzanian RBF model should return to the logic of conditionality to deserve RBF contract and regular monitoring of compliance with clauses to assess whether the payment is justified or not.

As do other countries, the signing of the contract is conditional on the Business Plan elaboration that shows how the beneficiary health facility can solve health problems in its catchment area. This contract means a commitment that if certain results are not achieved fully or partially the payment will not be made. The purchaser should have the appropriate resources and capacities to ensure verification of compliance with contract terms, these resources must be sufficient to ensure regular verification of quarterly data produced by the health facilities.

We propose a revision of the contract signing logic with a reduction of the contract period for 6 months in order to have a reasonable telescoping/overlapping between two quarterly Business Plans and this 6 month contract as what countries like Burundi do. This would help beneficiaries understand that if the results do not improve in six months, the contract will not be renewed. This provision would boost health facilities under contract to improve performance to deserve the next semester contract. The contract should not be taken for granted, it must be deserved and the recipient must know that the privilege of having a contract must be maintained by producing good results.

Note that this virtuous cycle of the Business Plan development, contract signing and payment of results must be maintained continuously to improve results.

- Participate in the verification process and approve payments

The only participation in the verification is the involvement of two agents of the Regional NHIF but the NHIF does not carry out the payments approval after receipt of the verification report. The real verification process is performed by the PORALG approving the report and sending it to the level of MOHSW for checking.

- Prepare a full list of health facilities, health facility addresses, health facility bank accounts and verified payment amounts

The RAS with the RHMT support perform the preparation of a full list of health facilities, health facility addresses, health facility bank accounts and verified payment amounts.  The list is sent to the MOHSW for a final checking. At the central level, it is the chief accountant's office in collaboration with the RBF National team who makes the final verifications before sending a payment request to the MOF.  The NHIF does not appear in the payment calculation process as was intended by the operational manual.

Accumulation of functions

Again, the RHMT and RAS perform many functions including the work that was reserved for other organs. This is probably due to the strong centralization of administration in the hands of the RAS that may hinder the separation of functions.

Recommendations to MoHCDGEC for necessary actions for any irregularities found during the verification process, as highlighted to the NHIF by the IAG of the relevant region;

The lack of action by the NHIF at different levels amputate the system a good separation of functions and leaves room to regional structures such as the RHMT and the RAS to do all the work. Currently there is no collaboration between the NHIF and the MOHCDGEC in the RBF; hence there prevails collaboration of MOHSW and RHMT which is already its collaborator and its representative at regional level. This increases further conflicts of interest due to an accumulation of functions at the RHMT level. The irregularities during the verification process could be detected by the RHMT but this could be hard to highlight and notify to MOHSW as the RHMT is the principal verifier. This creates a conflict of interest at the regional level.

Follow up with Ministry of Finance to ensure approved incentive is timely disbursed to the facilities.

The follow up with the MOF to ensure approved incentives is timely disbursed to facilities is occurring between the Office of the Chief Accountant and the MOF. The NHIF is not yet involved to play that role as purchaser with one of its tasks for the monitoring of payments at the MOF level.

Our discussions with members of the RBF national team allowed us to know that the NHIF will soon embrace its functions as described in the operational manual.

Recommendations:

- Ensure that the NHIF plays fully the role of purchaser as described in the project design document. This would help to improve the separation of functions.

- Strengthen the capacity of the NHIF in general and Regional NHIF in its role of negotiating outcomes to reach with health facilities. A signed contract requires knowledge and tracking of clauses contained in the Business Plan in order to assess the level of achievement prior to payment.

- Revise the attribution of roles between the NHIF and the CHMT in contract negotiation. This should happen between the provider and the purchaser and payment should be linked to a complete or partial achievement of expected results.

- Review the contract to dock on the strict monitoring of Business Plans for pushing providers to continuously improve their performance. Control mechanisms should be put in place to ensure that the content of the business plans is respected and that on the contrary case the contract must be stopped.

- Integrate in the quality verification checklist a component on the sharing of information with staff. This component will have the persuasive effect on the behavior of health facility managers vis-à-vis their employees or coworkers.

### Fund holder (MoF)

According to the RBF Design document, The Ministry of Finance (MoF) is the fund holder. It is responsible for paying the incentive to the providers (Health facility, CHMT and MSD Strategic Business Units) as directed by the Purchaser. There is two types of funds related to RBF system, namely Administrative and Incentive funds. The administrative funds will be channelled to the MoHSW and the incentive funds will be disbursed to the health care facilities via the respective Councils, and to MSD strategic business units.

The Purchaser initiates the payment process by communicating to the MoF the payments to be made. At the MoF, the Commissioner for Budget certifies that the funds are available, and the Accountant General makes the disbursement.

Specifically the fund holder will have the following responsibilities:

- To ensure that the design of the RBF disbursement and financial reporting processes are consistent with the Government of Tanzania financial management regulations.

- To disburse RBF funds for incentive to health facilities and MSD strategic business units, upon receipt of payment request from the Purchaser.

- To compile disbursement reports for each quarter through Epicor system.

- To share the disbursement schedules with NHIF, MOHSW and PMOLARG immediately after payments are affected.

The role of the Finance Ministry in PBF: Case of Burundi

The signing finance of the PBF on the State budget must respect the expenses chain circuit in all of its four phases such as the commitment, the liquidation, the ordering and the payment.

For that, the payment requirements of different health facilities, once transmitted to the Advisers of MOH, must take the commitment projects form. Firstly, those commitment projects are treated by the Inspector of Expenses Commitments (who’s an Agent of the Finance Ministry attached to the MOH MSPLS) who proceeds in budgetary control in checking:

- Good expenses imputation to the corresponding budgetary chapter;

- Credits availability on that chapter;

- Accuracy of the expenses calculation;

- Conformity of the planned commitment to the budgetary, financial and accountant regulations in force.

After having been controlled by the Inspector of Commitment Expenses, those commitment projects are signed by the Advisers of MOH and transmitted by the Directorate General for resources to the Finance Ministry under the commitment requirement form for suitable treatment. Those requirements must be committed, liquidated and ordered before their payment.

As matter of fact, the commitment and expenses liquidation done in the PBF context, just like any public expenses, will have to be done after having reassured that the relevant services are really fulfilled.

In this context, the commitment, the liquidation and the ordering of all expenses- this is to mean those that are operated in the FBP context on the public funds are under the responsibility of the Order Giver or of his/her representative.

The payment of the same expenses happens after the three steps (commitment, liquidation and ordering) will have been executed; and this task will be entrusted to the public accountant or an Agent by name appointed by him, acting under his control and responsibility.

That accountant must verify:

- That the received ordering is linked to an entire commitment and liquidation file and regularly constituted;

- That the credit is not deposed ;

- That no contrast is constituted ;

- That the payment will effectively attain the public debt.

The discussions we had with the stakeholders brought us to some preliminary findings about each responsibility.

- Ensuring that the design of the RBF disbursement and financial reporting processes are consistent with the Government of Tanzania financial management regulations.

The RBF funds payment to the health facilities was directly done to their bank accounts. However, from discussions carried out with the Finance Ministry, it seems that the authorities have not been involved in the process of RBF funds payment to the health facilities. According to a high authority encountered in October 2016, that approach is still new and the pilot experience was entirely carried out by the health Ministry. The Finance Ministry hasn’t played any role in the new project ever since. It is recently that they have started to acquaint with that new approach.  In accordance with the same high authority, it is too early to come for asking questions on the RBF implementation to our authorities for we haven’t actually played a role in that project and we haven’t taken part in any payment process for that project. If it is necessary to collect the information on the pilot project you should turn to the MOHCDGEC.

Since the launch of the pilot project, three payments have already been made to health facilities. Direct payments were done under the health ministry injunction and the transfers were done from the Bank Of Tanzania (BOT).

For the Kishapu District, the total amount paid for the three quarters is around 128 millions Tsh (64,000 USD). This however represents a small proportion of the ceiling amount as many facilities are far from the maximum to be earned per quarter.

After receiving requests from the office of the chief accountant, the MOF makes the necessary checks before transferring the funds to the bank accounts.

However, two concerns seem to hold the attention of many in the RBF actors we met:

- The health centers don’t have accountant status. In accordance with the regulations, they don’t have the right to hold the money paid by the government. This is presented as an obstacle and a potential risk in the case of mismanagement. . The accounting managers at the peripheral level are at the "ward" level. This level is the smallest administrative entity after the council. As a ward can have many health centers, there is the question of who will be responsible for monitoring the use of funds allocated to health facilities. .

According to the chief accountant, the MOF may consider giving this responsibility to the wards to manage money of health centers, which is contrary to the RBF spirit of giving autonomy in management of RBF funds to facilities. Note that in the meantime, health facilities manage the money but this decision was not taken by the MOF. A study was commissioned by the MOF to see whether the fund management responsibility could be kept in the health facility or not.

In the course of our meeting with Finance Ministry authorities, it was realized that they’re less informed on the RBF functioning. They declined questions that we asked them pointing to the fact that it is up to the health Ministry to respond them. The decision taking skill which authorized the health centers to have bank accounts remains scarcely known up to the present.

- Disbursing RBF funds for incentive to health facilities and MSD strategic business units, upon receipt of payment request from the Purchaser.

The MOHCDGEC pays directly RBF funds on the accounts of the health centers after receipt of the payment request sent by the Office of the Chief Accountant.

Note however that the chief accountant plays the role of "purchaser" on behalf of MOHSW which replace the NHIF for the moment. All the verifications that NHIF could have been doing are carried out by the Chief accountant’s office.

Some difficulties were inventoried during our discussions with the chief accountant. These include errors in the health facilities account numbers in the first and second payment of RBF funds. Some health center managers sent their personal accounts instead of transmitting the health facilities account numbers. Other health facilities had no accounts in commercial banks, which delayed their payment for the first two quarters.  These include health centers of Ngwajidalala dispensary and Masusante Dispensary. These centers have been regularized after completion of formalities for opening accounts according to RBF instructions. They received their payment from the third quarter.

It is worth noting that a late payment is still observed even after correction of these errors. Indeed, until now, health facilities have received payments for two quarters while they are at the  5.th implementation quarter. This shows that the payments do not yet meet the 60-day period between the verification and the arrival of funds on health facilities accounts. . A delay of 60 additional days has been observed. The first quarter covering April, May and June 2015 was paid in October 2015. The second one was paid in March 2016 instead of end November 2015.  In June 2016, the third quarter was not yet paid in health facilities accounts.

This whole payment process occurs in MOHCDGEC and the MOF has no influence on the steps. The details on the delays within the MOHCDGEC were not provided to know at which stage of the process the delays happen.

- Compiling disbursement reports for each quarter through Epicor system.

The compilation of payment reports is done at the Chief Accountant office but not the Finance Ministry.  The Epicor system was mentioned during our discussion with the accountant dedicated to the RBF project. According to her, that system is used to help health centers and hospitals to follow up the payments done.

- Sharing the disbursement schedules with NHIF, MOHSW and PMOLARG immediately after payments are affected.

The MOF having not played its role of Fund Holder in that RBF pilot project, it doesn’t share the payment plan with other structures. It is the MOHCDGEC, on its side, that takes in charge all the payment steps and holds every relevant information. The MOF, for this reason, doesn’t share information on payment for a simple reason that it doesn’t hold it at that project phase.

While meeting the NHIF, we realized that the information on the health structures payments doesn’t reach their level. The central level NHIF seems to be out of the system apart from having signed annual contracts with the implementation actors.

Nevertheless, a straight collaboration between the MOHCDGEC and the PORALG has been observed as far as the RBF implementation is concerned. However, information sharing on payments to health facilities was not particularly highlighted during our exchange.

### Provider / Health Facilities and MSD

According to the  RBF design document, both public and private health facilities at primary health care level are contracted for providing health care services to the community. These include dispensaries, health centers and hospitals at Council level.

The eligibility criteria for health facilities were developed under the Big Results Now (BRN) initiative. They include infrastructure, equipment and availability of qualified staff. Importantly, a health facility should be rated as one star or above to be involved in the RBF. A total of 46 health facilities have been selected as one or two stars. Only 2 facilities out of 46 are rated two stars. Each of these health facilities have benefited from the Start Up Fund of 10 million Tsh to carry out renovation work and put in place minimum equipment to ensure good quality of care. Among them twelve health facilities have been sampled to be visited during our visit in Kishapu health district. These include the Kahama Hospital which was retained even if it is not in the Kishapu district. This is because the district hospital was not functioning during the star rating period. Zero star facilities were included in the upgrade program with an investment of 10 millions Tsh (5000 USD) per facility to enable them to prepare for subsequent reassessment.

According to the Project Design document, providers are responsible for the following:

- Provide quality health care services to clients and communities.

- Develop clear business plan as part of the CCHP.

- Ensure that all clinical and crosscutting quality standards are observed.

- Prepare reports including HMIS reports, financial and technical report of the business plans.

- Collection, analysis, report and utilization of data for planning

- Collaborate with other key stakeholders and develop strategies for successful

implementation of RBF, this also includes leveraging of resources

- Mobilize resources based on available opportunities in the catchments areas.

- Develop or improve system for feedback mechanism to address clients complains.

- Develop capacity building plan that includes meeting, on job training, and mentorship

- program within the team.

- Ensure that all the resources are properly and efficiently utilized,

- Prepare and submit to the respective Council the RBF implementation and incentives

utilization report

- Ensure availability of reporting tools to facilitate data submission to higher level,

- Make sure that all necessary documents are accessible to verification and assessment,

- Report any fraud committed at the Health Facility to the R-RBFC (in writing) via CHMT,

- Implement sanctions against individuals responsible for professional misconduct,

- Support Community actors to carry out their own strategies under the RBF system;

- Lodge a complaint to the regulator via Council in an event of a dispute during the

.

Overall, it appears that providers are successfully carrying out their functions under RBF. However, there still important challenges, which need to be addressed prior to scale-up. These are described in detail under each function.

Business plan and quality health care services

The health care providers are dispensaries, health centers and hospitals which are in the Kishapu health district. Their selected staff received training on the fundamentals of the RBF and its operational requirements for successful implementation. Only health facilities rated of one star and above on the Big Results Now criteria are considered by the RBF project.  To build a Business Plan, Health facilities are required to conduct a situational analysis to identify the most important health problems to contend with. Indicators on major health problems have been identified and put into the project design document with prioritization of those the RBF will purchase.

At this stage of the pilot project implementation, health facilities develop a Quarterly Business Plan that summarizes the health issues they will tackle in connection with the indicators identified by the RBF project. A form is provided to guide a proper filling of various aspects to be improved. They establish the strategies to be implemented to improve productivity of the center and the quality of services provided to the population.

All health facilities visited have developed the business plans for all quarters, except the Kahama Hospital that has developed the business plan only for the first quarter. These Business Plans have served as a roadmap for activities during the concerned quarter. However, in some health centers as Kishapu health center, staff is not aware of the content of the Business Plan. The responsible completes alone and this creates friction between him and the center staff.

In this business plan elaboration, health facilities are supported by the CHMT which provides technical coaching and supervision work of the activities during the quarter. The quarterly Business plan is aligned to an annual contract between the health facility and the NHIF. The principle is that the payment of RBF subsidies done on the basis of achieved results and in proportion to the quality of service provided.

The volume of activity is gradually increasing with indicators improving for the vast majority of Kishapu health facilities. This is proven by an increase in funds earned by these structures from one quarter to another. The budget consumption rates are respectively of 11,3 % for first quarter, 15,7% for the second and, 21,2% for the third quarter. The quality of services is improved mainly the structural quality which was boosted by BRN funds that have been paid. These funds have allowed for renovations of clinics, purchase of laboratory equipment, maternity kits, rehabilitation or construction of incinerators.

Note that the coaching work needs to be strengthened to enhance the level of service quality standards offered in health facilities. In addition, collaboration with community health workers remains less controlled by both health center teams and CHMT members. Awareness raising and community mobilization actions for service users remain little undertaken.

Structuring the coaching role

The CHMT of Kishapu took the initiative to appoint supervisors who have to spend all they can in improving the performance of each health facility. A system of "Guardians" makes that each CHMT member must deal with coaching and monitoring of a limited number of dispensaries and health centers. This allowed namely improved reporting and data management with gradual increase of the amounts earned.

However, it is worth noting that the skills found in CHMT accuse weaknesses in the supervisory capacity especially when it comes to provide coaching on the choice of strategies to increase the services utilization. These strategies, which must relate to the improvement of the quality of services and outreach community mobilization, require further strengthening of the CHMT capabilities to ensure more efficiency.

The oversight that CHMT brings to health centers focuses on the data consolidation to benefit from RBF subsidies and spends less RBF strategies for increasing the services utilization. This suggests that coaching can be turned into a make-up of data to benefit from RBF subsidies in some health facilities especially since the exercise is to see if the results meet the RBF directives and requirements. Some supervisors argue that this is to help health facilities to not lose RBF money.

.Case of Kahama Hospital

Kahama hospital has prepared a single business plan for the first quarter of implementation. Since then the funds that have been paid on their account could not be used due to a misunderstanding between the management of the Hospital and DED office related to planned investments.

Indeed, DED rejects the proposal of the management of the hospital which wants to recruit workers to rehabilitate the incinerator without going through the public procurement procedures. The hospital suspected that these procedures will be costly and take too long to achieve. In addition, the hospital's officials are frustrated that the DED does not allow them to have access to their account to withdraw funds.

Since the beginning of the project, Kahama Hospital has no longer developed business plan claiming that it has no access to resources for implementation. However, the RBF subsidies continued to be paid quarterly on the hospital’s bank account.

This shows that the place and importance of the Business Plan were not well understood and its relationship to the contract that the health facility has signed. If similar cases go unnoticed, it means that the Business Plan has no relevance in the implementation of the RBF in Tanzania.

Reporting and Data management.

At the end of each quarter, a health facility prepares the HMIS report it sends to CHMT which in turn sends a consolidated HMIS report of the council at the RHMT. This report serves as a trigger for the verification team which is preparing to come see if these results are reliable or not. Health facilities keep the supporting documents they share with the CHMT members as supporting documents for the sake of expenditures proof in the quarter.

A quarterly activity report reflecting the Business Plan implementation level is generated. At the CHMT level, the data are compiled in an HMIS database before being sent to the regional level. However, the analysis capabilities of these data for use in planning require strengthening. Kishapu CHMT didn’t present any plan that shows the activities that have been prioritized for the last quarters.

- Collaboration and mobilization of resources in the catchment area.

During the situational analysis and preparation of the business plan, the health facility is required to take into account the resources available in its catchment area of ​​responsibility to capitalize in the strategies choice. A Business Plan elaboration Guide was provided to help providers in this exercise.

During our field visits, we found that these concepts of collaboration and mobilization of resources are a little blurry for most providers and this exercise is new. It requires more explanation and capacity building to ensure consistency. Talking about resources for many of the providers, resources are the infrastructure, the drugs, human resources and financial resources. There remains a facility - centered vision and the notion of resources is often limited to skills and equipment that a health center or clinic possesses.

This shortcoming can also be seen in CHMT members who play the role of coach. A dynamic of centrifugal action should be encouraged with more outreach strategies to reach beneficiaries especially in more remote areas. The collaboration with the community health workers should be strengthened for a better service utilization.

- Feedback mechanism to address clients complains.

Health facilities undergo verification of the reported results and a sample of patients who have used the services is taken to conduct verification at community level. The latter includes the verification of the existence of the patient, checking compliance of the declared service delivery and the satisfaction survey of service users. This last component gives a feedback to the concerned health facilities so they consider user complaints to rectify the criticized practices and reinforce good practices appreciated.

During our visits in health centers, we have not found any written feedback made by the verification team in order to encourage providers to change their way of caring patients.

Community verification and sub-contracting the CBOs

The RBF design document and the operational manual advocated the use of local NGOs which would sign sub contracts to conduct Community verification. However, the verification team chose to conduct this activity using its own agents with the collaboration of the Community Health workers (CHW)

In other countries applying the RBF like Rwanda, Burundi, Cameroon the community verification is conducted by Community Based Organizations (CBOs). They carry out patients’ tracing in the households and evaluate patients’ satisfaction level. The report is then sent to the verification structure.

The results of community verification are used by service purchasers to make a feedback to respective health facilities. The weaknesses pointed out by the community are signaled to the concerned health facilities for correction and positive actions are encouraged. Suitable strategies must be put in the business plan of the following term for weaknesses remediation.

Capacity building plan

At this stage of the RBF implementation, health facilities do not develop capacity building plan. The teams are still in the stage of learning to understand the RBF foundamentals. This quest for improvement stimulates initiatives that may be valued differently but they are not yet at the stage of development of the capacity building plan. Nevertheless, the team members in some health facilities organize meetings to share the strengths, weaknesses, opportunities and Threats in order to think about appropriate strategies to handle them. The facility teams are having meetings with community health workers to synergize their initiatives but it is still a new learning process not well handled by the coaching agents.

The guidance they receive from CHMT is in its infancy and also requires capacity building for better control of public health and community health issues.

- Efficiency in resources  utilization

After data verification and validation by MOHSW and MOF structures, payment is made directly into an account of the dispensary or health center. The use of these funds starts with an expression of needs by the health center team which is presented to Health Facility Governing Committee (HFGC) with deemed sufficient justification. The HFGC approves by signing the Minutes of the meeting held at the health center. The Minutes must be attached to the check and the needs expression document to be presented to the office of Council Medical Officer for expenditure approval and authorization of the Bank's cash withdrawal. Two persons, namely a representative of the health center staff and a representative of the HFGC, come to the Council to solicit the permission of the Bank's cash withdrawal. The Council Medical Officer, after verification of the documents prepared, then sign on the statement of needs document and thus the two envoys of the Health Center can withdraw money. These procedures are expected to increase transparency in the allocation of resources by the health centers.

Health facilities receive the amounts earned in all but delays still occur as the average length of payment is 120 days while operational manual stipulates 60 days for payment procedures. Indeed, the first payments were delayed following the bank details of the health facilities that had errors. Corrections procedures took time and resulted in a delay of 60days. The payment for the first quarter covering the period from April to June 2015 was done in October 2015.

Though, the known errors to have occasioned the payment delay for the first term were corrected, the payment delay went on for subsequent term without clearly presented reasons.

For the second quarter the payment was issued in March 2016 instead of November 2016. The payment for the third quarter was in process when we visited the Health facilities in June 2016. It was supposed to be issued in February 2016.

A quarterly maximum amount has been decided for each health facility category. For dispensaries, health centers and district hospitals, ceilings amounts are respectively 4,961,674Tsh(2500 USD), 19,900,459Tsh (10000 USD) 71,405,166 tsh (35702 USD)

The proportion of RBF funds is high when compared to all funds received by health facilities from three sources (RBF, CHF, user fees). In some  health facilities where we found financial data available, the proportion of RBF funds is around 80% of the total amount directly managed  per quarter. This is the case for Somagedi dispensary where the average funds from CHF and User fees was 190 750 Tsh (95 USD) and the RBF funds were 858851 Tsh (429 USD) for the third quarter.  The other sources of funds are managed by the councils and the allocation proportions to each facility couldn’t be determined during our assessment visits.

When we consider the amount earned by health centres and dispensaries, the budget consumption rate is still low but it is increasing from one quarter to another. From the first to the third quarter, the budget consumption rates are respectively of 11,3 %, 15,7%, 21,2%. The total ceiling amount per quarter is 270 Millions Tsh (135,000 USD) and the earned amounts are 30397419 Tsh (15,198 USD) for the first quarter, 42637323 Tsh (21,318 USD) for the second quarter and 57314546 Tsh (28657 USD) for the third quarter. These rates take into consideration 45 health facilities of Kishapu health district excluding the Kahama district hospital.

The resources of health facilities are managed following RBF funds management guidelines. Officials are gradually learning to independently manage the resources entrusted to them. The RBF funds are used by health facilities following the guidelines in the procedures manual regarding investments and sharing incentive bonus for staff.

The mechanisms in place to ensure transparency in the allocation of funds within the facility are:

- For expenditure for the center operation or for investment, 75% of RBF funds should be allocated. Health staff must establish the needs and costs related to them. This information should be presented and explained to the Health Facility Government Committee for approval. Once obtained, two agents of the health center must provide the minutes of the staff meeting with HFGC, the state needs and a bank check at the Council for to seek approval of the DMO. The latter must authorize with his signature on the document showing the expenditure. These agents may go to the Bank with the check to get the money in cash and go make expenditures.

- For the staff incentive bonuses, 25% of RBF funds can be allocated to it. Indeed, after having removed the incentive fees for community workers who collaborated with the health centers, staff must share the funds allocated to incentive bonuses. As suggested by the project operational manual, the criteria followed are responsibility and attendance for each employee.

Note however that inconsistencies were observed in some health facilities. Some structures take into account only the staff that is read on the government's payroll (civil servants) and excluded contractuals of the structure. This is illogical because all staff helps in improving the productivity of the award-winning health facility. In addition, this criteria can be dangerous because it threatens the cohesion and teamwork in the relevant structures. This should be harmonized.

The experience observed in other countries like Cameroon is that even non-Government employees earn RBF bonuses because they contribute to the facility productivity. Some experiences of countries which didn’t include them saw some team spirit broken and a high level of demotivation for those who are not paid. The case of the pilot project in Liberia was illustrative.

The health facility team doesn’t present the bonus utilization report to the CHMT. This is considered as part of the autonomy of management in many countries as they don’t want the district level to micromanage the health centers and dispensaries. However, the auditing is allowed to the regulator to check all the financial documents for more transparency.

Capacity building in resources allocation

This dynamic of efficient allocation of resources also requires technical supervision which is based on the specificities of each catchment area by conducting a combined analysis of service needs of the population served; the behavioral aspects in the search for care and capacity of the health facility to meet the demand for care. A technical capacity building of CHMT on coaching and resources allocation is necessary to improve the supervision of health facilities.

- There is no mention of the financial reserves kept in the account of the health facility to ensure the security funds in case of late payment. It is the same for the use of the indices tool that is not mentioned in the operation of provider structures. Both provisions are used in other countries respectively to provide some financial security in case of delays in payment of funds and to increase transparency in the use of funds from these structures.

Sources of funds and reporting

The Health facilities are receiving in their bank accounts funds from the following sources :

- Cost Sharing (user fees),

- Drug revolving fund,

- Payments of RBF subsidies,

- National Health Insurance Fund,

- Community Health Insurance fund,

The funds received from those sources are put into a common account and use does not separate the RBF funds from other sources. These are directly controlled by the facility in charge and Health facility government committee with approval of the DED.

For the external sources, the RBF operational manual states that external sources are:

- Block and Development Grants,

- Personal Emoluments (PE), Other Changes (OC),

- Development Partners and Basket Funds or bilaterally ( e.g. USAID, EGPAF, etc).

- Receipts in Kind: donated food, linen, mosquito nets, etc

- Community contributions, often towards construction, rehabilitations etc

Under the current setting health centres and dispensaries fall under the authority of local government authorities (LGAs):

- Salaries of the health personnel are channelled directly from the MoF to the DED office and pay the staff  through theirs banks accounts.

- Funds for drugs, which represent the biggest share of non-salary expenditure, are under the direct responsibility of the MoH. On a monthly basis, the MoH transfers money to the Medical Stores Department and the facilities get their supplies from MSD.

- At the level of the municipalities, there exists a so called "account No. 6" for health issues. In this account central government allocations (i.e Block Development Grant, Other charges and) and Basket fund are all pooled in this account. The account is directly controlled by the DED, Facilities are required to submit their needs/budgets to the DED through DMO to get access to these fund.

Conclusively, there is no actual cash transfer from the External sources going directly to the facility. Facilities are regarded at subsections of the health department at council level.

RBF expenditures are reported separately from other sources of funds. This is because RBF is considered a project. In few facilities it was reported together with the cost sharing money i.e NHIF, CHF and user fees. However, this was only for incomings and not expenditures. Generally, the acquisition process is clear but the reporting on the use of RBF is not clear.

During our assessment visits, the RBF Funds were reported separately, because RBF was not included in the budget. For Financial year 2016/17, RBF is included in the Budget. This gives an indication it will be reported with other funding mechanisms.

The barriers for the use of the health facility funds are mostly related to the requirement to seek permissions at the Council before withdrawing money or incurring expenses. This was illustrated by the case of Kahama Hospital which had blockages at the office of the DMO and the DED office. The latter required the hospital to follow public procurement procedures which are expensive and take a long time to complete. This created a standoff between the hospital authorities and the office of DED. The latter denies any withdrawal of money by the management of the Hospital for investments, which is an obstacle to the management autonomy for providers advocated by the RBF.

Note that the RBF operational manual states that the opening of Bank account should be done according to the government financial procedures and regulations.

However, the DED office allowed withdrawals for the share allocated to the premiums of staff motivation. This interference in the functioning of the hospital showed the hospital's dependence on decisions taken by the Office of DMO and the DED. Those decisions are based on existing procedures in Tanzania for the award of public contracts. They update the power issues associated with existing administrative links and the potential influence peddling and conflicts of interest that implies. For the purchase of medicines and other consumables, authorization of the DMO should be given to go to replenish stocks  from other wholesale accredited pharmacies. This is done only when the MSD faces stock-outs of drugs. The latter are often noted once at the MSD Mwanza as the information about medicines is not shared in advance. This increases the expenses of health facilities whereas they could replenish their stocks directly from the closest accredited pharmacies.

Another barrier has been noticed when the in charge of dispensaries or health centers monopolize information on RBF funds paid. As a result, there is lack of transparency on the management of these funds, where employees are not aware that the RBF funds have been paid to the health facility account. This was observed in the Kishapu health center.

 Data reporting

Healthcare providers are gradually getting accustomed to the RBF dynamics and this is reflected in improved data reporting. While supervision visits remain insufficient (One visit per quarter per health center on average), they help to better complete the records and financial documents. The quality of reporting generally improves from one quarter to another as reported by the RBF national team data. However a more heightened vigilance should be kept to ensure that the coaching sessions do not turn into data manipulation game to deserve RBF payments.

Indeed, in the speech of CHMT members, it appeared that the "guardians" go to clinics and health centers to "help to prepare the data to avoid losing RBF money". This recalls an attempt repeatedly observed in other countries applying RBF and trying to present clean data to capture the RBF payments for fear of having a large margin of error that would cause them lose their money. The risk with this is that the data transmitted at the HMIS does not reflect the total number of cases received at the health facility. The transmitted data becomes only cases that meet the RBF definitions. This biased cleaning is detrimental to the health information system and this is even more dangerous for a country that begins immediately with a single integrated tool for health data collection as is the case for Tanzania.

The innovating idea to set up the “Guardians”

The “guardians” are supervisors, members of CHMT who are appointed for closely and specifically monitoring a well determined number of health centers to help them improve their productivity..

This initiative was stimulated by the RBF introduction. It allowed those supervisors to strengthen formative supervisions so that the improvement logic of results is deeply understood. This aims at strengthening the collaboration links between the CHMT and the health centers under its supervision so as to supervise them in this new approach. Every guardian is held accountable of the successes or failures recorded by health centers under his/her supervision.

- Verification tools and documents

Registers and other useful audit documents are prepared in advance. They are presented to verification teams for analysis after each quarter with regard to the quantitative data. Case definitions are applied to count the number of patients received in a health facility. Unit costs are applied to calculate the amount of money gained.

For the quality, visits are conducted by verification teams accompanied by staff of the visited structure. The quality checklist is applied for quality verification and scores are attributed.

The verification team finds the tools useful and easy to follow after having being trained on that activity. The team incorporated clinical staffs from the Shinyanga hospital to deal with some clinical components of the quality checklists.

- Report any fraud and sanctions

At present, cases of fraud linked to the data manipulation are not yet reported and sanctions have not been seen.

Note that this kind of fraud emerges as people better understand the RBF system. The RBF national team in collaboration with the RBF regional coordination teams needs to remain vigilant to these possibilities to develop technical guidelines consistently.

The only sanction applied at this stage for erroneous reporting is the loss of earned income. In Tanzania, as in other countries, any error equal or greater than 10% in each indicator is subjected to penalty of that percentage of the earned amount in that particular indicator. Example the facility had earned 3000 for a certain indicator and it was found to have 15% error in that indicator; hence the earning in that indicator will be 3000 – (15% of 3000) which will be 2550 instead of 3000. Penalty has been introduced in RBF system so as to reduce errors in reporting data and hence improve quality of data.

- Support Community actors

Health facilities are working with community workers to raise awareness and mobilize communities for better service provision. Some examples are cited in connection with community health workers who accompany pregnant women to give birth in health centers, Traditional Birth Attendants (TBAs) who refer and accompany pregnant women to give birth in a health center, community workers who raise households’ awareness to bring children for vaccination, etc.

Meetings with community workers are held in health centers to discuss ways to improve the services provision. These community workers are paid on RBF funds taking into account the number of services to which they actively participated.

There are not yet identified specific complaints at this stage although in some health centers, community workers have not received their pay.

Recommendations:

- Revise the training content to include modules explaining the RBF principles and good practices. This will enable actors to know the limits of each other in terms of  separation of duties or other good practices that make the RBF the most efficient.

- Remove the requirement for officers to have to travel long distances involving expenses to seek the DMO approval for every single expense incurred at the care center. This causes unnecessary costs and time for these centers which already suffer from limited human and financial resources.

- Reinforce expenditure audit activities of health facilities by the Internal auditor General services

- Introduce the use of index tool to improve the good funds allocation in health facilities with the initiation of financial reserve funds.

- Allow effective autonomy of management by removing requirement for seeking approval for any expense by the DMO and the DED. Management transparency and accountability should be improved to through reinforcement of audit of incurred expenses to see if they comply with the directives given by the regulatory services.

- Remove that conditionality of purchasing medicines from the MSD and allow health centers to replenish their stocks from the closest registered pharmacies. This will reduce unnecessary expenses related to the procurement processes.

- Increase competitiveness within the medicines sector by pushing the MSD to open branches in Shinyanga region and even in Kishapu district.

### Verifier  (IAG)

According to the project design document, the internal verifier is the Internal Auditor general (IAG) with involvement of experts from the region. He identifies a verification team using the existing capacity in the region including RHMT, NHIF staff, Regional Hospital, NGOs, Internal Auditors and other experts to undertake the verification.

Experts from the purchaser NHIF at the regional level are in order that the NHIF be confident in the results of verification. The identified verification team conducts verification of results for dispensaries, health centers and hospitals.

Furthermore the team conducts patient tracing for 10% of clients registered to have received services in the facility, which also checks for patient satisfaction for the selected indicator. Patient satisfaction is assessed through a separate developed checklist; however the score is finally incorporated in the overall quality score.

The independent verifier will be the Controller Auditor General (CAG) who will conduct the expert counter-verification twice a year, using a sample of 25% of facilities at that time participating in RBF. The independent verifier will counter-verify quantity results as verified by the IAG of each region and will conduct a quality assessment using the in-force quality checklist.

The roles and responsibilities of verifiers are the following:

- Verify and counter verify the results reported by the provider;

- Check correctness and consistency of data entered into HMIS tools and DHIS2;

- Check whether minimum quality standards of service provision in health facilities are met;

- Provide timely feedback to providers, purchaser and regulator on the quality of services basing on agreed indicators;

- Advice the regulator, purchaser and providers on issues of service coverage and quality of care depending on the verification results;

- Report the verified results to the purchaser.

- Conduct patient tracing and client satisfaction survey;

Those roles and responsibilities guided us to check if the verification was conducted as prescribed in the operational manual and the RBF design document.

- Verification of the results reported by the provider;

According to the operational manual, the internal verification is conducted by the Internal Auditor General who is assisted by the RHMT, the NGOs, the NHIF. But in reality the leadership was taken by the RHMT which involved regional NHIF officers and recruits from hospitals. The latter been involved in order to get the staff who have medical skills.

The verification team works under the authority of the RAS representing the PORALG. The Internal Auditor General (IAG) who is also under the authority of the RAS didn’t perform his function of chief verifier. Since the beginning of the RBF pilot project, the IAG took part in a single internal verification activity which was his first involvement. The RHMT owned the chief verifier’s function.

For resource availability reasons, the RHMT prepares and organizes the verification visits for health centers, clinics and hospitals. This activity takes about 15 days to cover the health structures of Kishapu district, The RHMT team is strengthened by co-opted agents from the Regional Hospital, the NHIF and NGOs which want to join the team. It is divided into 3 groups including one that makes quality verification at dispensaries and health centers, a group that monitors the quality at clinics and CDS and a third group involved in the quantitative and qualitative verification at the Kahama hospital. The verification team is made of 20 persons.

The internal verification was conducted on a regular basis since the launching of the pilot project in kishapu. The verification results have been forwarded to PORALG for validation before sending reports to the MOHSW.

The actors involved in the verification activities have an understanding of verification tasks. They come up with explanation on the conduct of verification sessions and seem to understand the dynamics of collaboration with the staff of the visited structure to capitalize on lessons learned from this activity.

A budget of 61 millions Tsh (30500USD) is allocated to that activity each quarter and it is managed by the RHMT.

Indeed, one of the RHMT members said:

We are receiving funds  from the RBF headquarter which are specific for verification. This is from the Ministry of Finance but it is done in collaboration with the Ministry of Health. Sixty one Millions for the period of January to March 2016 for the Kishapu disctrict Council, Msalala District Council, Shinyanga District Council, Shinyanga Municipal council, Kahama Town Council and Ushetu District Council. This is used to pay perdiems for verifiers, fuel and car maintenance, transport.

The data collected in health facilities are analyzed and used to calculate bonuses for quantity and quality. The results are recorded in a report that will be shared with the RBF Regional Committee for approval. This report will then be sent to MOHSW for verification before submission to the chief accountant and the MOF for subsidies payment to health facilities.

Community verification is done by the same verification team whose agents sample 10% of patients who used the services in health centers. These agents work with community workers to identify households of these patients.

- Checking correctness and consistency of data entered into HMIS tools and DHIS2;

Verification of quantitative data is based on data generated at health centers and dispensaries. This data is compiled to be entered into the DHIS2 tool adopted by MOHSW for better reporting harmonization. Before entering data in that tool, the verification team has to check correctness and consistency and validate it.

- Checking quality standards

The quality verification group ensures that the quality indicators allow the health care improvement. Quality checklists developed for this purpose are used to assess the level of quality in health facilities. After that verification, a score is calculated. That score will be multiplied by the quantity score to calculate the payment amount. The percentage of the quality score will give the proportion of the amount to be paid which is calculated based on the quantity output.

For the regulatory entities (RHMT, CHMT), only the quality checklists are applied and scores are calculated.

- Feedback to providers, purchaser and regulator

The verification activity is conducted in collaboration with the health facility staffs. They learn from their successes and errors to improve during the next quarters. At the end of the verification session, a meeting is organized within the health facility to give a feedback to the staffs. This feedback highlights the strengths which made the facility to gain money and the shortcomings which made them lose some points. .

According to the project design document, feedback should be given to the purchaser so that he purchases the results and prepares a request for payment to the MOF. This feedback should also be made to the regulator to know the status of the implementation.

However, two difficulties were identified:

- Feedback to purchaser

With the dissociation between the verifier and the purchaser, the project should strengthen the collaboration between the verification team and the purchaser who must share verification data. The idea of ​​sending NHIF expert to participate in the verification was to reassure the reliability of the results of this activity.

Our discussions with members of the NHIF Regional Office helped us discover that not only the two NHIF representatives are not really involved in the RBF verification as they focus their attention on verifying data for the CDF but also the verification team doesn’t collaborate in any way with the NHIF. The latter is not yet involved in the performance purchasing process; information sharing has not been initiated to date.

- Feedback to the regulator (RHMT)

If a feedback to the regulator were envisioned, it is done through a transfer of verification results to MOHSW for validation. This transmission is done in two ways namely HMIS data and a detailed report submitted to the RBF National team after validation by the PORALG. The HMIS data is sent to the Directorate of Health Information system while the detailed report is directed to the RBF national team for a description of how the verification was conducted. This report is highlighting the progress made and the weaknesses found at the health facility level.

It is this feedback that powers the Office of the Chief Accountant to initiate financial verification procedures for a preparation of a payment request to the MOF.

Note however that at the regional level, the RHMT being part of the RBF data verification team performs some regulation function by ensuring conformity of actions with the directives of the MOHSW. This puts the RHMT in a position accumulation of functions that  creates a conflict of interest.

- Patient tracing and client satisfaction survey;

As mentioned above, the verification team sends its own agents for the Community verification. They work with community workers to trace patients who used the services of the verified health facility. They also assess the patient satisfaction using a questionnaire.

This isn’t in line with the guidelines of the operational manual that suggests using a local association to trace the sampled patients which represents 10% of patients who used the services.

This is probably due to the will of RHMT and his staff to keep all activities in their hands. NGOs have not been recruited. This circumvention of RBF directives lost a community participation lever through the involvement of an already active association in the community.

In the RBF spirit, the involvement of local NGOs for community verification also provides leverage to strengthen their financial capacity of actors at the local level and increase the attention of the population on health services provided by the health center.

During our visits to different facilities, there were no signs of over reporting identified. We didn’t learn about sanctions linked to deliberate fraud mechanisms. However, In some cases the error margin was higher than 10% and the difference proportion was deducted from the total amount paid for the quantity.

Two problems have been identified with this audit activity:

- The quarterly internal verification includes persons recruited in hospitals to assist in the verification of quality. This is a mobilization of people with medical skills. However, their mobilization outside their usual positions leaves substantive emptiness in hospitals and their time outside their hospital of assignment shows that this organization cannot be sustainable especially as new districts adopt increasingly the RBF. A different solution should be found to constitute a lasting and effective verification entity.

- The verification at the community level makes use of community health workers to identify patients in households. This collaboration can be a problem especially as these community workers are working with health facilities to raise awareness and mobilize demand. This may cause fear in patients who would like to speak freely on the negatives aspects they have found. The collaboration with the community health workers could increase the social desirability bias as patients don’t want to get frictions with the health professionals. Patients will tend to report only what is positive from health centers without making strong suggestions about gaps for remedy.

From the Project Design Document, the external audit shall be conducted by the Controller Auditor General.  Within the health sector, a team of external auditors is already appointed to carry out audits for different health programs. The manager of CAG ensures that the institution has the necessary and sufficient technical resources to conduct the external audit activity and that falls within their prerogatives. He does the same for other health programs. However, negotiations between the RBF National team and the CAG is slow to materialize. One of the sticking points is that the CAG would seek a subcontractor for this activity, driving RFB team to fears the exorbitant costs (To be checked with the RBF Unit during the second visit).

Until now, the external verification has not been conducted. The system is not yet in place. RBF Unit was in the process of negotiation with the CAG and planning for training in order to strengthen the capacity of the CAG senior auditors.

Recommendations:

- Revise the tasks separation between the regulatory and verification bodies. The RHMT should at least play the minimal role of verification to learn from this experience in order to improve its technical follow up at the regional level.

- Clarify the implications related to RBF principles and good practices including the separation of functions. The lack of understanding of these implications makes difficult the detection of functional RBF incompatibilities.

- Assign this verification function to an autonomous structure that would ensure an objective assessment without the possibility of conflict of interest. This structure may be the NHIF itself which takes the lead and it can be supported by the NGOs.

- Find NHIF own human resources for the verification structures to avoid lack of staff in other health structures which are already in need. This can be achieved through capacity building of the existing staff in the NHIF.

- For community verification, recruit community-based organizations to conduct this activity without having any functional relationship with health centers. This is predisposed by the RBF procedural manual in Tanzania.

### PBF Steering Committee

According to the RBF project design document, the RBF Steering Committee has the following roles and responsibilities:

- Provide strategic and policy direction related to RBF;

- High-level monitoring of project implementation and results;

- Ensure excellent coordination and timely implementation by the managers at all entities of government and contracted agencies;

- Review progress reports prepared by the National RBF Team;

- Review and comment on annual work plans and budgets;

- Ensure that agreed performance targets and timelines for activities under the different components are met;

- Proactively address critical issues that could hinder project implementation.

- Mobilize resources for RBF implementation

- The committee will be conducted semiannually and it will be chaired by PS for the MOHSW

The RBF steering committee has up to now play its role though some weaknesses have been signaled by some members. The preparation of meetings and the information broadcast require an improvement of notably in thematic spread that will be debated during semi-annual meetings. It was realized that some high responsible didn’t take share to the two meetings that had already taken place.

However, it was also realized that those meetings are subject of debate on the RBF with an evaluation analysis of RBF approach. As the pilot project is at its first year, definite decisions were not taken to impact the implementation course of RBF.

Some extent of sensitization is needed to invite members to actively participate and follow closely the evolution of that approach. This should be the task of RBF National Team with the support of DPP.

### The Counter – Verifier (Controller Auditor General)

The RBF project design document stipulates that the independent verifier will be the Controller Auditor General (CAG) who will conduct the ex-post counter-verification twice a year, using a sample of 25% of facilities at that time participating in RBF. The independent verifier will counter-verify quantity results as verified by the IAG of each region and will conduct a quality assessment using the in-force quality checklist. Not only that but also the independent verifier will also audit financial management at each selected facility.

Up to our evaluation visit, the CAG was not involved in that RBF project yet as that was described. The discussions were under the way between the RBF national team and the CAG to find the modalities of its implication. The discussions seemed to aim at the contract type to be given to it and the training it had to benefit.

Our discussion with CAG showed that the CAG avails the needed resources for carrying out such a kind of work, according to its proper sayings.

# DISCUSSION AND SOLUTION HINTS

## The design phase

The conception of RBF project in Tanzania took into account the most part of principles and practices currently applied in this approach. Some other practices weren’t knowingly considered so as not to destabilize existing administrative and financial procedures in the public services offer.

That worry of wanting to maintain the existing procedures has facto and still keeps a kind of challenge in way of collaborating between the stakeholders in RBF project as well as some hindrances to the full health facilities brightening.

As explained above, the reconsideration of those principles and practices put aside should improve the RBF efficiency system in Tanzania without harming the health system under the way and the governmental initiatives of reforms as well.

## The training phase

The given training has stressed much on the operational aspects to the detriment of conceptual aspects. The actors of implementation have good understanding of roles and responsibilities which were given by the project design document and the operational manual. A kind of confusion still continues on the implications linked to conceptual disposals on the functions separation, the autonomy of health facilities’ management, the contracts negotiation, the importance of the elaboration of business plan, etc.

Those insufficiencies must be corrected by a refresher training to better explain the important links between the RBF principles and the operational disposals to be taken into account during the implementation so as to avoid interest conflicts and challenges to the management autonomy, guarantee of the best performance of the structures under contract.

## The Implementation

Since the RBF project launching, the implementation activities have taken the normal progress with good activities occurrence at different levels. The majority of key functions to RBF have been exerted in accordance with project directives except the purchaser role, Fund Holder and the counter verifier. The following points sum up what we realized during our evaluation.

### Regulation role

The regulator (MOHCDGEC) has wholly played his role in the course of the preparation and the implementation of RBF in Tanzania. He knew how to involve the different actors to conceive and elaborate the key documents of RBF and to define the roles and responsibilities of various stakeholders. Nevertheless, the concern to keep the existing procedures incited to the reserves as far as adoption of some principles and practices advocated by RBF is concerned.

### Facilitation Role

The PORALG central level acts like the supervisor of activities carried out at regional and council level. Then, it regularly assures the monitoring and evaluation of activities carried out by regional entities under the RAS authority and the activities carried out by the district structures under the DED authority.

This creates the information flux from the intermediate and peripheral level that attains the PORALG central level. Consequently, this one can take decisions concerning corrections and adjustments of implementation to the regions and councils level.

Taking into account the mission of RBF National Team, its roles and responsibilities, this structure would be more efficient if it were lodged in the PORALG to exploit effectively that information flux from peripheral level. For lack of that relocalization, a close collaboration between the RBF National team and the PORALG should be further strengthened to draw maximum of lessons from RBF pilot experiments in Tanzania.

### Purchasing role

The purchaser’s role given to NHIF was not exerted in accordance with the indications of the project design document and the project operational manual. That action was carried out by MOHSW in a place of NHIF and the regional office was not deeply involved in sending two agents in the verification team.

That situation has to be corrected so that the NHIF may wholly play its purchaser’s role in involving the regional offices. The former will be able to capitalize their proximity with the contracted health structures. For better carrying their mission, those regional offices should benefit a training and capacity building on how to carry out the various attributions of the purchaser.

Indeed, the purchaser is supposed to assure the scrupulous respect of the contract clauses that he signs. This requires the significant action in the checking of the purchased results. He should also ensure that the business plan content reflects the needed health improvements in the of health facilities catchment areas. In fact, a business plan that doesn’t show how some key problems will be resolved wouldn’t deserve a contract from the purchaser. For assuring good harmony, the purchaser has to negotiate the health problems that should be priority depending on the health situation that prevails at the time of business plan elaboration. That priority should be inspired by the evolution of health indicators. Those showing weak performance level should have much more attention and vice versa.

All those considerations incite us to suggest that the NHIF becomes the verification head that should work in close collaboration with the IAG and the local NGOs to assure further objectivity. In addition, the NHIF should be endowed with human resources enabling to check the content and the pertinence of business plans before signing the contracts with the health facilities. If the business plans pertinence weren’t demonstrated the contract would be suspended for the concerned period. That should incite the contracted structures in perpetual logic of searching health solutions to the problems found in their catchment areas.

Likewise, the NHIF will hold accountable all the RBF actors to obey to the contract terms signed with it.

Notice, moreover, that the NHIF is also in charge of the initiation of the health coverage mechanisms notably the one covering state civil servants and another one covering part of workers of informal sector.

The mastering of the approach like the RBF by the NHIF will allow it to further master the supply side , while increasing its capacities to manage the demand side strategies. This will build a better mastery to run the Single National Health Insurance (SNHI).

### Verification role

The verifier role has shown some level of conflict of interest  in giving a prominent place to the RHMT that is naturally the regulator at regional level. To remedy it, it should be useful to withdraw the RHMT from the verification team and issue to it a regulator role with a RBF Task Force built within to closely collaborate with the RBF National Team. This regional RBF task force will play a crucial role of RBF relay to the RBF national team in order to monitor and document the lessons learnt from the pilot experiences. This will keep the central administration informed about the daily RBF implementation which would be hard to monitor from Dar-Es-Salaam.

Besides, a contract should adapt to the RHMT new missions so as to reinforce the RBF monitoring and evaluation on regional and council levels. In the beginning, the RHMT / Task Force should inform the superior level such as the PORALG which will have in it the RBF national team.

Notice that the RBF technical capacities of RHMT must be strengthened in order to assure its adequate new tasks.

### Health care provision role

The Providers carried out their missions in satisfactory ways though some improvements require some capacities strengthening on quality of care and community mobilization. It could be very helpful to grant them more autonomy and ease their work by removing the obligation to get the approval from the District Medical Officers before withdrawing and allocating financial resources. Financial auditing could be reinforced to ensure more transparency and accountability.

### Counter verification role

The CAG is not yet involved in the RBF project in Tanzania. Its involvement will help see clearly on the effectiveness of verification and give an idea on the data liability collected up today.

### Fund holding role

The Ministry of Finance was not yet involved as Fund Holder of RBF project. All the activities were carried in the Health Ministry which is against the directives of the Project design document. A correction should be made so that that Ministry may fully play its role.

The consideration of that finance mechanism by the MOF should help the country better analyze the costs and anticipate to the financial sustainability on middle and long terms.

The effective involvement of MOF and NHIF should be seen as a pledge of the best ownership building and an institutional and financial sustainability for the future.

Considering all above-mentioned findings, the observed gaps at different levels of RBF implementation should be corrected starting by revising the Project Design Document and the Operational manual to capture the adopted modifications. The latter will have to be pointed out so as to redefine the roles and the responsibilities of the various actors as well as the procedures to follow for the stakeholders who will have changed the functions. (e.g. RHMT, NHIF)

The adoption of RBF principles and practices currently involved in other countries for the RBF should help find complementary solutions to the initiatives that the country launched. This is much more encouraging that the country has set up open doors to the possible adjustments for the coming times.

# References

- Meessen B., L. Musango, J. P. Kashala, and J. Lemlin. 2006. « Reviewing institutions of Rural health Centres : The Performnce Initiative in Butare, Rwanda ». Tropical Medicine and International Health 11 (8) : 1303-17.

- Soeters R, Habineza C, Peerenboom PB. Performance-based financing and changing the district health system: experience from Rwanda. Bulletin of the World Health Organization 2006 November;84(11):884-9.

- Van de Poel E, Flores G, Ir P, O'Donnell O. 2016. Impact of Performance-Based Financing in a Low-Resource Setting: A Decade of Experience in Cambodia. Health Econ. Jun; 25(6):688-705. doi: 10.1002/hec.3219.PMID:26224021

- Meessen B, Soucat A, Sekabaraga C. Performance-based financing: just a donor fad or a catalyst towards comprehensive health-care reform? Bulletin of the World Health Organization 2011;89:153-6.

- Fritsche G, Soeters R, Meessen B. Performance-Based Financing Toolkit. Washington DC: World Bank; 2014.

- Big results Now, national report of star rating baseline assessment in twenty regions (2015-16)

- Manzi, F. Schellenberg,  J.A., Hutton, G Wyss K.  Mbuya C.  Shirima K. Mshinda H. Tanner, M. and Schellenberg, D..Human resources for health care delivery in Tanzania: a multifaceted problem. Human Resources for Health201210:3. DOI: 10.1186/1478-4491-10-3

- Bob Perenboom P., Basenya O., Bossuyt M., Ndayishimiye J., Léonard Ntakarutimana, Van de Weerd J.. La bonne gouvernance dans la réforme du système de santé au Burundi. Santé Publique 2014.2 (Vol.26à.pp.229-240.

Faith-based hospitals which are designated to serve as council hospital where no government facility exists

Chief examiner of Accounts, Ministry of Health Community development gender elders and Children, Dar- es- salam, Bank Details- Kishapu health facilities, 2015-2016