## Slide 1: Moving Forward with the HCFS

## Slide 2: Points from the Discussion Notes
INCREASED FUNDING should NOT mean just more budget– work on efficiency gains (including needs=based allocation also help)
Consider EARMARKED TAXES and FEES and innovative ways to get money from formal sector and migrant workers
Although cognizant of reforms in social protection– desire of MoHFW is stand-alone health reform
Autonomous government agency to drive reforms
Benefit package to be determined and agreed to LATER
Questions on POLITICAL WILL and CAPACITY

## Slide 3: Health System Assessment Findings
Impressive performance in service delivery
Improving health information system with expanding use of information technology
On-going reforms in medicine procurement and distribution
Capable of fast production of human resources for health
Strong NGOs working in the health sector
Growing private health sector
High out of pocket payments
Centralized government health system

## Slide 4: Moving Forward while Building on the Gains and Addressing Bottlenecks
Enactment of Necessary Legislation/s including increased financing laws or policies (i.e. added budgetary allocation/mandatory premium payments/ earmarked taxes)
Ensuring Coordination with HPNSDP/demand-side financing (DSF)/other reforms
Increasing Implementation Capacity of the government in a demand-driven health system
Building up Health Provider Management Capacity
Generating Public Support from All Stakeholders

## Slide 5: Initial actions for the implementation of the Health Care Financing Strategy (HCFS)
Health Economics Unit (HEU) must be strengthened immediately.
  Addition of at least 10 technical and all necessary administrative staff to be funded initially by DPs and subsequently by an increase in the budgetary amount for OP line item for staffing
Development Partners (DP) commit the fund the costs of the immediate strengthening of the HEU and the initial outsourcing of the implementation functions

## Slide 6: Transitioning while building up capacities
TRANSITION
HCFS Advisory Council
HCFS Implementation Team
SSK Operations Units
Outsourced Technical capacities to various Government/ Quasi-Government/NGO/Private Organizations
National Health Protection Authority
Governing Board
Management Team
SSK- Poor and Formal Sector (Members/Provider/Fund Management Offices)
Technical /Research Offices
Informal Sector Regulatory Offices

## Slide 7: Necessary Legislation
Create HCFS Advisory Council with HEU as secretariat
Contract a government or an alternative quasi-government agency to help draft the policies and legislation (with DP support)
Drafting and advocate the enactment of a law institutionalizing the Health Care Financing Strategy

## Slide 8: HCFS Advisory Council
Chaired by the Minister of Health
Co-chaired by the Ministry of Finance
Members include:
  Minister of Local Government and Rural Development
  Minister of Social Protection
  Secretary of Health
  Director General (DG) of HEU
  Representatives from Business/Employers
  Representatives from civil society/NGOs
  Representatives from employee groups
  Representatives from informal sector workers
  Representatives from health providers (doctors/hospitals)
  Media representative
  Others
HEU shall act as the secretariat with representatives of DPs sitting as observers.

## Slide 9: Enactment of the following laws
Enactment of the National Health Protection System (NHPS) and the creation of the National Health Protection Authority (NHPA) with the following HCFS elements
  Single national risk pool with non-poor informal sector pre-paying to various schemes AND a single fund combining the mandatory scheme for formal sector workers and the government subsidized non-contributory scheme for the poor (SSK)
  User fee retention of government health facilities
  Investment in IT in health facilities
  Registration and regulation of providers of pre-payment schemes to non-poor informal sector
  Contracting with private/NGO health care providers
  Integration of DSF into the NHPS
Increased budgetary allocation
New revenue sources (preferably earmarked taxes and fees)

## Slide 10: Coordination
Create HCFS implementation team with DG-HEU as head
Work for the incorporation of the HCFS in the HPNSDP during the mid-term review in September 2014.

## Slide 11: HCFS Implementation Team
Chaired by the DG of HEU and the Members include government officials working on the following:
  HPNSDP
  DSF
  Community clinics
  Urban health
  IT reforms
  Drug supply reforms
  Hospital reforms
  Need-based allocation reforms
  Others
Representatives from NGOs and the providers of the outsourced services

## Slide 12: Implementation Capacity
Outsource key technical functions to government, quasi-government and NGOs (with DP support)
HEU shall lead the implementation of the “SSK-poor” non-contributory scheme with the intention to build capacity on:
  fund management
  management of members
  contracting with health care providers and purchasing of health services.
HEU should be provided capacity to regulate the micro-health insurers and other providers of pre-payment schemes to the non-poor informal sector

## Slide 13: Contract out following technical capacities
Institute of Health Economics of Dhaka University shall be contracted to do rapid studies and assist the development of fund management, member management, benefit coverage, and public/private provider contracting and payment policies; and other health financing policies and guidelines
A government agency and/or NGO/private organization to develop management training courses (particularly financial management courses) and the conduct of these courses to government health facilities/ hospitals
DGHS MIS to rapidly scale up the automation of the information systems of government hospitals
A government or quasi-government agency to help draft the following legislation/policies
Independent M and E and Marketing plan/activities to NGO/private sector

## Slide 14: Management Capacities AND Public Support
Management Capacity
Outsource the conduct of management training of government and private health care providers to government or NGO/private training institutions (with DP support)
Public Support
In addition to the council and implementation team generating support, contract out the drafting of a marketing plan (with DP support)

## Slide 15
 | 6/13 to 1/14 | 2/14 to 12/14 | 1/15 to 12/18 | 1/19 to 12/19
Create HCFS Advisory Council |  |  |  | 
Create HCFS Implementation Team |  |  |  | 
Contracting with government/quasi-government agencies on the following technical activities Health financing research including benefits coverage and levels; and provider contracting and payment methods Development of management training modules and the conduct of management training (including financial management) of government health facilities Independent monitoring and evaluation Development and implementation of marketing plan Policy research and the drafting of legislation, policies and guidelines |  |  |  | 

## Slide 16
 |  | 2/14 to 12/14 | 1/15 to 12/18 | 1/19 to 12/19
Establishment of SSK central operations unit and SSK field operations unit |  |  |  | 
Draft legislations drafted and submitted |  |  |  | 
HCFS incorporated into the HPNSDP |  |  |  | 
Launch of “SSK-poor” scheme |  |  |  | 
Assuming the necessary laws are passed: Institutionalization of the National Health Protection System Organization of the National Health Protection Authority (NHPA) – HCFS Advisory Council/Implementation Team and SSK operations units are brought in to NHPA Launch of “SSK-formal sector” scheme Launch of the regulation of informal sector providers of pre-payment schemes |  |  |  | 
EXPANSION |  |  |  | 
REVIEW and AMENDMENT (SINGLE FUND, PURELY REGULATORY or RETAIN DUAL ROLE) |  |  |  |