## TaskForce
| ACTIVIDADE | DESCRIÇÃO DA ACTIVIDADE | [17 empty] | Estado | Responsável | Priority
|  |  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M
Gestão do Grupo de Trabalho da Estratégia de Financiamento | Estabelecer o grupo de trabalho da EF | Finalizar os TdR, Plano de Trabalho, Cronograma | [17 empty] | Contínuo | DPC | Medium | High | bar: N
| Marcar encontros contínuos com os intervenientes | Realizar encontros quinzenais para apresentar o progresso das actividades | [17 empty] | Contínuo | DPC | bar: N
|  | Circular as notas dos encontros | [17 empty] | Não iniciou | DPC/USAID | Medium | Medium
Workshop 1: Lançamento da Estratégia de Financiamento da Saúde | Preparação para Workshop 1: Lançamento do grupo de trabalho do financiamento a saúde | Recepção por parte do Ministro | [17 empty] | Não iniciou | DPC/WB/WHO/USAID | Medium | Low | bar: N to D
|  | Finalizar a agenda e a lista de participantes | [17 empty] | Não iniciou | DPC | Medium | bar: N to D
|  | Finalizar os materiais de lançamento | [17 empty] | Não iniciou | DPC/WB/WHO/USAID | Medium | bar: D to J
| Workshop 1: Lançamento do Grupo de Trabalho | Lançar o grupo de trabalho da EF para apresentar o quadro conceptual | [17 empty] | Não iniciou | DPC
Workshop 2a : Análise da Situação | Preparação para Workshop 2: Análise da Situação | 1. Working paper e Policy Brief: Custeamento One Health | [17 empty] | Não iniciou | USAID | bar: N to M
|  | 2. Working paper e Policy Brief: Espaço Fiscal para a Avaliação da Saúde | [17 empty] | Não iniciou | USAID/WB | bar: N to M
|  | 3. Working paper e Policy Brief: Análise do Panorama sobre o Seguro | [17 empty] | Não iniciou | USAID | bar: N to M
|  | 4. Preliminary Analysis: Dados preliminares das CNS | [17 empty] | Contínuo | WHO/USAID | bar: N to M
|  | 5. Working paper e Policy Brief: Análise da Situação (Visão geral) | [17 empty] | Não iniciou | WHO/USAID | bar: N to A
|  | 6. Working paper e Policy Brief: NASA Analysis | [17 empty] | Contínuo | UNAIDS | bar: A
| Workshop 2a: Análise da Situação | 1/2 dia de Discussão Técnica | [17 empty] | Não iniciou | DPC
|  | Rascunho: Secção dos Antecedentes da Estratégia de Financiamento a Saúde | [17 empty] | Não iniciou | USAID
Workshop 2b: Discussão com os Intervenientes | Workshop 2b: Discussão com os Intervenientes | Discussão com os Intervenientes | [17 empty] | Não iniciou | WHO
Workshop 3: Mobilização de Recursos | Preparação para o Workshop 3: Mobilização | 7. Working Paper e Policy Brief: Modelos de geração de receitas | [17 empty] | Não iniciou | WB/USAID | bar: M to J
|  | 8. Working Paper e Policy Brief: Caso de Investimento para a saúde | [17 empty] | Não iniciou | WB | bar: F to J
|  | 9. Modelos de Pacotes básicos de serviços | [17 empty] | Não iniciou | WHO | bar: N to J
| Workshop 3: Mobilização de Recursos | 1/2 dia de Discussão Técnica | [17 empty] | Não iniciou | DPC
|  | Rascunho: Secção da Mobilização de Recursos | [17 empty] | Não iniciou | WB
Workshop 4: Agregação dos Recursos | Preparação para Workshop 4: Agregação dos Recursos | 10. Working Paper e Policy Brief: Opções de partilha de risco | [17 empty] | Não iniciou | USAID | bar: M to A
|  | 11. Working Paper e Policy Brief: Despesas Catastróficas | [17 empty] | Não iniciou | WHO | bar: M to A
| Workshop 4: Agregação dos Recursos | 1/2 dia de Discussão Técnica | [17 empty] | Não iniciou | DPC
|  | Rascunho: Secção da Agregação de Recursos | [17 empty] | Não iniciou | WHO/USAID
Workshop 5: Alocação dos Recursos e Mecanismos de Pagamento dos Serviços | Preparação para Workshop 5: Alocação dos Recursos e Mecanismos de Pagamento dos Serviços | 12. Policy Brief: Sumário sobre mecanismos de PBF | [17 empty] | Não iniciou | USAID | bar: A to O
|  | 13. Policy Brief: Planificação e Alocação de Recursos | [17 empty] | Não iniciou | USAID | bar: A to O
|  | 14. Estudo sobre mecanismos inovadores de financiamento à saúde | [17 empty] | Não iniciou | WHO | bar: A to O
| Workshop 5: Agregação dos Recursos e Mecanismos de Pagamento dos Serviços | 1/2 dia de Discussão Técnica | [17 empty] | Não iniciou | DPC
|  | Rascunho: Secção de Alocação dos Recursos e Mecanismos de Pagamento dos Serviços | [17 empty] | Não iniciou | WHO
Workshop 6: Consenso dos Stakeholders | Workshop 6: Consenso dos Stakeholders | Rascunho da Estratégia de Financiamento a saúde | [17 empty] | Não iniciou | DPC | bar: J to M
|  | 1/2 dia para Apresentação da Estratégia de Financiamento a Saúde | [17 empty] | Não iniciou | DPC
|  | Revisão da Estratégia de Financiamento a Saúde com base nos comentários | [17 empty] | Não iniciou | DPC | bar: D to M
Finalizar e Apresentar a Estratégia de Financiamento da Saúde | Finalizar a Estratégia de Financiamento da Saúde | Finalizar a Estratégia de Financiamento a Saúde | [17 empty] | Não iniciou | DPC/WHO/USAID | bar: N to M
| Apresentar os resultados | Actividades de Visibilidade: Cobertura da Imprensa e Workshops de Advocacia | [17 empty] | Não iniciou | DPC/WHO/USAID | bar: J to M
|  | Pontos de Discussão para o MISAU apresentar aos Ministérios homólogos | [17 empty] | Não iniciou | DPC/WHO/USAID | bar: J to M
Mecanismo de Implementação | Quadro de implementação | 15. Quadro de implementação e Plano de trabalho detalhado | [17 empty] | Não iniciou | DPC/WHO/USAID
| Plano de trabalho detalhado para a Unidade de Financiamento a Saúde dentro do MISAU | [18 empty] | Não iniciou | DPC/WHO/USAID | bar: N to M
| Fortalecimento das capacidades | [18 empty] | Não iniciou | WHO/USAID
-

## Year 1 (hidden)
wk strm | ACTIVITIES | align with PES | align with | YEAR 1
|  | /Action Plan | PFM | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul
Start-up meeting in Maputo with COP, Deloitte HQ PM, and partners | bar: YEAR 1 Jul
Project start-up briefing with USAID | bar: YEAR 1 Jul
Office space secured | bar: YEAR 1 Jul
All personnel hired | bar: YEAR 1 Jul
Work planning session with partners and key stakeholders | bar: YEAR 1 Jul
Office operational | bar: YEAR 1 Jul
Subcontracts finalized with partner organizations | bar: YEAR 1 Jul to YEAR 1 Aug
Finalize work plan and PMP | bar: YEAR 1 Jul to YEAR 1 Aug
Remaining operations staff hired | bar: YEAR 1 Aug to YEAR 1 Oct
PMO and subject matter expert technical assistance to MISAU, MMAS and CSOs | bar: YEAR 1 Aug to YEAR 1 Jul
Comprehensive Institutionalization Strategy developed in collaboration with counterparts and stakeholders | bar: YEAR 1 Sep
Quarterly program review meetings with USAID | bar: YEAR 1 Oct; YEAR 1 Jan; YEAR 1 Apr; YEAR 1 Jul
PMP review meeting with USAID | bar: YEAR 1 Aug
M&E Workshop conducted for project team | bar: YEAR 1 Aug
Baseline Assessment Report completed | bar: YEAR 1 Aug to YEAR 1 Sep
1.1 Support to DAF | Confirm DAF performance targets, metrics, and develop dashboards to monitor performance improvements | bar: YEAR 1 Jan to YEAR 1 Mar
Map current processes in DAF | bar: YEAR 1 Nov to YEAR 1 Dec
Support DAF to design SOPs, including monitoring and compliance mechanisms, job aides, and training materials | bar: YEAR 1 Jan to YEAR 1 Mar; YEAR 1 May to YEAR 1 Jun
Support DAF to implement, monitor and enforce compliance with SOPs | bar: YEAR 1 May to YEAR 1 Jul
Update Funcionalizacao da DAF Report | bar: YEAR 1 Feb
Disseminate DAF performance improvements to internal/external stakeholders | bar: YEAR 1 Mar to YEAR 1 Jul
1.3 Governance Support to CMAM | Support definition of CMAM IA objectives and development of IA visits plan to achieve targets. | bar: YEAR 1 Jan to YEAR 1 Feb
Support temporarily additional IA positions to allow CMAM to achieve quantitative and qualitative targets | bar: YEAR 1 Feb to YEAR 1 Jul
Capacitate CMAM AI staff on the use of recently developed (with Support from UNICEF) IA guidelines ( for health facilities and district/provincial warehouses. | bar: YEAR 1 Feb to YEAR 1 Jul
Support implementation of IA provincial visits | bar: YEAR 1 Feb to YEAR 1 Jul
Develop standardized IA provincial visits reports and support data analysis, dissemination and use. | bar: YEAR 1 Mar
Determine with CMAM opportunity to outsource or perform in-house stock audits of central warehouse and assist CMAM in implementing recommendation. | bar: YEAR 1 Apr to YEAR 1 Jun
Develop methodology and tools and capacitate staff on CMAM central sectors IA. | bar: YEAR 1 Apr to YEAR 1 Jul
Promote collaboration between CMAM IA and MISAU General Inspectorate to follow-up implementation of IA recommendations | bar: YEAR 1 Jan to YEAR 1 Jul
1.4.1 | Clarify Performance Targets and Introduce Capacity Building and Change Management Approach | bar: YEAR 1 Nov
1.4.2 | Conduct desk review of literature | bar: YEAR 1 Nov
1.4.3 | Analyze current state of capacity and prioritize performance improvement areas | bar: YEAR 1 Nov to YEAR 1 Dec
1.4.4 | Draft performance improvement workplan | bar: YEAR 1 Nov to YEAR 1 Dec
1.4.5 | Support transition to UGB | bar: YEAR 1 Jan to YEAR 1 Feb
1.4.6 | Support CMAM Financial Systems to follow international best practices standards | bar: YEAR 1 Jan to YEAR 1 Mar
1.4.7 | Disseminate CMAM Financial Management performance data with donors and MISAU | bar: YEAR 1 Apr to YEAR 1 Jun
1.4.8 | Detailed Analysis/Mapping of Finance Unit Structure, Processing, and Performance Expectations | bar: YEAR 1 Jan to YEAR 1 Feb
1.4.9 | Work with Finance Unit to fill capacity gaps identified in organizational structure and processes | bar: YEAR 1 Mar
1.4.10 | Work with CMAM to measure performance of Finance Unit | bar: YEAR 1 Apr to YEAR 1 Jun
1.4.11 | Support Finance Unit to participate in annual planning cycle | bar: YEAR 1 Jan to YEAR 1 Jun
1.4.12 | Support Finance Unit to prepare budget based on annual plan | bar: YEAR 1 Jan to YEAR 1 Jun
Clarify roles of the various groups involved in the management and distribution of assets and supplies
1.5 | Develop manual for the acquisition, receipt, storage, and distribution of supplies and goods
Provide training and in-service mentoring to Administracao Interna, Patrimonio, and Centro de Abastecimento on the manual
1.6.1 | Recruit project staff, define workstream goal and objectives, and identify key stakeholders | bar: YEAR 1 Mar to YEAR 1 Apr
1.6.2 | Introduce business case for health governance in the province and agree on performance targets/future vision, Identify current state of participatory governance in health sector. Hold workplanning session with Conselho Coordenador representatives | bar: YEAR 1 Jun to YEAR 1 Jul
2.1.1 | Establish National Health Financing Advisory Committee | bar: YEAR 1 Jan to YEAR 1 Feb
2.1.2 | Introduce concept of national health financing strategy | bar: YEAR 1 Jan to YEAR 1 Feb
2.1.3 | Define TOR for a health financing strategy in cooperation with the MISAU’s Health Planning and Economics Department | [15 empty] | shift all forward 2 months | bar: YEAR 1 May to YEAR 1 Jul
2.1.4 | Draft Health Financing Strategy | bar: YEAR 1 Jul
2.1.5 | Work with Health Planning and Economics Department to define implementation plan of Health Financing Strategy
2.1.6 | Confirm performance targets/capacity building needs of Health Planning and Econ Dept | bar: YEAR 1 Apr to YEAR 1 May
2.1.7 | Define specific technical knowledge needs of Health Planning and Economics Department and define activities to meet those needs | bar: YEAR 1 Feb to YEAR 1 Jun
2.1.8 | Provide TA to Health Planning and Economics Department on key tenets of health financing strategy and capacity building efforts | bar: YEAR 1 May to YEAR 1 Jul
2.2.1 | Organize NHA Steering Committee to continue support to the 2013 NHA exercise | bar: YEAR 1 Feb to YEAR 1 May
2.2.2 | Organize NHA team and decide upon a governance structure of the team | bar: YEAR 1 Feb to YEAR 1 Mar
2.2.3 | Provide comprehensive NHA 2012 Training | bar: YEAR 1 Mar
2.2.4 | Identify data sources and key stakeholders in the NHA process (primary and secondary sources) | bar: YEAR 1 Mar to YEAR 1 Apr
2.2.5 | Collect NHA data at household level | [15 empty] | TBD
2.2.6 | Conduct NHA Institutionalization workshop | bar: YEAR 1 May
2.2.7 | Develop NHA institutionalization plan | bar: YEAR 1 May to YEAR 1 Jun
2.2.8 | Explore opportunities to incorporate household level health expenses questions into existing survey mechanism | bar: YEAR 1 May to YEAR 1 Jun
2.2.9 | Introduce concepts in resource efficiency, ways to maximize resources, and financial performance management | bar: YEAR 1 Apr to YEAR 1 Jun
2.2.10 | Demonstrate tools for mapping resource allocation, efficiency mapping, and value initiatives | bar: YEAR 1 May to YEAR 1 Jun
2.2.11 | Increase MISAU and Health Planning and Economics Department’s capacity in OneHealth costing tool | bar: YEAR 1 Jun
2.2.12 | Create clear communications for decentralized health system on OneHealth capabilities and resources | bar: YEAR 1 Jul
shift back to original
2.3.1 | Identify and agree on PBF pilot scheme | [15 empty] | strategy and methodology rather than carrying it out. | bar: YEAR 1 Jan
2.3.2 | Develop PBF goals, objectives, and approach | bar: YEAR 1 Feb
2.3.3 | Develop PBF operations manual and training modules | bar: YEAR 1 Feb to YEAR 1 Mar
2.3.4 | Implement PBF scheme | bar: YEAR 1 Apr
3.1.1 | Confirm future vision for GFU and develop transistion/change management plan and capacity building activities for PSM, M&E, Finance to achieve that vision | bar: YEAR 1 Nov to YEAR 1 Jan
3.1.2 | Revise Round 8 HSS Grant, Budget, Performance Framework | bar: YEAR 1 Dec
3.1.3 | Help MISAU meet GF CPs | bar: YEAR 1 Dec
3.1.4 | Set up financial system for GF disbursement | bar: YEAR 1 Jan to YEAR 1 Mar
3.1.5 | Develop or revise the performance framework for future GF grants | bar: YEAR 1 Mar; YEAR 1 May to YEAR 1 Jun
3.1.6 | Review and update GFU processes, and develop SOPs on progress reports and data collection to support coordination between programs and depts | bar: YEAR 1 Mar to YEAR 1 Jul
3.1.7 | Build GFU capacity (e.g. management tools, knowledge management system, communication and advocacy skills) | bar: YEAR 1 Mar to YEAR 1 Jul
3.2.1 | Confirm mandate/vision of DOP, GFU, and provide support to transition to that vision | [15 empty] | $$$$ | bar: YEAR 1 Nov to YEAR 1 Dec
3.2.2 | Support the development of new proposals | [15 empty] | as needed
3.2.3 | Support WB unit to align their results framework with national M&E system | bar: YEAR 1 Dec to YEAR 1 Jan; YEAR 1 Jun to YEAR 1 Jul
3.2.4 | Provide support to expand GFU procedures and working modalities to other PMU for vertical projects | [15 empty] | as needed
3.2.5 | Support national programs to develop M&E plans aligned with the sector strategic plan | bar: YEAR 1 Mar to YEAR 1 May
3.3.1 | Advise on the development of TOR for Joint Annual Evaluation of Health Sector | bar: YEAR 1 Nov to YEAR 1 Jan
3.3.2 | Participate in Joint Annual Evaluation of Health Sector | bar: YEAR 1 Mar
3.3.3 | Support operationalization of M&E Action Plan
3.3.4 | Support finalization of TOR of M&E Dept staff | bar: YEAR 1 Oct to YEAR 1 Nov
3.3.5 | Support M&E Dept to define the structure of M&E System in Health Sector at all levels. Check with Dimitri and HR person on this one. Discuss our role with head of dept of M&E | [15 empty] | high priority | bar: YEAR 1 Jan to YEAR 1 Jul
3.3.6 | Support the updating of the supervision guidelines, including the M&E component | bar: YEAR 1 Sep to YEAR 1 Jul
3.3.7 | M&E Performance Assessment Framework of Health Sector Adjusted and Adopted at Provincial level | bar: YEAR 1 Sep to YEAR 1 Jul
3.3.8 | Support definition of tools for Data Quality Verification | bar: YEAR 1 Mar to YEAR 1 Apr
3.3.9 | Elaborate the standard document for annual health statistics report | bar: YEAR 1 Jan to YEAR 1 Mar
3.3.10 | Develop tools for the systematic use of information for decision-making | bar: YEAR 1 Apr to YEAR 1 May
3.3.11 | Develop training materials for M&E Dept staff, and support on the job training (yr 1 provide support to help them develop a strong training plan and discuss financial support for training in year 2 to fill funding gap) | bar: YEAR 1 Dec to YEAR 1 Jan
3.3.12 | Define evidence-based targets at central and provincial levels | [15 empty] | low priority move to yr 2 | bar: YEAR 1 Jul
3.3.13 | Define operational research objectives | [15 empty] | low priority move to yr 2 | bar: YEAR 1 Jul
3.3.14 | Establish tools to increase knowledge management (institutional memory) at DMA | [15 empty] | low priority move to yr 2 | bar: YEAR 1 Jul
4.1 | Support coordination of start-up of Twinning Program | bar: YEAR 1 Jun to YEAR 1 Jul
4.2.1 | Confirm and quantify performance targets for APE program and counterpart | bar: YEAR 1 Dec to YEAR 1 Mar
4.2.2 | Assess the capacity of the APE Unit in the context of their performance target areas | bar: YEAR 1 Dec to YEAR 1 Mar
4.2.3 | Strengthen the capacity of the APE Unit to achieve performance targets | bar: YEAR 1 Nov to YEAR 1 Jun
4.2.4 | Strengthen coordination of APE Working Groups | bar: YEAR 1 Nov to YEAR 1 Jun
4.2.5 | Exchange visits to a successful CHW Program (remove entirely) | [15 empty] | Year 2
4.2.6 | Support MISAU to determine if the APE scope should be extended | bar: YEAR 1 May
4.2.7 | Support MISAU's Training Department for materials development related to the expanded role of APEs | bar: YEAR 1 May to YEAR 1 Jun
4.2.8 | Strengthen the supervision mechanism for APEs in provinces | bar: YEAR 1 Dec to YEAR 1 Jan; YEAR 1 Mar to YEAR 1 Jul
4.2.9 | Attend meetings and conference at provincial level | bar: YEAR 1 Feb
4.2.10 | Integrate APE Program indicators into the national health information system | bar: YEAR 1 Jun to YEAR 1 Jul
4.2.11 | Strengthen the mechanism for sustainable funding for the APE Program | bar: YEAR 1 Nov to YEAR 1 Jul
4.3.1 | Develop evaluation plan for course | [15 empty] | STTA | bar: YEAR 1 Nov to YEAR 1 Dec
4.3.2 | Conduct final evaluation of course overall and make minor updates to next course (system/process) | bar: YEAR 1 Nov to YEAR 1 Dec
4.3.3 | Evaluate central level EI and TAS pilot course modules | bar: YEAR 1 Nov to YEAR 1 Jul
4.3.4 | Evaluate quality of professors of central level EI and TAS pilot courses | bar: YEAR 1 Nov; YEAR 1 Jan to YEAR 1 Jul
4.3.5 | Evaluate performance of graduates of first year of the central level EI and TAS pilot courses | bar: YEAR 1 Nov; YEAR 1 Jun
4.3.6 | Complete the Level 4 EI curriculum package | bar: YEAR 1 Aug to YEAR 1 Jan
4.3.7 | Implement the EI Level 4 course in Maputo at ICSM | bar: YEAR 1 Feb to YEAR 1 Jul
4.3.8 | Implement the TAS Level 5 course in Maputo at ICSM | bar: YEAR 1 Feb to YEAR 1 Jul
4.3.9 | Support MMAS to integrate courses into the PES 2014 | bar: YEAR 1 Mar to YEAR 1 Jun
| Develop curricula for Level 3 and 4 for TAS medium course | [15 empty] | 6 mo each | bar: YEAR 1 Jan to YEAR 1 Jul
Develop curricula for Level 5 for El medium course | bar: YEAR 1 Jun to YEAR 1 Jul
4.3.10 | Prioritize and select provinces and provincial institutions to roll out the TAS and EI courses | bar: YEAR 1 Jan
4.3.11 | Develop an implementation for roll out of the EI and TAS course to each selected province | bar: YEAR 1 Mar to YEAR 1 Jun
4.3.12 | Conduct a training of trainers for provincial level courses | bar: YEAR 1 Jun to YEAR 1 Jul
4.3.13 | Incorporate updates and improvements into central level courses based on the evaluation of the first years of the pilot courses | [15 empty] | year 3
4.3.14 | Update the Level 3 EI curriculum package | [15 empty] | 2014
4.3.15 | Update the Level 5 TAS curriculum package | [15 empty] | 2014
4.3.16 | Implement the EI Level 3 course at the provincial level in 2 provinces | [15 empty] | year 2
4.3.17 | Implement the TAS Level 5 course at the provincial level in 2 provinces | [15 empty] | year 2
4.4.1 | Develop metrics for performance targets. Need to hire staff first. Start in April. | bar: YEAR 1 Jan to YEAR 1 Mar
4.4.2 | Conduct a capacity building assessment at DPMAS in Sofala and Niassa | bar: YEAR 1 Feb to YEAR 1 Apr
4.4.3 | Monitor progress towards meeting performance targets | bar: YEAR 1 Apr to YEAR 1 Jul
4.4.4 | Process mapping and process improvement exercise | bar: YEAR 1 Feb to YEAR 1 Apr
4.4.5 | Develop or review and update Standard Operating Procedures (SOPs) | bar: YEAR 1 Feb to YEAR 1 May
4.4.6 | Conduct training/orientation for new SOPs | bar: YEAR 1 Apr to YEAR 1 Jun
4.4.7 | Develop monitoring processes for SOPs | bar: YEAR 1 Jun to YEAR 1 Jul
4.4.8 | Develop/adapt financial management tools and processes | bar: YEAR 1 Mar to YEAR 1 Jul
4.4.9 | Conduct training on financial management tools and processes | bar: YEAR 1 Apr to YEAR 1 Jun
4.4.10 | Develop or update procurement processes | bar: YEAR 1 Mar to YEAR 1 Jul
4.4.11 | Conduct training on procurement processes | bar: YEAR 1 Apr to YEAR 1 Jun
4.4.12 | Conduct advocacy workshops to enable DPMAS to communicate/advocate to receive budget requests | bar: YEAR 1 Apr to YEAR 1 Jun
4.4.13 | Support DPMAS to host coordination meeting to manage/coordinate provincial partners | bar: YEAR 1 Mar to YEAR 1 Jun
4.4.14 | Support annual planning exercise at the provincial level | bar: YEAR 1 Mar to YEAR 1 Jul

## Five Year (hidden)
Illustrative Five Year HSWSS Implementation Plan
ACTIVITIES |  | YEARS
|  | 1 | 2 | 3 | 4 | 5
Program Management & Monitoring | Submit quarterly project reports
Submit Annual Work Plan & updated PMP
Submit Annual Progress Report
Complete independent, external mid-project and final evaluation
Submit close out plan
Submit final project report
IR1 : Increased Effectiveness in Governance | Map current status of DAF, UGEA and CMAM to leadership's vision
Complete implementation plan for DAF, UGEA and CMAM activities
Collaborate with FDC to amp sub-recipient capacity to the five-year vision
Deliver targeted capacity building to DAF, UGEA and CMAM to strengthen governance mechanisms
Revised SOPs in place and utilized within DAF, UGEA and CMAM
Ongoing updates to manuals, SOPs and tools to strengthen DAF, UGEA and CMAM performance
One-on-one coaching sessions with DAF, UGEA and CMAM staff
Development of the customized CMAM Internal Audit Methodology
Transfer of skills and knowledge to FDC sub-recipients in improved planning, budgeting and M&E
Transfer of skills and knowledge to provincial level directorates in the improved processes developed within DAF and UGEA
Transfer of skills and knowledge to the CMAM Directorate Board to sustain improvements in procedures
Integration of updated procedures into provincial level directorates
IR 2: Improved Management of Health Sector Funding | NHA Data Collection Team selected and trained
Data collection and analysis for NHA
NHA completed and disseminated
Deliver targeted capacity building to MISAU to strengthen management of health financing
Allocation criteria selected for MISAU budgeting and planning
Allocation criteria integrated into annual budgeting and planning
Develop rational performance-based financing strategy
Transfer of skills and knowledge to provincial level directorates in improved allocation and management of funds
Costing information integrated into annual programmatic planning and budgeting
IR 3: Strengthened Management & Operations Capacity | Map current status of the GFU to leadership's five-year vision
Finalize the detailed operational plan for the Department of Projects (DOP) with leadership
Deliver targeted capacity building to MISAU to strengthen operational capacity
GF staff transitioned to MIISAU payroll (with receipt of GF funding for Round 9)
Transfer of skills and knowledge to provincial level directorates in improved processes
Institutionalize improved processes within selected provincial level health directorates
IR 4: Strengthened Institutional Capacity | Map prioritized support to the twinning program, the APE program and MMAS educational programs to the respective leadership's five-year vision
Complete analysis and dissemination of APE financial options for sustainability
Complete pilot course of Level 5 Social Welfare Workers and Level 3 Early Childhood Educators
Deliver targeted TA to strengthen the operations and management of the APE roll-out
Develop decentralized opportunities to provide sustained educational programs through MMAS
Institutionalize mechanisms for ongoing collaboration and knowledge sharing of health management and administration programs
Support provincial level institutions to integrated social welfare and early childhood educator programs into standard offerings

## Additional Activities (hidden)
Work-stream # | Activity # | Activity Title | Details | Responsible | Timeframe | Indicator or Target Numbers | Budget Inputs
X.X | X.X | Name of activity | What? How? Where? With whom? | Who will lead? Who will be involved (HQ, consultant, partner, counterpart)? | When and how often will it happen? By when will it be done? | Expected targets/ deliverables and how to measure it | Resources
|  | Support to MMAS/MISAU to assess and standardize community level roles | Support discussions and exploration to rationalize and standardize community level roles, coordinated by Community Committees | Sandy will work with MMAS and MISAU and get input from USAID. Support will be provided by STTA if required. | Dec 2012 to Dec 2013 | Options analysis on different scenarios to consider by MMAS and MISAU | LOE for Sandy and STTA if required

## Calendario
| Data* | Encontro
2013 | 2013-11-05 | Lançamento | Finalizar os TdR, Plano de Trabalho, Cronograma
| 2013-11-19 | Planejamento
| 2013-12-03 | Planejamento
2014 | 2014-01-21 | Planejamento
| 2014-02-04 | Workshop 1 | Lançamento do Grupo de Trabalho
| 2013-02-17 | Planejamento
| 2014-03-04 | Planejamento
| 2014-03-18 | Planejamento
| 2014-04-01 | Planejamento
| 2014-04-15 | Planejamento
| 2014-04-29 | Workshop 2a) | Análise da Situação
| 2014-05-06 | Workshop 2b) | Discussão com os Intervenientes
| 2014-05-20 | Planejamento
| 2014-06-03 | Planejamento
| 2014-06-17 | Planejamento
| 2014-07-01 | Planejamento
| 2014-07-15 | Planejamento
| 2014-07-29 | Workshop 3 | Mobilização de Recursos
| 2014-08-12 | Planejamento
| 2014-08-26 | Planejamento
| 2014-09-09 | Planejamento
| 2014-09-23 | Workshop 4 | Agregação dos Recursos
| 2014-10-07 | Planejamento
| 2014-10-21 | Planejamento
| 2014-11-04 | Planejamento
| 2014-11-18 | Workshop 5 | Agregação dos Recursos e Mecanismos de Pagamento dos Serviços
| 2014-12-02 | Planejamento
| 2014-12-11 | Planejamento
2015 | 2015-01-20 | Workshop 6 | Consenso dos Stakeholders
| 2015-02-03 |  | Finalizar a Estratégia de Financiamento a Saúde
| 2015-03-24 |  | Apresentar a Estratégia de Financiamento a Saúde
* Os Encontros estão programados ocorrerem as terça-feiras, numa base bissmanal

## Studies
Análise da Situação | 1. Custeamento One Health
2. Espaço Fiscal para a Avaliação da Saúde
3. Análise do Panorama sobre o Seguro
4. Dados preliminares das CNS
5. Análise da Situação (Visão geral)
6. NASA Analysis
Mobilização de Recursos | 7. Modelos de geração de receitas
8. Caso de Investimento para a saúde
9. Modelos de Pacotes básicos de serviços
Agregação dos Recursos | 10. Opções de partilha de risco
11. Despesas Catastróficas
Alocação dos Recursos e Mecanismos de Pagamento dos Serviços | 12. Sumário sobre mecanismos de PBF
13. Planificação e Alocação de Recursos
14. Estudo sobre mecanismos inovadores de financiamento à saúde
15. Finalizar a Estratégia de Financiamento a Saúde
16. Quadro de implementação e Plano de trabalho detalhado