## Slide 1
GFF Portfolio Update
Background document for GFF monthly country update call, 13 July 2016

## Slide 2: Country status at a glance
Pioneers: Tanzania, Kenya
Focused on national strategies first: DRC, Ethiopia
Second wave quick starters: Cameroon, Liberia, Uganda
Early 2016: Bangladesh, Mozambique, Senegal
Determining approach: India, Nigeria
2015
2016
Frontrunners
Second wave

## Slide 3: Cameroon: recent developments
Latest updates
  Investment Case draft being prepared, with workshop planned for week of 18 July
    GFF mission to support the process
  CRVS workshop planned for early August
  Work underway on fiscal space analysis and public financial management study
Main challenges
  Investment Case process has dragged out longer than anticipated
  Health financing process moving slowly
Key opportunities
  Strong government willingness to leadership by the government
  Very inclusive process, including involvement of key financiers
Next steps
  First draft of the Investment Case expected by end of July, with complementary financing to be worked out over the subsequent months (by September)

## Slide 4: Cameroon: background information
Country platform
  Health sector strategy steering committee, supported by two technical working groups
  Multiple partners supporting different elements of the process
  Continued strong collaboration between partners, particularly among UNFPA, UNICEF, Gavi, and the Global Fund
Investment Case
  Agreement reached on geographical areas of focus (3 northern regions and eastern region) and broad programmatic priorities (maternal health, neonatal health, adolescent health, nutrition, and CRVS)
Complementary financing of the Investment Case
  Discussions underway, including with France, Germany, Gavi, Global Fund, and the U.S. Government (PEPFAR)
  World Bank/GFF Trust Fund financing: US$100m IDA, US$27m trust fund
    Approved by World Bank Executive Directors
Health financing strategy
  Limited materials to draw upon (no existing strategy)
  Agreement about analytical work reached at kickoff workshop in February 2016
  Strategy expected June 2017

## Slide 5: DRC: recent developments
Latest updates
  Participation of the Minister of Health at the Investors Group
  Investment Case being finalized
  World Bank mission focused primarily on health financing week of 11 July
Main challenges
  Investment Case still not sufficiently consistent and clear document (reflection of the fact that different stakeholders were involved in different pieces)
  Costing and resource mapping are not matching
Key opportunities
  Strong ownership by minister and strong ongoing collaboration between key financiers and technical partners is strong and growing (includes Global Fund, UNFPA, UNICEF, USAID, and World Bank)
Next steps
  Government holding workshop week of 11 July on health financing (particularly purchasing and pooling)
  Aim is to finalize Investment Case by the end of July

## Slide 6: DRC: background information
Country platform
  Draws on an existing multi-stakeholder platform
  Supported by a technical team led by the Office of the Prime Minister
Investment Case
  Built on national health sector strategy
  Focused around service delivery platforms (community delivery, strategic purchasing) and health systems strengthening (HRH, supply chain, financing, info systems)
Complementary financing of the Investment Case
  Strong existing collaboration and involvement from a range of key financiers, including Canada, the Global Fund, JICA, Norway, USAID, and World Bank
  World Bank/GFF Trust Fund financing separated into two projects:
    CRVS: US$30m IDA (for info systems, not only CRVS), US$10m trust fund: approved March 2016
    Additional financing for current project: US$100m IDA, US$40m trust fund: Board date is February 2017
Health financing strategy
  Health financing assessment completed
  Draft HFS prepared – ongoing work to develop important areas (e.g., pooling, purchasing)

## Slide 7: Ethiopia: recent developments
Latest updates
  End-June World Bank identification mission had good technical consultations with partners including H6 and SDG PF partners
    JCCC will be briefed on mission discussions at the next meeting in July
  Discussions on health financing strategy continued with strong interest from partners such as USAID and Gates Foundation
Main challenges
  More work needed to define the CRVS elements of the support from GFF Trust Fund
  More active engagement with civil society in consultations around the program
Key opportunities
  Country Partnership Framework is being developed for IDA18, so possibility of additional IDA once that is agreed upon in second half of 2017 (possibly US$120 million)
    Potential to use the second tranche of IDA to define and include the CRVS elements of the support from GFF Trust Fund
Next steps
  Next mission likely in the second half of September

## Slide 8: Ethiopia: background information
Country platform
  Joint Consulting Forum for sector policy and reform issues
  Joint Core Coordinating Committee for technical work
  TWG for health financing
  TWG for RMNCAH
Investment Case
  Health Sector Transformation Plan (HSTP) serves as the Investment Case
  Focus on demand-side, supply-side and multisectoral interventions (i.e., CRVS, nutrition)
  Strong equity and quality focus
Complementary financing of the Investment Case
  Pooled funding through SDG Performance Fund already exists
  Interest in further aligning funding, including from DfID, GFATM, Gavi, Power of Nutrition TF, USAID and the World Bank
  World Bank/GFF Trust Fund financing: US$50-60m IDA likely available this year, tentatively to be presented to the IDA Executive Directors by March 2017
Health financing strategy
  Advanced draft under review
  Health financing a key issue (both social health insurance for formal sector and community health insurance for non-formal sector)

## Slide 9: Kenya: recent developments
Latest updates
  Discussions underway on providing support to MOH so that it is better positioned to work with the private sector in a more systematic and sustainable way  TOR is being developed for such a position
Main challenges
  Extent of alignment by counties with national framework is unclear in light of devolution and capacity challenges
Key opportunities
  Trust fund for TA paired with results-focused financing  strong incentive for improving quality of implementation
Next steps
  Continue supporting county annual work plan development in alignment with RMNCAH Investment Framework
  Continued consultations on the health financing strategy, with government in lead

## Slide 10: Kenya: background information
Country platform
  Inclusive coordination platform with RMNCAH TWG & Health Financing TWG
Investment Case
  National RMNCAH Investment Framework finalized and approved
  Focus on supply-side performance incentives, vouchers and CCTs to boost demand
  Geographic prioritization on 20 counties
  Technical assistance provided by DfID, JICA, UNAIDS, UNFPA, UNICEF, UN Women, USAID, WHO, and the World Bank
Complementary financing of the Investment Case
  Commitment from Governments of Denmark, Japan, the United Kingdom, and the United States as well as the World Bank, with resources from IDA and the GFF Trust Fund
  World Bank/GFF Trust Fund financing: US$150m IDA, US$40m trust fund
    Board decision expected June 2016
Health financing strategy
  Five key areas: resource mobilization; purchasing; benefits definition; accreditation and licensing; and governance

## Slide 11: Liberia: recent developments
Latest updates
  GFF mission scheduled week of 18 July: objective is to support finalization of the Investment Case
    Specific focus on identifying adolescent health priorities and finalizing the resource mapping so to enable the country to determine scope of the Investment Case
  MOH has requested Gavi and the Global Fund to join the mission to ensure alignment and streamlining the financing to the Investment Case
  Ministry is reaching out to main financiers (European Commission, Gavi, Global Fund, USAID, and World Bank) to finalize the resource mapping
Main challenges
  Finalizing the scope of the Investment Case
Key opportunities
  Momentum on the health financing strategy following UHC Forum
  Opportunity to support country with further developing strategy on adolescents
Next steps
  July mission

## Slide 12: Liberia: background information
Country platform
  TWG on RMNCAH and TWG on health financing overseen by a health sector committee
Investment Case
  Updated costed Investment Case shared for consultation
  Four priorities:
    Quality EmONC and adolescent/youth-friendly RMNCAH services
    Emergency preparedness, surveillance, and response (esp. maternal and newborn death surveillance and response)
    Sustainable community engagement
    Enabling environment: leadership, governance, and management
Complementary financing for the Investment Case
  Discussions underway with Gavi, Global Fund, USAID, and the World Bank
    Global Fund HSS application in process and Gavi HSS funding request due September 2016
  World Bank/GFF Trust Fund financing under discussion (likely US$16 million allocation from GFF Trust Fund)
Health financing strategy
  Key areas: Health Equity Fund, use of resource allocation formula between counties, improved alignment and on-budget donor funding

## Slide 13: Mozambique: recent developments
Latest updates
  A GFF mission took place 6-17 June 2016
  Investment Case:
    The national health strategy (PESS) will provide the basis for discussions of prioritizations of interventions
    The specific instruments/mechanisms to channel funding remain to be agreed upon, with the outcome of the ongoing revision of the PROSAUDE MOU and Procedures Manual important for agreeing on way forward for pooling external financing
    New momentum related to CRVS and how the GFF process can improve donor coordination, harmonize approaches and mobilize resources for CRVS.
  Health financing strategy:
    An advanced draft has been prepared and was discussed during the mission
Main challenges
  Needed TA and a GFF coordinator are not yet in place although consultants have now been identified
Key opportunities
  There is momentum around the GFF process and it seems to be on the right track
  Mozambique is one of the focus countries of PMNCH  key areas for collaboration being explored
Next steps
  The GFF roadmap is being followed:
    Investment Case: GFF task force meeting every two weeks; next meeting in mid-July will focus on reports from 4 working groups (nutrition and family planning practices; adolescent health’ child health; and sexual reproductive maternal and neonatal health) that are preparing background materials
    Health financing strategy: next mission will discuss 1) how findings from the Health sector Public Expenditure Review, including the Fiscal Space Analysis section, can be incorporated; 2) key proposals that can be taken forward immediately, 3) implementation plan, and 4) draft TOR for TA to support implementation
    Next GFF mission in Maputo is scheduled for 15-19 August 2016

## Slide 14: Mozambique: background information
Country platform
  A task force has been appointed to lead the GFF process in MOH under the National Director of Public Health
  Existing coordination mechanisms under the SWAp is used as country platform
Investment Case
  The process has started and will be completed by November 2016
  The process for the IC is outlined in the GFF Roadmap
Complementary financing for the Investment Case
  All health partners are engaged in the process and resource mapping is under way
  There are ongoing discussions about how to best pool external financing, reduce fiduciary risk and ensure clear links between spending and the MOH’s stated priorities and desired results
Health financing strategy
  Over the past 2 years, the MOH has worked on a strategy, and the existing draft will be updated in the GFF process
    The technical working group on health financing (GTF) will support the elaboration of the HFS
  Consultations with various stakeholders including MOF, local governments, the National Social Security Institute, etc., are planned

## Slide 15: Senegal: recent developments
Latest updates
  World Bank mission took place in early June (not focused on the GFF but some GFF discussions occurred)
  Investment Case:
    Will prioritize interventions based on other strategies (see next slide) that are currently being updated
    UNICEF will fund EQUIST training.
  Health financing strategy:
    First meeting of steering committee that will develop strategy planned for 8 August
    Roadmap for development of strategy has been prepared
    TORs for TA for PFM assessment, fiscal space analysis, and health accounts have been developed:
      USAID (Abt) will support health financing TA in country
      GFF will hire former P4H focal point to support government
Key opportunities
  Strong government leadership and good dialogue among partners
Next steps
  GFF mission in September (exact dates to be finalized)

## Slide 16: Senegal: background information
Country platform
  Builds on existing coordination structures: RNMCAH platform was installed end of April and it will be extended to include private sector and CSOs (decree is currently with Minister)
Investment Case
  Will build on existing strategies that are currently being updated such as the emergency plan on maternal, newborn, child and adolescent health (SMNEA), nutrition strategy, and integrated child health strategy
Complementary financing of the Investment Case
  Discussions underway, including with Gavi, Global Fund, JICA, UNICEF, USAID, WHO
Health financing strategy
  The HFS will integrate the universal health insurance program (Couverture Maladie Universelle) that is currently under development

## Slide 17: Tanzania: recent developments
Latest updates
  No significant changes since June update
Next steps
  Mission planned in week of 18 July to follow up on implementation status, country platform and CRVS

## Slide 18: Tanzania: background information
Country platform
  SWAp coordination mechanism acts as country platform
  Supported by technical sub-groups focusing on RMNCAH and health financing
  Wide stakeholder engagement
Investment Case
  One Plan II used as Investment Case
Complementary financing of the Investment Case
  HSSP IV – in which the One Plan II is nested – is supported by Canada, DANIDA, DfID, GIZ, the GFTAM, Irish Aid, UNDP, UNFPA, UNICEF, USAID, the World Bank, and WHO
  World Bank/GFF Trust Fund financing: US$200m IDA, US$40m trust fund approved in May 2015
Health financing strategy
  Draft is currently in parliament
  Emphasis on: creation of a fiscal space through efficiency gains; partner alignment around prioritized investments; leveraging private sector resources; and expansion of performance-based financing to enhance quality, cost-effectiveness and sustainability

## Slide 19: Uganda: recent developments
Latest updates
  Discussions underway between MOH, USAID, and World Bank on complementary financing, including related to the private sector
  Videoconference held between the MOH and the GFF Secretariat on major challenge on finalization of the Investment Case (the links between costing and resource mapping, and the coherence of the costing) and on improving the coordination of the GFF process
Main challenges
  Costing and resource mapping are not well aligned
  Full potential of the GFF to improve coordination not being realized yet
Key opportunities
  Strong interest on the part of several key financiers to be more fully engaged in the process
Next steps
  MOH interested in hiring a coordinator that can assist with GFF process and with tracking and encouraging complementary financing
  Addressing of issues around costing
  World Bank project to be presented to Board in July 2016
  Further discussions around complementary financing

## Slide 20: Uganda: background information
Country platform
  Using the existing health sector coordination mechanism
Investment Case
  Sharpened RMNCAH Plan has five strategic shifts:
    Emphasising evidence-based high-impact solutions
    Increasing access for high-burden populations by promoting a set of service delivery mechanisms that operate synergistically
    Geographical focusing/sequencing
    Addressing the broader multisectoral context (focus on adolescent health)
    Ensuring mutual accountability for RMNCAH outcomes
  Includes health systems strengthening and capacity building required to deliver successfully
Complementary financing of the Investment Case
  Discussions now underway, including with DfID, Gavi, SIDA, and USAID
  World Bank/GFF Trust Fund financing: US$110m IDA, US$30m trust fund
    Board decision expected in July 2017
Health financing strategy
  Approved by MOH senior management, awaiting review by Cabinet
  Six objectives, including around resource mobilization, pooling, and strategic purchasing

## Slide 21: Other countries
Bangladesh
  Discussion on next health sector SWAp to begin in August, with GFF to be linked with this
  Additional Financing for ongoing health sector SWAp approved by World Bank Board
Nigeria
  MOH hosted a 2-day consultation with development partners in late June to discuss the National Health Sector Development Plan (NHSDP II), which includes RMNCAH
  The Minister of Health has approved moving forward with the Global Financing Facility activities including the development of an Investment Case for Nigeria, in alignment with NHSDP II
  Next steps: Planning for a workshop to support the development of the Investment Case